## Slide 2: IT String requirements
Marta Bajko
TE-MSC

## Slide 3: IT STRING SCOPE
Cluster E
Cluster D
Cluster A
Cluster B
Cluster C
Cluster F
DFH + CL IR PC
IR STRING DSH

## Slide 4: IT STRING short term ACTIVITIES
Based on scope , the preliminary studies and cost estimates will be prepared in parallel with
Set up a TEAM and the modus operandi with GL and WPLs
ESTABLISH a COMPLET list of INGREDIENTS
Set up a possible TIMELINE and agree on that
WORK out a TEST plan
Work out a BUDGET and RESOURCES
Check specifically those equipment which are only be used in Sm18
Extract from the Mandate
….

## Slide 5: TIMELINE test for HL LHC magnets
From these it was defined the test stand readiness requirements ( see the presentation of Volker)

## Slide 6: TIMELINE HL LHC IR STRING
STRING Phase2 can not start before mid 2021 due to late arrival of the 1st series of D1
STRING Phase1 can start in 2019 end with prototypes but Q3 will missing
2019
2018
2020
2021
2022
2023

## Slide 7
Quench: provoked, natural, holding current, propagation, detection, protection, clic, dump, switch
Cryogenics: cooling- warming speed ( Nb3Sn), heat load, recovery after quench, pressure, temperature, shielding
Integration: layout, interconnections, systems around ( racks, cables trays, control cables et), total weight
Powering: bus bar, connections, current leads, power distribution at warm and at cold, converters, water cooled cables
Electrical integrity: splice resistance, electrical insulation
Interlock
Vacuum: leak detection, beam screen
Instrumentation , DAQ systems, DB , QA, QC: specific or not to string
Alignment
Validation of a layout- integration
Validation of installation sequence and procedures
Validation of a system (of components)
Validation of their collective behaviour
Develop methods, techniques
Develop tooling
Develop procedures
X
definition of
Installations
Test
Operation
2
support
HWC
OP
GOALS in parallel:
HL LHC STRING preliminary TEST PLAN

## Slide 8
HL LHC STRING Ingredients… mainly from the WPs and possibly series equipment
Magnets: Q1, Q2a, Q2b, Q3,CP, D1
Power converters: 3 x 20 kA, 6 x 3 kA, 9 x 120 A
Power distribution: DFH and Current leads + SC link ( DSH)
Protection and EE system: 3 x switches x 20 kA, 3 x Dump
Cryogenic equipment ( cooling and cryo distribution)
Vacuum equippment
Cryogenic feed box
80 m
Shuffling Module
DFH
20 kA
12kA
20 kA
6 x3 kA
9 x 0.12 kA
Switch & Dump
SC Link (DSH)
Connection Module
LHe 4.2 K
He gas recovery
Bus Bars
Connection Module
Converters
D1
CP
Q3
Q2b
Q2a
Q1
Test the COLLECTIVE BEHAVIOUR of ingredients tested individually
SERVICE UPGRADE needed for :
Cryogenic cooling: additional 6 kW power plant and ( see estimates in the presentation of Luigi based on the complete planning of HL LHC magnet test plan + LHC spare magnet test program)
Demineralised water cooling: additional 55 m3/h ( aprox.0.5 MW) 
It is now blocked due to the fact that we have the approval together with the primary water
Primary water cooling: additional 2.5 MW for cryogenics
Electricity : tbc
IT STRING INGREDIENTS
These was defined and is part of the SM18 Test Facility UPG Project. See the presentation of Volker.
DAQ, Interlock, Software for Analysis ect is to be tested in the STRING