## Slide 1
SM18-UPG orientation
– Wrap-up (scenarios) –
22.6.2015
V. Mertens

## Slide 2
SM18-UPG
HL-LHC
10.0
MTP
13.0
HI-ENE
0.5
SC magnet R&D
1.1
SC RF R&D
X.X
Cluster D
5.6
Cluster Y
(cold conn.)
2.0 ?
SM18-UPG funding and expenses (in MCHF)
warm
3.3 ?
Cluster G (excl. HFM)
2.5
2 H benches for 20/18 kA
2 ?
CRG infrastructure
12.7
Building + general services
Electricity
1.0 ?
Crane
0.1
(0.25)
Safety
X.X
Misc.
X.X
SC link / String3
3.8 ?
HFM
X.X
HL-LHC
HL-LHC
~completed
Primary water
4.6
Buildings
1.0 ?
Controls/network
0.2 ?
EN-CV consol.
FCC
1.0
Notes: Estimates MB + LS

## Slide 3
Various scenarios
Starting from the budget assumptions (what is IN/NOT IN) on the previous slide ...(25.6 MCHF).
Technical solution for H benches to be defined and re-costed. All figures preliminary.
If String = YES + to be fully operated  scenarios A, B, C. If String = NO  scenario D.
Nominal cryogenics upgrade (35 g/s, #6), launch now, becoming fully ready in 2019.
Test programme can be carried out as foreseen (with 50 % margin + redundancy).
Total cost: 12.7 + 1.7 + 5.6 + (3 ... 8)  23 – 28 MCHF.
Reduced cryogenics upgrade (25 g/s, #5), launch now, becoming fully ready in 2019.
Test programme can almost be carried out as foreseen (35 % margin + redundancy).
Total cost: 11.7 + 1.7 + 5.6 + (3 ... 8)  22 – 27 MCHF.
Much reduced cryo upgrade (10 g/s, #4), launch now, becoming fully ready in 2019.
Test programme at risk; delay to be anticipated (15 % margin + no redundancy after String; reduced testing during String („margin“ < 0).
Total cost: 5.7 + 1.2 + 5.6 + (3 ... 7.5)  15.5 – 20 MCHF.
Only 3rd WPU (no refrigerator, #3), launch now, becoming ready in 2017/18.
Test programme not possible as planned, no String, important delays.
Total cost: 2.7 + 0.5 + 5.6 + (3 ... 7)  12 – 16 MCHF.
Delay decision by 1 yr when String test scope is better defined, schedules may have evolved, H-bench solution clearer, budget better known, costs re-evaluated.
Cryogenics becomes available in 2020 (String planned to operate as from mid-2020).
A
B
C
D
E