## Sheet1
Description of task | Responsible | Cables to be removed | DEC | N0 cables to be removed | Cables to be pulled | DIC | N0 cables to be pulled | DIR
BI line
BI corrector magnets (power) | S. Pittet | tbc (?) | Not received | ? | tbc (?) | Not received | ? | Received*
BI corrector magnet interlocks | P. Dahlen | yes (1) | Not received | ? | yes | Not received | ? | ?
BI quadrupoles (power) | S. Pittet | yes | Not received | ? | yes | Not received | ? | Received*
BI quadrupole interlocks | P. Dahlen | yes | Not received | ? | yes | Not received | ? | ?
BI.BVT (power) | S. Pittet | yes | Not received | ? | yes | Not received | ? | Received*
BI.BVT interlocks | P. Dahlen | yes | Not received | ? | yes | Not received | ? | ?
BI.DIS | R. Barlow | yes | Not received | 500 | yes | Not received | 200 | Received
BI.SMV: 3 transformers | S. Pittet | yes | Not received | ? | yes | Not received | 3 DC cables specified | N/A
BI.SMV position monitors | F. Roncarolo | yes | Not received | ? | yes | Not received | ? | ?
BLMs in BI line and injection region | C. Zamantzas | no? (yes if done in LS2) | Not received | ? | yes | Received | 16 | Not received
Diamond BLMs in injection region | C. Zamantzas | no | N/A | N/A | yes | Received | 8 | Not received
Head-/Tail Dumps (at BI.SMV) | D. Grenier | no | N/A | N/A | yes | Done in LS1 | 1 | N/A
H0/H- Dumps (at BI.BSW4) | D. Grenier | no | N/A | N/A | yes | Done in LS1 | 1 | N/A
BI.KSW: control cables | G. Grawer | no? | N/A | N/A | yes | Received | 24 | N/A
BI.KSW: power cables | G. Grawer | yes | Received | 12 | yes | Received | 32 | N/A
BI.SMH | A. Prost | yes | Received | 47 | N/A | N/A | N/A | N/A
BI.BSW controls | C. Chanavat | no | N/A | N/A | yes | Not received | ? | ?
BI.BSW power | S. Pittet | no | N/A | N/A | yes | Not received | 18 DC cables specified | N/A
Charge exchange foil | P. Van Trappen | no | N/A | N/A | yes | Received | 38 | Received
H0/H- monitor | F. Roncarolo | no | N/A | N/A | yes | Received | 28 | N/A
Stripping foil camera | S. Burger | no | N/A | N/A | yes | Received | 24 | N/A
Vacuum equipment | P. Bellorini | no | N/A | N/A | yes | Received | 132 | N/A
BR (Booster Ring)
Q-strip converters (QDE3+14) | S. Pittet | no | Not received | ? | yes | Not received | ? | Received*
New RF cavities | M. Haase | yes | Received | 2240 LS2 | yes | Received | 855 LS2 | ?
Finemet Test Cavity | M. Haase | yes | Received | 115 LS2 | no | N/A | N/A | N/A
BTKRF | M. Haase | yes | Received | 15 LS2 | no | Received | 140 LS2 | N/A
Transverse damper kickers | A. Blas | yes | Received | 32 | yes | Received | 32 | N/A
Transverse damper pickup | A. Blas | yes | Received | 16 | yes | Received | 32 | N/A
Ring pickups | J. Belleman | yes | Received | 48 | yes | Received | 224 | N/A
Watchdog BR.TMD8L1 | P. Odier | yes | Received | 10 | yes | Received | 24 | N/A
BLMs (2 FLAT-ICs per section) | C. Zamantzas | no? (yes if done in LS2) | Not received | ? | yes | Received | 104 | N/A
Matching monitor | M. Duraffourg | no | N/A | N/A | yes | Received | 67 | N/A
New wire scanners | B. Dehning | no | N/A | N/A | yes | Not received | ? | N/A
Transfer lines (BT, BTP, BTM)
Wide-band pickup (BTP PS side) | J. Belleman | no | N/A | N/A | yes | Received | 10 | N/A
Magnets power (number still tbd) | A. Newborough | yes | Not received | ? | yes | Not received | ? | N/A
Interlocks (WICs) for new magnets | P. Dahlen | no | N/A | N/A | yes | Not received | ? | N/A
BLMs | C. Zamantzas | no? (yes if done in LS2) | Not received | ? | yes | Received | 36 | ?
Surface
Beam Interlock System | C. Martin, S. Gabourin | no | N/A | N/A | yes | Received | 22 | N/A
Received* | Request for racks integration. Installation by TE-EPC.