## Slide 1: Wa105 6x6x6
D.Smargianaki
1
D.Mladenov
M.Nessi
D.Smargianaki

## Slide 2
D.Smargianaki
2
Wa105 6x6x6
Roof
2 x Wall
2 x Wall
Floor
*11.716 m
Without
The roof :
11.116 m
*11.764 m
*11.764 m
*External dimensions

## Slide 3
EHN1 CE ready by 1-July-2016
We expect that the cryostat preparation/installation will take 6-7 months if done sequentially
Can we start some pre-assembly in January 2016 ?
Can we push the preassembly to the warm and part of the membrane structure?
Can we have the roof be treated separately?
D.Smargianaki
3
Requirements/constraints

## Slide 4: wa105 6x6x6 Warm structure PRE-ASSEMBLY SEQUENCE
D.Smargianaki
4

## Slide 5
D.Smargianaki
5
1. Assemble one by one the floor element and the 4 walls, including the stainless steel plate, on the floor
2. As soon as one is finished it get mounted into a structure
3. With this we prove that the assembly can fit geometrically
4. Once the structure is finished, we measure it. In particular the top to find out how geometrically the roof has to be assembled. We also trace the position of the rods, for a later assembly
5. We bring back one by one the pre-assemblies on the floor and then we add GTT panels where possible
Pre – assembly sequence

## Slide 6: Assemble one by one the floor element and the 4 walls, including the stainless steel plate, on the floor
D.Smargianaki
6
1

## Slide 7
D.Smargianaki
7
Outer structure pRe - assemblies
Floor
4 x Wall
& stainless steel
plate everywhere
1

## Slide 8: As soon as one is finished it get mounted into a structure With this we prove that the assembly can fit geometrically Once the structure is finished, we measure it. In particular the top to find out how geometrically the top has to be assembled
D.Smargianaki
8
2
3
4

## Slide 9
D.Smargianaki
9
2

## Slide 10
D.Smargianaki
10
2

## Slide 11
D.Smargianaki
11
2

## Slide 12
D.Smargianaki
12
2

## Slide 13
D.Smargianaki
13
2
3
4

## Slide 14
D.Smargianaki
14
Where can we do this ?
We need 15 x 15 m2 to do the flat preassemblies, one by one
Then we need 15 x 15 m2 for the 3rd assembly
And we need storage place for the components we are taking down later
We need a 40 tons crane in each location
2 teams of 4 persons each, working on the 2 locations
Plus surveyors and QA people

## Slide 15
D.Smargianaki
15
Flat pre-assembly
3rd pre-assembly
pre-assembly storage

## Slide 16: We bring back one by one the pre-assemblies on the floor and then we add GTT panels where possible
D.Smargianaki
16
5

## Slide 17
D.Smargianaki
17
Outer structure pRe - assemblies
Floor
4 x Wall
& stainless steel
plate everywhere
5

## Slide 18
D.Smargianaki
18
Adding GTT panels
Rods in place
Partial secondary membrane
Partial primary membrane
5

## Slide 19
D.Smargianaki
19
assembly in the final position
Weld SS plate in the corners
Add GTT foam
Add secondary membrane
Finish the last layer of foam
Pose the missing primary membrane
Final welding

## Slide 20
D.Smargianaki
20
ROOF
Prepare it on the floor
Drill holes for penetration
Weld reinforcement tubes
Install it
Install missing foam and membrane in the corners
Finish welding membrane

## Slide 21
D.Smargianaki
21
Final assembly

## Slide 22: BUCKUP SLIDE
D.Smargianaki
22

## Slide 23
D.Smargianaki
23
EHN1 – some dimensions
9.5 m
14.2m
18.2 m
Distances :
Between floor level & Crane level = 9.5 m
Between floor level & First beam level = 14.2 m
Between floor level & Roof level = 18.2 m
Floor level
Crane level
Roof level
First beam level