## Slide 1: Organization of Task 5.2: Study accelerator dipole magnet design options
F. Toral - CIEMAT
CIEMAT-VC, July 9th, 2015

## Slide 2
Title: Study accelerator dipole magnet design options
Participants: CEA, CERN, CIEMAT, INFN, KEK (?)
Summary
Milestones | 
MS-5.2 Baseline specifications and assumptions for accelerator magnet | M10
Deliverables | 
D-5.1 Overview of magnet design options | M10

## Slide 3: Description
3
The initial scheme was based on a first layout selection, followed by electromagnetic and mechanical studies performed sequentially by different teams.
Now we have agreed that each participant will study one coil layout, both including electromagnetic and mechanical calculations, to choose one preferred option for further analysis (Task 5.4):
  CEA: block design
  CERN: review of the state of the art
  CIEMAT: common coil design
  INFN: cos-theta design

## Slide 4: Remarks
4
Cable grading is likely necessary to reduce the cost: high Jc and low Jc (even NbTi) blocks could be present.
One must keep an eye on coil end effects from the beginning: minimum bending radius, Lorentz forces.
The common coil layout is intrinsically a double aperture design.
Electromagnetic design is not enough. We need to address the mechanical concept to take care of the huge electromagnetic forces.
Some assumptions on cable properties are necessary at the very beginning for the electromagnetic calculations.

## Slide 5: Timeline
5
End of August: design parameters, constraints and evaluation criteria.
End of October: first electromagnetic design.
End of December: first mechanical design. Identification of problems for further analysis.
End of Marach: Design report, including first considerations for coil-ends and fabrication feasibility.
Within end of April: internal review and choice.