## Slide 1: HL-LHC ACTIVITIES DURING LS2
Paula Álvarez López,
on behalf of the HL-LHC Project team

## Slide 2: Agenda
HL-LHC baseline evolution
Overview of LS2 installation works on the LHC Layout
LS2 installation works detailed by WP
Wrap up: summary of all LS2 works for HL-LHC

## Slide 3: BASELINE as of September 2014 (Chamonix Session)

## Slide 4
DF(X-M) +
SC Link DSH (X-M)
Cryo line IR+MS
Alignment
QPS2
Magnet system
MQXFA MQXFB, MBXF, MBRD, MQYY,
Q5 1.9, Q6 1.9
MCBXFB, MCBXFA, MQSXF, MCTXF, MCTSXF, MCDXF, MCDSXF, MCOXF, MCOSXF, MCSXF,MCSSXF, MCBRD, MCBYY
Beam vacuum
TAXS, TAXN
Interaction Region and MS
IP 1,5
Collimation (TCTPM, TCL, TCLM, TCTP)
Beam diagnostic
BPMSQW, BMPSQ, BPMSQT, BMLC
DS Collimation for ion
IP 2
H.F. dipoles
Cryo-bypass + TCLD
DFH(X-M) +
Power converters
SC link/powering
IP 7
Hor. SC Link
DSH + DFA
Power converters
EE
Crab Cavity Cryomodules
RF system
Loads, circulators, RF power, LLRF, HVPS, central LLRR
DS Collimation pp (TBC RUN II)
IP 1,5
H.F. dipoles
Cryo-bypass + TCLD
DS Collimation pp (TBC RUN II)
IP 7
H.F. dipoles
Cryo-bypass + TCLD
Rad-hard electronics for
BLM and BPM
CC diagnostic and protection
P
I
C
BIS
DFA+
SC Link DSHA
DFHA +
Power converters
SC link/
Powering arc
IP 1,5
Cryoplant
IP 1,5
CB
Warm compressor and other surface eq.
Equipment on the Beam | Tunnel equipment | Vert. J | Surface Eq. | Dis.
HL-Baseline & LS2
HL-LHC Baseline
Susceptible to LS2

## Slide 5
Cryoline for RF
Beam diagnostic
IP 4
Fast wire scanners BWSF
New light extraction line BSRT
Beam gas vertex detector BGV
Injection protection
IP 2, 8
TDIS
TCLIA, TCLIB (TBC)
TCDD TCDDM (TBC)
TCLIM (TBC)
MKI (TBC)
Q5 at point 6
IP 6
Dump (TBC)
IP 6
TCDS (TBC)
MKB, TDE (TBC)
High rad warm magnets (TBC)
IP 7
Collimation upgrade
Secondary TCSPM
Primary TCP TCPP
TCSG, TCLA, TCAP
IP 3, 7
IP 3 ,7
IP 3, 7
TCSP
IP 6
CB
Cryoplant
IP 4
Warm compressor and other surface eq.
HL-Baseline & LS2
HL-LHC Baseline
Equipment on the Beam | Tunnel equipment | Vert. J | Surface Eq. | Dis.
P
I
C
BIS
TAXN for LHCb
IP 8
Susceptible to LS2

## Slide 6: BASELINE TODAY, SEPTEMBER 2015

## Slide 7
DF(X-M) +
SC Link DSH (X-M)
Cryo line IR+MS
Alignment
QPS2
Magnet system
MQXFA MQXFB, MBXF, MBRD, MQYY,
Q5 1.9, Q6 1.9
MCBXFB, MCBXFA, MQSXF, MCTXF, MCTSXF, MCDXF, MCDSXF, MCOXF, MCOSXF, MCSXF,MCSSXF, MCBRD, MCBYY
Beam vacuum
TAXS, TAXN
Interaction Region and MS
IP 1,5
Collimation (TCTPM, TCL, TCLM, TCTP)
Beam diagnostic
BPMSQW, BMPSQ, BPMSQT, BMLC
DS Collimation for ion
IP 2
H.F. dipoles
Cryo-bypass + TCLD
DFH(X-M) +
Power converters
SC link/powering
IP 7
Hor. SC Link
DSH + DFA
Power converters
EE
Crab Cavity Cryomodule
RF system
Loads, circulators, RF power, LLRF, HVPS, central LLRR
DS Collimation pp (TBC RUN II)
IP 1,5
H.F. dipoles
Cryo-bypass + TCLD
DS Collimation pp (TBC RUN II)
IP 7
H.F. dipoles
Cryo-bypass + TCLD
Rad-hard electronics for
BLM and BPM
CC diagnostic and protection
P
I
C
BIS
DFA+
SC Link DSHA
DFHA +
Power converters
SC link/
Powering arc
IP 1,5
Cryoplant
IP 1,5
CB
Warm compressor and other surface eq.
HL-Baseline & LS2
HL-LHC Baseline
Baseline, now postponed
No longer baseline
Equipment on the Beam | Tunnel equipment | Vert. J | Surface Eq. | Dis.
(SPS Test)

## Slide 8
Cryoline for RF
Beam diagnostic
IP 4
Fast wire scanners BWSF
New light extraction line BSRT
Beam gas vertex detector BGV
Injection protection
IP 2, 8
TDIS
TCLIA, TCLIB
TCDD TCDDM
TCLIM
MKI prototype
Q5 at point 6
IP 6
Dump (TBC)
IP 6
TCDS (TBC)
MKB, TDE (TBC)
High rad warm magnets
IP 7
Collimation upgrade
Secondary TCSPM
Primary TCP TCPP
TCSG, TCLA, TCAP
IP 3, 7
IP 3 ,7
IP 3, 7
TCSP
IP 6
CB
Cryoplant
IP 4
Warm compressor and other surface eq.
P
I
C
BIS
HL-Baseline & LS2
HL-LHC Baseline
HL-Baseline but postponed
No Baseline
TAXN for LHCb
IP 8
Equipment on the Beam | Tunnel equipment | Vert. J | Surface Eq. | Dis.
New transportable refrigerator
Upgrade of 18kW refrigerator
IP 4
Mask for D1
Mask for D1
IP 8

## Slide 9: LS2 INSTALLATION OVERVIEW

## Slide 10: Installation Overview for LS2
Cryo-bypass+TCLD
TAXN
Fast wire scanners
BGV
TCSPM
Mask for D2
In-situ a-C coating
New Q5
Prep. works halo diagnostic systems
High bandwidth pick-ups
Mask for D1
TDIS
New transp. refrigerator

## Slide 11: LS2 INSTALLATION WORKS DETAILED BY WP

## Slide 12: WP3 – IR Magnets
Equipment | Quantity | Location
Q5 | 2 units | P6
Q5

## Slide 13: WP4 – Crab Cavities & RF: SPS Tests
Equipment | Quantity and period | Location
Prep. Works (RF & Cryo lines, movable table) | EYETS 2016 | SPS-LSS6
Cryomodule 1 | 1 proto in YETS 2017 | SPS-LSS6
Cryomodule 2 | 1 proto in LS2 | SPS-LSS6
RF system Installation | YETS 2017, LS2 | SPS-LSS6
Crab cavity cryomodule
RF system

## Slide 14: WP5 – Collimation
Cryo-bypass+TCLD
Equipment | Quantity | Location
TCSPM | 1 prototype | P7
Wire collim. | Up to 4 | P1, P5
Intervention for crystal collimation | - | P7
Cryo-bypass + TCLD | 2 units | P2
TCSPM | 8 units | P7
Hollow e-lenses | Prep. works | P4
TCSPM
EYETS 2016
YETS 2017
Hollow e-lens prep. works

## Slide 15
TAXN
Equipment | Quantity | Location
TAXN for LHCb | 2 units (1 per IP side) | P8
Mask for D2 | TBC | P8
Mask for D2
WP8 – Collider-Experiment Interface

## Slide 16: WP9 – Cryogenics
Equipment | Location
Upgrade of 18kW refrigerator | P4
New transportable refrigerator | P4
New transportable refrigerator

## Slide 17: WP 12 – Vacuum
Equipment | Location
In-situ a-C coating | P2, P8
Works for other WPs1 | P2, P4, P6, P7, P8
In-situ a-C coating
WP3 | Q5 | P6
WP5 | By-pass collimator + TCLD | P2
WP5 | Hollow e-lens | P4
WP5 | TCSPM | P7
WP8 | TAXN | P8
WP8 | Mask for D2 | 
WP13 | Fast wirescanners | P4
WP13 | BGV | P4
WP14 | TDIS | P2,P8
WP14 | Mask for D1 | P2, P8
1 EQUIPMENT REQUIRING VACUUM INTERVENTION

## Slide 18: WP 12 – Vacuum
Equipment | Location
In-situ a-C coating | P2, P8
Works for other WPs1 | P2, P4, P6, P7, P8
In-situ a-C coating
WP3 | Upgrade of Q5 in P6 | P6
WP5 | By-pass collimator + TCLD and Empty Cryostat | P2
WP5 | Hollow e-lens & Crystal collimation works | P4
WP5 | New secondary collimator TCSPM | P7
WP8 | TAXN | P8
WP8 | Mask for D2 | P8
WP13 | Fast wirescanners | P4
WP13 | Beam Gas Vertex Detector (BGV) | P4
WP14 | TDIS | P2,P8
WP14 | Mask for D1 | P2, P8
1 WPs AND EQUIPMENT REQUIRING VACUUM INTERVENTION
Courtesy:
V. Baglin

## Slide 19: WP 13 – Beam diagnostics
Fast wire scanners
BGV
Equipment | Quantity | Location
Beam gas vertex detector | 1 proto. | P4
Fast wire scanners | 1 proto. | P4
High bandwidth pick-ups | 1 (SPS)+ 2 proto. | P4
Prep. works for halo diagnostic systems on synchroton light monitor | - | P4
High bandwidth pick-ups
Prep. for halo diagnostic systems on synchroton light monitor

## Slide 20: WP 14 – Beam transfer & Kickers
TDIS
Mask for D1
Equipment | Quantity | Location
MKI prototype | 1 | TBC
Injection absorber (TDIS) | 6 units | P2, P8
Mask for D1 | 2 units | P2,P8
Upgrade of control system: LBDS MKD generator upgrade MKD controls upgrade |  | 
EYETS 2016 (tbc)

## Slide 21: WP 17.1 – Civil Engineering:
Building description | P1 | P5 | Location
Shaft | PM17 | PM57 | UNDERGROUND
RF gallery side 17 | UA17 | UA57 | 
Cryogenic cavern | US17 | US57 | 
Water cooling station cavern/area | UW17 | UW57 | 
SC cryo-link gallery | UL17 | UL57 | 
Power converter gallery | UR15 | UR55 | 
Personnel/safety gallery | UPR15 | UPR55 | 
SC cryo-link gallery | UL13 | UL53 | 
RF gallery side 13 | UA13 | UA53 | 
Helium tank platform | SHE17 | SHE57 | SURFACE
Ventilation building | SU17 | SU57 | 
Electrical building | SE17 | SE57 | 
Head shaft building | SD17 | SD57 | 
Compressor building | SHM17 | SHM57 | 
Extension to technical galleries | SL11/13 | SL5/51 | 
New technical gallery | SL16/17 | SL56/57 | 
Cooling towers | SF17 | SF57 | 
Helium unloading towers | SDH17 | SDH57 | 
Nitrogen tank platform | SLN17 | SLN57 | 
Rectifier building | SR17 | SR57 | 
Post LS2
Pre LS2

## Slide 22: WPs with no installation works during LS2
WP6A, WP6B: no installation works foreseen before LS3
WP11: Two complete units (15 m long) will be manufactured and tested before LS2. Whether the installation will happen in LS2 or in a subsequent slot (either LS3 or an EYETS during Run3) will be decided in 2016. Refer to Lucio’s presentation.
WP7: Energy Extaction (EE) and Quench Protection (QDS) systems linked to 11 T and triplets production. Other works (mainly consolidation) are planned for LS3.

## Slide 23: SM18: Timeline for the different tests for HL-LHC magnets
2015 2016 2017 2018 2019 2020 2021 2022
The first milestone is November 2015 for the model magnet testing.
The vertical test bench capable to test partially this models will be delivered only in May 2016 and for full test in September 2016 cluster D. (See photo on the civil engineering work that is ongoing in SM18).
Planning has been kept as last year for what concerns modifications of test benches.
Courtesy:
M. Bajko

## Slide 24: WRAP UP: SUMMARY OF ALL LS2 WORKS

## Slide 25
Description | WP | Period | Location | Risk
Preparation works for Crab Cavity installation | 4 | EYETS 2016 | SPS – LSS6 | 
Installation of TCSPM prototype | 5 | EYETS 2016 | P7 | 
Installation of wire collimators | 5 | EYETS 2016 | P1, P5 | 
MKI Prototype | 14 | EYETS 2016 | TBC | 
Installation of CC Cryomodule (DQW) & RF | 4 | EYETS 2017 | SPS – LSS6 | 
Preparation works for crystal collimation | 5 | EYETS 2017 | P7 | 
Change of Q5 | 3 | LS2 | P6 | 
Installation of CC Cryomodule (RFD) & RF | 4 | LS2 | SPS – LSS6 | 
Installation of Cryo-bypass + TCLD | 5 | LS2 | P2 | 
Installation of TCSPM series | 5 | LS2 | P7 | 
Preparation works for hollow e-lens | 5 | LS2 | P4 | 
Installation of TAXN for LHCb | 8 | LS2 | P8 | 
Installation of Mask for D2 | 8 | LS2 | P8 | 
Upgrade of 18 kW refrigerator | 9 | LS2 | P4 | 
New transportable refrigerator | 9 | LS2 | P4 | 
In-situ a-C coating | 12 | LS2 | P2, P8 | 
Fast wirescanners | 13 | LS2 | P4 | 
Beam gas vertex detector | 13 | LS2 | P4 | 
High bandwidth pick-ups | 13 | LS2 | P4 | 
Prep. Works Halo diagnostic systems on synchroton light monitors | 13 | LS2 | P4 | 
TDIS Installation | 14 | LS2 | P2, P8 | 
Mask for D1 | 14 | LS2 | P2, P8 | 
Upgrade of control system | 14 | LS2 | - | 

## Slide 26
…and big thank you to all WP leaders and engineers for their contribution!
THANK YOU ALL FOR YOUR ATTENTION!

## Slide 27: EXTRA SLIDES

## Slide 28: WP11 – Current baseline and options for installation:
LS3 Installation (P2, P7)
OPTION: LS4 Installation (P1, P5)
Location | Installation | Quantity
P2 | LS3 | 2 unit *
P7 | LS3 | 2 or 4 units (tbc)
P1, P5 (Option) | LS4 | Max. 8 units
* 1 unit = 2 MBH + 1 BPC |  | 

## Slide 29: WP Interfaces
 | WP1 | WP2 | WP3 | WP4 | WP5 | WP6A | WP6B | WP7 | WP8 | WP9 | WP 10 | WP 11 | WP 12 | WP 13 | WP 14 | WP 15 | WP 16 | WP 17
WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  | - | - | -
WP3 |  |  |  | - |  |  |  |  | - |  |  | - |  |  |  |  |  | 
WP4 |  |  | - |  |  | - |  |  | - |  | - | - |  |  | - |  | ? | 
WP5 |  |  |  |  |  | ? |  |  |  |  |  |  |  |  |  |  |  | 
WP6A |  |  |  | - | ? |  |  |  | - |  |  |  |  | - | - |  |  | 
WP6B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP8 |  |  | - | - |  | - |  |  |  | - |  | - |  |  |  |  | - | 
WP9 |  |  |  |  |  |  |  |  | - |  | ? |  |  |  | - |  |  | 
WP10 |  | - |  | - |  |  |  |  |  | ? |  |  |  |  |  | - | - | -
WP11 |  |  | - | - |  |  |  |  | - |  |  |  |  |  | - |  |  | 
WP12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - | -
WP13 |  |  |  |  |  | - |  |  |  |  |  |  |  |  |  |  | - | 
WP14 |  |  |  | - |  | - |  |  |  | - |  | - |  |  |  |  |  | 
WP15 |  | - |  |  |  |  |  |  |  |  | - |  |  |  |  |  | - | -
WP16 |  | - |  | ? |  |  |  |  | - |  | - |  | - | - |  | - |  | -
WP17 |  | - |  |  |  |  |  |  |  |  | - |  | - |  |  | - | - | 
WP1 | Management
WP2 | Accelerator physics
WP3 | Magnets
WP4 | Crab cavities
WP5 | Collimation
WP6 | Cold powering
WP7 | Machine protection
WP8 | Collider Experiment Interface
WP9 | Cryogenics
WP10 | Energy Deposition & Absorber Coordination
WP11 | 11-T Dipole Magnets
WP12 | Vacuum
WP13 | Beam Diagnostics & Instrumentation
WP14 | Beam Transfer and Kickers
WP15 | Integration & (De)-Installation
WP16 | Hardware commissioning
WP17 | Infrastructure, Logistics and Civil Engineering
Courtesy: C. Parente

## Slide 30: WP17 Interface Matrix
 | WP 17.1 | WP 17.2 | WP 17.3 | WP 17.4&5 | WP 17.6 | WP 17.7 | WP 17.8 | WP 17.9 | WP 17.10
WP1 |  |  |  |  |  |  |  |  | 
WP2 | - | - | - | - | - | - | - | - | -
WP3 | - |  | - | - |  |  |  |  | 
WP4 |  |  |  |  |  |  |  |  | 
WP5 | - |  |  |  |  |  |  |  | 
WP6A |  |  | - |  |  |  |  |  | 
WP6B |  |  |  | ? | - |  | ? |  | 
WP7 |  |  | ? |  | ? | - |  |  | 
WP8 | - |  |  |  |  |  | ? |  | 
WP9 |  |  |  |  | - | ? |  |  | 
WP10 | - | - | - | - | - | - | - | - | 
WP11 | - |  | - | - |  |  |  |  | 
WP12 | - |  |  |  |  |  | ? |  | 
WP13 |  |  | - | - |  | - | ? |  | 
WP14 | - |  |  |  |  |  | ? |  | 
WP15 |  |  |  |  |  |  |  |  | 
WP16 |  |  |  |  |  |  |  |  | 
WP17.1 | P |  |  | ? | ? |  | ? |  | 
WP17.2 |  | P |  |  | ? | ? | ? |  | 
WP17.3 |  |  | P | - | - | ? | ? |  | 
WP17.4&5 | ? |  |  | P | - | ? | ? |  | 
WP17.6 | ? | ? | - | - | P | ? | ? |  | 
WP17.7 |  | ? | ? | ? | ? | P | ? |  | 
WP17.8 | ? | ? | ? | ? | ? | ? | P |  | 
WP17.9 |  | - |  |  |  |  |  | P | 
WP17.10 |  |  |  |  |  |  |  |  | P
WP17.1 | Civil Engineering
WP17.2 | Electrical Distribution
WP17.3 | Cooling and Ventilation
WP17.4 | Acces & Alarms
WP17.5 | Technical Monitoring
WP17.6 | Survey & Alignment
WP17.7 | Transport
WP17.8 | Upgrade of Test Facilities for HL-LHC
WP17.9 | Logistics & Storage
WP17.10 | Safety
Source: HL-LHC Conceptual Specs.

## Slide 31: P1 Layout

## Slide 32: P5 Layout