## Slide 2: Ions: Updates on LIU baseline and options (incl. staged implementation), parameter reach, schedule
S. Gilardoni for LIU-ION group
In collaboration with:
G. Bellodi, C. Carli, J. Jowett, M. Bodendorfer, D. Manglunki et al.
HL-LHC – LIU Joint Meeting – 15 Oct. 2015

## Slide 3: Clarification of the scope (pending confirmation from HL-LHC)
Follow-up after C&S review: running scenario after Alice upgrade as requested by ALICE (see ALICE LOI CERN-LHCC-2012-012):
  2020 – Pb–Pb 2.85 nb-1
  2021 – Pb–Pb 2.85 nb-1
  2022 – pp reference run
  2023,2024 – LS3
  2025 – Pb–Pb 2.85 nb-1
  2026 – ½ Pb–Pb 1.5 nb-1 + ½ p–Pb 50 nb-1
  2027 – Pb–Pb 2.85 nb-1
  In total ~ 4 runs to cumulate 10 nb-1 starting integrating the 10 nb-1 after LS2, i.e., 2021.

## Slide 4: New calendar for ions run
Most recent calendar shared with HL-LHC (see John’s presentation)
Same as before but 1 year later
2021 - Pb-Pb 2.85 nb-1
2022 - Pb-Pb 2.85 nb-1
2023 - pp reference run
2024, 2025.6 - LS3
2027 - Pb-Pb 2.85 nb-1
2028 - ½ Pb-Pb 1.5 nb-1 + ½ p-Pb 50 nb-1
2029 - Pb-Pb 2.85 nb-1
2030 LS4

## Slide 5: Timelines of LIU
LIU (machine and simulation) studies during Run 2 until LS2
  Key dates for pending decisions until 2016
LIU installations and hardware work mainly during LS2
Beam commissioning of LIU beams
  Pb ion beams need to be ready by 2021 ion run
  Proton beams during Run 3 to be ready after LS3
Run 2
Run 3
LS 2
PHASE 1 with LIU studies, installation and beam commissioning
Run 2
Run 3
Run 4
LS 2
LS 3
LS 4
LS 5
PHASE 2
Run 3
Run 4
HL-LHC installation

## Slide 6: Post LS2 Scheme
1.55 108 ions @ injection
max. 13 injections
200ns
100ns
50ns spacing
50ns spacing
100ns
Twice 8x108 ions/bunch
~2μs
LEIR
PS
SPS
LHC
max. 1248
Baseline requirements:
Maximize number of bunches in LHC with 50 ns bunch spacing
  Slip stacking in SPS
Increase at maximum the intensity per bunch.
  More intensity from LEIR
  More intensity from L3 and increased rep. rate
Transverse emittance is less important than intensity

## Slide 7: Impact of need of 50 ns
Only way to get it:
100 ns from the PS  bunch splitting @ low energy
  Not possible to split at high energy because too close to transition
    PS optics not so flexible to change gamma transition as for the SPS.
  Less intensity per bunch compared to 200 ns or 100 ns spacing with no splitting (as for protons 25 – 50 ns)
    Not possible so far to double the intensity per bunch extracted by LEIR to maintain the same intensity as the 200/100 ns with no splittings
Slip stacking in SPS
  Bunch spacing changed from 100 @ injection to 50 ns in intermediate porch to avoid spending too long time @ low energy
  Obs: 25 ns not possible because would require bunch splitting in PS.

## Slide 8: Ion project baseline life-time
LEIR
Linac3
Design
Procur.
Inst.
Comm.
Xenon Run
Performance improvements
Performance improvements
Performance improvements
Performance improvements
Performance improvements
SPS
Design
Commissioning
Procurement
Installation

## Slide 9: Parameter table @ SPS extraction
HL-LHC parameters based EDMS document 1525065 v.0.3
(evolving document)
Production scheme with goal of matching requested beam param.
EDMS document 1533832 LIU of beam parameter in preparation, in collaboration with John.
(evolving document)
Obs: TDR in preparation

## Slide 10: Parameter table, closer look with Lumi full model
Maximum achievable integrated luminosity with current baseline : 1.17 nb-1/y Maximum achievable integrated luminosity with upgraded SPS kicker : 1.67 nb-1/y
See John’s talk

## Slide 11: Main complex limitations (where we are a good fraction of our resources)
Linac3 reduced maximum current
  Larger number of injections in LEIR  longer cycles  longer SPS FB
LEIR maximum intensity due to losses at capture
  Limiting maximum performances of the complex
Losses/emittance degradation at SPS FB due to IBS-TSK-like effect
  Intensity decreases along the batch with footprint remaining on LHC specific luminosity

## Slide 12: Linac3
Intensity from the Linac limited due losses between source and LEBT
Emittance from the source too large compared to the acceptance of the RFQ
  longstanding issue for device measuring emittance from the source
An initial 20% improvement in transmission in the low energy part of the Linac expected by installing new electrostatics lens (einzel lens) and increasing aperture between source and first solenoid
  Work to be done during YETS 2015-16
  Linac improvement studies from early 2016, maximum gain beyond 20% will be probed, brainstorming started to possible studies.
  Revising BI requirements for studies
100 ms rep. rate operation to increase injection rep. rate in LEIR
  Upgrade of power converters advanced to YETS 2015-16
  100 ms operation limited before LS2 because of cooling and ventilation consolidation needed, but test periods already in 2016

## Slide 13: The Pb54+ life-cyle in LEIR
Extraction
@ 2880ms
Asymptotic int. lim.
max. extr.:
5.8x108 Pb54+/bunch
(Coasting beam)
B-field
BHN current [1000A]
LIU Ions goal
?

## Slide 14: LEIR performances
Performances limited at beam capture for unclear reasons
- direct space charge + resonances preferred mechanism, test starting this month for transverse emittance control
- not clear sign of beam instabilities observed
- chromaticity correction did not improve losses
- local vacuum degradation seems excluded from past desorption studies
Studies limited in time because
- machine model including impedance, e-cooler and precise optics not
available  planning for 2016 development
- machine availability limited to Pb ion run (see Django’s talk), reason of early start
in 2016.
- tried to make best use of Ar run for studies. Will do the same also for Xe.
Same resources running the machine (for Ar post LS restart and new particle) and studying performance limits.
100 ms injection to increase intensity before acceleration
- e-cooling providing double current for faster cooling rate (proved with Ar).
Already tested for maximum current, cooling rate not yet.
- full tests planned for 2016

## Slide 15: 2015 planning: Ar until April – Pb in LEIR since July
Argon run

## Slide 16: Planning of LEIR studies
Activity | 2015 |  |  |  |  |  |  |  |  |  |  |  | Status
 | J | F | M | A | May | Jun | Jul | A | S | O | N | D | 
LEIR startup |  |  |  |  |  |  |  |  |  |  |  |  | 
LEIR for collider |  |  |  |  |  |  |  |  |  |  |  |  | 
Polarity check |  |  |  |  |  |  |  |  |  |  |  |  | HW prepared, but effect of chroma from Ar run ad now Pb
Optics measurements (LOCO) |  |  |  |  |  |  |  |  |  |  |  |  | Not started, need stable injection
Find refuting tests for working hypothesis |  |  |  |  |  |  |  |  |  |  |  |  | Done
Space Charge & Intrabeam scattering - experiment |  |  |  |  |  |  |  |  |  |  |  |  | Not started, need nominal intensity
Space Charge & Intrabeam scattering - simulations |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing
Desorption effects |  |  |  |  |  |  |  |  |  |  |  |  | 
Impedance model |  |  |  |  |  |  |  |  |  |  |  |  | Postponed next year, no fellow found
Transverse Damper - optics |  |  |  |  |  |  |  |  |  |  |  |  | Done
Transverse Damper - system |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing, found doubts for transient during bunching
Magnetic model |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing
Instabilities - experiment |  |  |  |  |  |  |  |  |  |  |  |  | Not started, need nominal intensity
RF during capture |  |  |  |  |  |  |  |  |  |  |  |  | Ongoing, started during setting up
electron cooling |  |  |  |  |  |  |  |  |  |  |  |  | Doubling the current tested, now cooling rate
100 ms operation |  |  |  |  |  |  |  |  |  |  |  |  | Next year as planned
Transverse emittance blow-up |  |  |  |  |  |  |  |  |  |  |  |  | Christian will start working on that soon
Some precision studies LIU-specific delayed due to recent limited machine performance Limited resources re-centered on recovering injection efficiency
(see Django’s talk)

## Slide 17: 2016 Ion Schedule driven by LIU studies
Draft 2016

## Slide 18: PS
- No limits identified so far for PS
- RF gymnastics are similar to the one of protons and already implemented in the past
- 100 ns beam already produced in the PS this year (See Django’s talk)

## Slide 19: Limitation of SPS long injection flat bottom
ATLAS data
Initial Luminosity
SPS
LHC
Two effects observed on luminosity:
Slope imprinted by SPS injection plateau.
Slope imprinted by LHC injection plateau.
From M. Schaumann

## Slide 20: Discussion on IBS-TSK
Observation from last run not conclusive on source of losses @ SPS injection.
Losses along the batch seems to be more caused by IBS or Touschek-like effect mixed with direct space-charge and RF-noise (most recent studies in 2012-13)
Consequence for 2015 studies (see Elena’s talk also):
  Needs more data that can be taken, at least initially, parasitically on operational beam, with 100 ns to be compared with 200 ns bunch spacing
  Interesting to measure with different bunch-length from PS (by adjusting final rotation with more 80 MHz cavities) and/or intensities
  Profiting from:
    Q20 (but eventually we could propose to study a Q19 or a Q18)
    Improved RF noise from Ar run
Test with double harmonics injection in the SPS to inject in larger buckets

## Slide 21: SPS Slip stacking
RF confirmed that slip stacking in the SPS should work, with only final efficiency/beam parameters to better determined by further simulations
- No first principle identified by which scheme should not perform
Lack of manpower being identified within the RF group
  Resources will be available starting early 2016 for:
    start developing of LLRF HW for slip-stacking
      First conceptual design included in the TDR
      Investigate also what can be done before LS2 with a single beam control instead of the two proposed for final LLRF
    assess expected performances of slip stacking via simulations
    study final bunch rotation needed with Q20 to match LHC longitudinal acceptance

## Slide 22: Slip stacking tests in 2015
Tests can be done before only with one batch (flat top, flat bottom) to:
Investigate the beam life time without the phase loop (PL)
  unpredicted behavior of the PL during the slip stacking procedure
  might be necessary to operate without PL
Define the aperture limitation ΔR
Test and optimize the designed RF programs regarding the particle losses and the final longitudinal emittance
(see Elena’s talk)

## Slide 23: 100 ns SPS kicker
First feasible option to bridge the gap with HL-LHC request is implementing the 100 ns kicker injection in SPS to increase number of bunches.
Technically feasible for first YETS after LS2, preliminary design in TDR
- decision has to be taken end of this year/beg. next year
- Main show stoppers to be probed:
- resources limited in ABT (not included in planning) and possibly in EN/STI
- Technical feasibility of the 100 ns (reason for present proto-typing)
- budget of ~ 3 MCHF not in LIU anymore, part of the budget cut, more precise budget to be assessed

## Slide 24: Risk if LEIR intensity not improving
So far, no clear understanding of losses
- Ar run showed losses at capture as for Pb
In parallel, trying to improve the loss decay in the SPS due to long waiting time at low energy
- with Linac3 at injecting at 100 ms and an improvement of the Linac current we could hope to shorten the LEIR cycle to 2.4 s (as in LHC Design Report).
 Shorter flat bottom at SPS injection  less batch degradation
First feasible option to bridge the gap with HL-LHC is clearly implementing the 100 ns kicker injection in SPS.
If LEIR problem is solved then (ultra-stretched scenario):
- profit from full intensity from the Linac and shorter cycles
- full intensity from LEIR
- Improved IBS-TSK limit and/or short SPS cycle
- 100 ns injection in SPS
Reachable parameters not evaluated yet, goal for 2016, to reduce even further gap with HL-LHC requests

## Slide 25: Other brainstorming ideas (from 2010)
Disclaimer: proposed as study case in 2010 but no resources available to proceed with them
Limitations (likely):
  In LEIR: for intensity per batch (some efforts to “see” nominal intensities ejected due to direct space charge forces?)
  In the SPS: for intensity per bunch (direct space charge?), duration of accumulation plateau (ions diffusing out of bucket?)
Additional Linac3 RF tanks (to increase the Energy):
  Additional tanks after stripper
    Mitigation of space charge effects in LEIR for more bunches/PS cycle
    Upgrades of LEIR injection line, possibly increase of LEIR to PS transfer energy
  Stripper after additional tanks (increases charge state):
    Mitigation of intensity limitations in LEIR and SPS
    Still upgrades of LEIR injection line …
  Cost, resources and time line not really compatible with upgrade program
Lower frequency RF system in SPS (in addition to 200 MHz) to mitigate SPS intensity limitations
  For longer bunches at PS to SPS transfer
  To revive the bunchlet scheme and recombine bunches
  Already discarded for protons

## Slide 26: Conclusions
So far not possible to bridge the gap between the HL-LHC request and LIU-ION goals in terms of beam parameters.
Coherent planning of studies in L3, LEIR and SPS proposed
Difficult so far to reach critical mass for resources available. Same resources on machine operation and machine study for LEIR. Improving in 2016 for SPS, less clear for LEIR.
LEIR study requires running machine with Pb, since machine model not sufficiently precise in many aspects
  Impedance model  2016
  Optics/Space-charge simulations available but to be improved
All schemes are based on the improvement of LEIR extracted intensity
Studying improvement of the lifetime in the SPS and/or shorter cycles in LEIR to reduce spread along the batch.
This latter will be a plus anyhow in case of LEIR baseline parameters will be reached.
Clearly important to improve current from the Linac3

## Slide 28: Backup slides

## Slide 29: Planning for studies and HW implementations
 | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  | 
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
LHC operation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Ion operation with Pb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Ion operation with other ions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Linac3 studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Linac3 implementations (LEBT changes, 100 ms) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
More intensity from Linac |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Linac3 tests 100 ms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LEIR studies with Pb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
e-cooler tests with Pb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Decision on ecooler |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SPS test on 100 ns PFL//PFN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SPS feasibility test with slip stacking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SPS slip stacking (after LS2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBS studies - emittance evolution vs intensity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 30: Linac3 low energy modifications

## Slide 31: What intensity did LEIR extract in 2013?
Xmas
Tech stop
Pb54+/bunch
Goal (4.5E8/bunch)

## Slide 32: Findings
Clues from measurements:
  Working point on 4th order resonance
  Transverse instability at RF capture
  Positive chromaticity in the vertical plane (2013)
  Beam loss associated to RF-capture rather than mag. Ramp
  Negative chromaticity in both planes (Ar, 2015)
BHN current [100A]
4.
2.
3.
1.
5.
2013
Ar 2015

## Slide 33
Electron cooler
Injection
Extraction
βx
βy
D
μy
μx
Bend
Bend
Bend
Bend
Pb54+ MADX-PTC simulations with operational parameters

## Slide 34: Resonance lines diagram of LEIR
Qx - Qy = -1
2Qx - Qy = 1
4Qy = 11
Qx + 3Qy = 10
3Qy = 8
2Qx + 2Qy = 9

## Slide 35
2013:

## Slide 36: e-Cooler: Electron beam from 200mA to 335mA (with Ar)
Time
Momentum
200mA
Injection
Cooled and dragged beam

## Slide 37: e-Cooler: Electron beam from 200mA to 335mA (with Ar)
Time
Momentum
335mA
Cooled and dragged beam

## Slide 38: SPS-slip stacking: news from the past (PS)
From Philippe