## Slide 1: NA & EA CONS meeting #7
31.08.2015

## Slide 2: Agenda
News
Report from various meetings
Strategy and plan for the next 5 years (proposal)
APT spending profile (proposal)
Next EA and NA CONS meetings
Next steps

## Slide 3: News: MTP change
Experimental areas consolidation comprises all activities needed to maintain the North Area, the East Hall and the AD facility. Due to the focus on the LHC injectors upgrade and accelerator consolidation and manpower shortage, 50- 60% of the materials allocation is re-profiled until after LS2, for example for the consolidation North Area power convertors. The allocation for the MTP period is limited to an absolute minimum and will only allow some urgent consolidation items.
The consolidation headings benefit from the flexibility to move some activity- related materials to personnel to cover some of the consolidation projects. Overall, the available manpower situation is difficult to ensure execution of the needed work packages to ensure reliable and safe operation.

## Slide 4: News: Target numbers re-profiling
Chart: NA & EA Consolidation budget reprofiling
| 2015.0 | 2016.0 | 2017.0 | 2018.0 | 2019.0 | 2020.0 | 2021.0 | 2022.0 | 2023.0 | 2024.0 | 2025.0
EA CONS | 902 | 505 | 1011 | 2021 | 1516 | 1011
NA CONS | 2802 | 9509 | 8571 | 10415 | 8394 | 8394 | 1218
EA CONS new | 598 | 634 | 511 | 1021 | 766 | 611 | 745 | 1000 | 750 | 400
NA CONS new | 2590 | 3546 | 2628 | 3872 | 2751 | 2751 | 6584 | 5943 | 6543 | 5643 | 5643
Mar-15 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Grand Total
EA CONS | 902 | 505 | 1,011 | 2,021 | 1,516 | 1,011 |  |  |  |  |  | 6,966
NA CONS | 2,802 | 9,509 | 8,571 | 10,415 | 8,394 | 8,394 | 1,218 |  |  |  |  | 49,303
Aug-15 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Grand Total
EA CONS new | 598 | 634 | 511 | 1,021 | 766 | 611 | 745 | 1,000 | 750 | 400 |  | 7,036
NA CONS new | 2,590 | 3,546 | 2,628 | 3,872 | 2,751 | 2,751 | 6,584 | 5,943 | 6,543 | 5,643 | 5,643 | 48,494
2014 MTP: 55 MCHF
2015 MTP: 22MCHF

## Slide 5: News
In August, meetings with:
  J-P Burnet (TE-EPC)
  D. Tommasini (TE-MSC)
  J. Devine (EN-EL)
  M. Nonis (EN-CV)
  M. Benedikt
  R. Saban

## Slide 6: Report from various meetings: TE-EPC&TE-MSC
The overall budget envelope needed to conduct the EA consolidation is 20 MCHF. Half of this budget is required to apply a new technology: pulsing the magnets, which would reduce the annual power consumption of the East Area from 11 to 0.6 GWh. The 2 main stakeholders are TE-EPC (50 new power converters) and TE-MSC (magnet with new laminated yokes).
There are many arguments to go-ahead:
  The safety, access and RP situation is such that the old layout is no longer possible to operate.
  The rectifiers are 50-60 years old! No chance to continue beyond LS2.
  The renovation of converters for TT2 represents a synergy regarding the technology- much engineering is “used twice”.
  It is in the line of optimizing/standardizing equipment.
  The energy saving has a positive impact on the energy budget.
  The lower power has a positive impact on the up-stream electrical power supply and cooling.
  Pakistan may contribute to the magnet refurbishment.
  Resources are available in TE-EPC and TE-MSC to conduct this consolidation during the period 2016-2020.
The deadline to decide to go/no go is set at the end of 2015.

## Slide 7: Report from various meetings: EN-EL
Extension EHN1/NA-CONS:
James and Guillaume Gros has made a cost estimate for the electric infrastructure for the EHN1 extension and the consolidation of the electric distribution of the EHN1. The two projects are technically linked as the old infrastructure is too obsolete for such new power needs to be connected. It’s therefore difficult to handle the two project independently; however financially the EHN1 extension project will only be able to carry the expenses strictly linked to the needs in the extension (CENF-project).
The cost estimate is therefore made complete, but with the possibility to distinguish if an item is mainly related to:
- Purely extension
- Purely consolidation
- General distribution, from sub-station to a distribution in the hall.
For the first two headlines (extension and consolidation) it’s rather clear which budget should bear the expenses. For the general distribution, we need to make an arbitration on a percentage how much should be attributed to extension and how much to be on consolidation.
In the WG-paper for the infrastructure budget request for the EHN1 extension, my suggestion is to use a factor 20% (extension) and 80% (consolidation) for the general expenses for power distribution.
For cable trays, they have made a separate cost estimate (cable containment)
We did not discuss the electric cabling or infrastructure for the East area, yet. There is an EA-CONS meeting next week when, and an EL-planning meeting the 16th September we could further discuss these issues.

## Slide 8: Report from various meetings: EN-CV
YETS 2015-2016:
  Ventilation units in the NA PC rooms (BA81) 95 kCHF
  Chilled water (BA82)  170 kCHF
  Chilled water coils in AHU’s (BA82)  100 kCHF ?
2016-2017-EYETS:
  Chilled water circuits in TT84, TT81 and TT82 (2016 + EYETS 2017) 325 + 300 KCHF
  Ventilation units in the NA PC rooms (BA82) EYETS 2017150 kCHF
  AHU consolidation in NA surface buildings & BA80, 81 and 82 220 kCHF
YETS 2018
  Cooling towers 100 kCHF

## Slide 9: Strategy and plan for the next 5 years (proposal)
Launch the EA-consolidation (and up-grade) during the period 2016-2020 i.e. before- and during LS2. This involves some budget re-profiling. It is an opportunity to revamp an area which otherwise is deemed to close down.
As the consolidation of North Area is not possible during this period, focus on urgent consolidation items only and launch the main NA-consolidation after LS2.
Challenge the budget currently allocated (7 and 48.5 MCHF) and request 20 MCHF for EA and 60 MCHF for NA via a BCR.
This would not change the MTP (2016-2020) where more than 22 MCHF are already funded. Transparent for current management.

## Slide 10: Update of APT
18 Sep as deadline for the up-date of APT
EN-CV will update its requests

## Slide 11: APT proposal for EA
Activity | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Magnets mainenance |  |  | 150 |  |  |  | 
Change magnets to laminated |  | 530 | 1000 |  |  |  | 
Rectifier upgrade original estimate | 1000 | 1000 | 800 |  |  |  | 
Rectifiers extra for energy recovery | 2000 | 2000 | 1770 |  |  |  | 
Collimators |  | 75 |  |  |  |  | 
Collimators remote control |  |  | 80 |  |  |  | 
Layout change of beam lines |  |  | 1555 |  |  |  | 
Shielding modifications |  |  | 100 |  |  |  | 
Electrical infrastructire AC |  |  | 1650 |  |  |  | 
Electrical infrastructure DC |  |  |  | 130 |  |  | 
Ventilation system in primary zone |  |  | 400 |  |  |  | 
Replacement PVC cables |  |  | 1500 |  |  |  | 
Magnet cooling |  |  | 950 | 400 |  |  | 
Controls upgrade |  |  |  | 70 |  |  | 
Beam loss monitors |  |  |  | 20 |  |  | 
Beam stoppers |  |  |  | 500 |  |  | 
Control rooms |  |  |  | 300 |  |  | 
Air conditioning building |  |  |  |  | 985 |  | 
Civil engineering |  |  |  |  |  | 500 | 1000
Asbestos removal |  |  | 120 |  |  |  | 
Various items |  |  | 200 |  |  |  | 
Savings on EL and CV infrastructure |  | ? | ? | ? |  |  | 
Total | 3000 | 3605 | 10275 | 1420 | 985 | 500 | 1000
 |  | TOTAL MTP 2016-2020: |  | 18300 |  |  | 

## Slide 12: Next steps
EA CONS meeting on September 3rd @ 9.00.
NA CONS meeting next week.