## Slide 1
03 September 2015
1
EHN1 civil engineering project status (AUGUST)
Summary:
Updating of the activities carried out on-site (Done) in AUGUST
List activities on going (Next steps) and scheduled for SEPTEMBER
Final consideration
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi

## Slide 2
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi
(1) DIAPHRAGM WALLS
-73 panels-
Execution EAST side: (100% completed)
Execution SOUTH/WEST side: (100% completed)
Done (1/3):
Guide walls allowing DW excavation: (100% completed)
Execution NORTH/WEST side: (100% completed)
100% TOTAL PANELS
EAST
N/W
S/W
EHN1 civil engineering project status (AUGUST)
03 September 2015
2
Problem for execution of panels close to EHN1 has generated ~4 weeks of delay to complete the task
and..
Construction defects discovered in other panels already casted came out during excavation to set up the crown beam
lead to..
About 4 weeks of delay on the overall planning as connected activities have been blocked
TASK COMPLETED in AUGUST

## Slide 3
Done (2/3):
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi
(2) TECHNICAL GALLERY
-70 meters-
Earthworks: (100% completed).
Execution TG: (85% completed). Type 3 done. Type 1 to be completed
Backfilling: (25% completed).
EHN1 civil engineering project status (AUGUST)
03 September 2015
3
Side retaining wall and backfilling foreseen later as not in the critical path. Priority given to other activities

## Slide 4
Done (3/3):
(3) PITS EXECUTION
Crown beam execution: (22% completed). Start with E side.
Excavation first ties level: (22% completed).
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi
Excavation head DW level: (100% completed). After excavation pit A..
Excavation second ties level: (0% completed). Only for certain DW panels
…Others
First ties level execution: (13% completed). Not yet in tension
-step by step-
EHN1 civil engineering project status (AUGUST)
03 September 2015
4

## Slide 5
Next Steps: Activities scheduled for September
(2) TG: Upper slab and retaining wall to be executed in the 2nd half of September
(3) PITS: Has at the moment the High Priority.
80% Crown beam executed 1st half of September. Completion foreseen in the 2nd half..
Excavation inside pits and execution whole 1st order of anchors within the 2nd half of September
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi
31/08/2015 =>
EHN1 civil engineering project status (AUGUST)
03 September 2015
5

## Slide 6
Final Consideration:
- The completion of the DW complex had ~4 weeks of delay on the planning.
Defects reparation and DW completion led to the inability to advance with the parallel activities foreseen. Overall delay estimated in about 4 weeks.
CE Contractor will evaluate all the possibility to retrieve or minimize time lost (i.e. work during the weekend, add different workshop and internal resources, overlap several activities with metallic contractor).
Planning will be reviewed given the priority to the execution of the pits (critical path).
CE Handover unchanged for the moment (Jul-2016).
Next status of the works end-September.
Extension of Building 887 - Neutrino Platform General Meetings
N.Lopez – M.Manfredi
EHN1 civil engineering project status (AUGUST)
03 September 2015
6