| # Progress Report |  |
| --- | --- |

# PH Safety Office - Présents: Olga, Niels, Catherine, Alex, Isabelle, Maurici

September 1, 2015

| ## Status Code Legend |  |
| --- | --- |
| On Track: Project is on schedule | - High Risk: At risk, with a high risk of going off track |
| - At Risk: Milestones missed but date intact | - Off Track: Date will be missed if action not taken |
| Achieved |  |

| Theme | - Action / Follow-up | - Responsible | - Deadline |
| --- | --- | --- | --- |
| Evacuation build 5, 4 | Following parking modification, a meeting with FB (A. Cuenca) and HSE is schedulle 17.09 to define the new assembly point in case of evacuation | Maurici | - 17.09 |
| Small Experiments Safety Clearance | Assessment of the Ipad SW issue Proposal of a optimized procedure for Small Exp. Clearance. Discussion planned done with Henric. Common action Henric/ Olga at very early level to request ISIEC form and close follow up of status of documentation with the Small experiments. Change ISIEC format to adapt to the new safety policy - ISIEC sent to the team for comment, Waiting to meet Angela for feedback EDMS folders are created. Collect and insert all past safety clerances - Ongoing. | Alex/ Olga Olga Olga Alex / Bruno | - 08.09 - 15.10 - 08.09 - 22.09 |
| Experiments Safety Clearance | - NA61 assessment done - Magnetic field disclaimer, provide clearance to run if all - Request assessment of the exhaust line - Extinguisher a poudre | Olga - Olga + Thomas | - 09.09 - 21.09 |
| Safety files | WA104, WA105, NA62 and NA61 structure for Safety files is created. - NA61 EXSO (Antoni) has been contacted and we are waiting a feedback on available documentation. Some documents have been transferred . Import existing files from WA104 and WA105 with assistance of EXSO Restart discussion with Valeri (NA62) for the SF content as rthe provided list is not applicable to the structure After discussion with PH-DT (Andrea), propose a revised version of PH-DT SF structure for PH-DT buildings Write an addendum to the main SF management document (already signed by the departement leaders) to include PH and propose to Livio for signature - (first meeting with Benoit 08.09). Request EDMS support (Rachel) to mirror the PH SF structure at higher EDMS level like all other departments | Alex Olga/Alex Isabelle Olga with Benoit Alex / Olga | - 15.09 - 15.09 - 08.09 - 15.10 - 08.09 |
| Fire Safety | Present the list of the 20 most critical build. For fire safety at next PH-SO meeting and a status of the actions : contact with TSOs, list of actions, etc.. - Provide list of emergency guides for each PH buildings ( to be put on EDMs and web pages) , check that they have been trained, if not organise a training program with FB | Maurici - Maurici | - 08.09 - 22.09 |
| Safety inspections | Present a proposal of use of Sailor / web pages/ SOS/…. to have in real time immediate vision of safety inspection and building status. | Isabelle /Alex | - 22.09 |
| Chemical Hazards | Update Polichem document with PH data . | Isabelle | - 08.09 |
| TSO Support and Follow Up | Proposer 3 groupes de 20 TSOs à supporter respectivement par Niels, Maurici et Isabelle | Isabelle | - 08.09 |
| Workshop Safety | Final control of the WS GSI Contact Angela to discuss the WS GSI document | Isabelle/ Olga Isabelle /Olga | - Done - 08.09 |
| New safety policy | Contact Angela to understand the status of discussion with big experiments and restart process | Olga | - 15.09 |
| EDMS /Web Administration | - It has been agreed with Valerie and Nathalie to put all all EXSO / TSO nomination letters on EDMS folder (restricted) Collect and insert all documents in EDMS Book meeting room for all year and create Indico meetings associated PH Web pages assessment and creation Current Web page status (ask Angela) | Claire/ Antonella Claire/ Antonella All Isabelle | - TBD - 15.09 - End of year - 08.09 |
| Training | Assess the existing web EXSO training Report on status of Risk Awarness in workshops for users Mise en place d’un cours sur utilisation applications informatiques traitant de sécurité EDMS/Service NOW/MTF/SAILOR/IMPACT pour TSOs. Refresh du cours TSO à suivre avec Christoph Balle/HSE . Create the list of PH trainers (working at height, mask,…) Contact FB to agree on their implication for the extinguisher training | - All - Isabelle - Isabelle - Isabelle - Olga / Niels - Olga | - 15.09 - 08.09 - TBD - TBD - 15.09 - 15.09 |
| General | - Create a list of Experiments and buildings safety visits with Safety coordinators,TSO , EXSO and DSO, contact safety coordinators. Discuss with HSE the safety inspections , request HSE to remove the non PH buildings from the list, reassess the risk ranking for PH buildings, improve follow up Make a list of the PH EPI Find a secure building to store the PH EPI, create a list of EPI Check with all PH TSO if their buidlings have alarm system and if people are sleeping inside Lead blocks : plan of action | Olga Olga / Niels Niels/ Isabelle Isabelle Isabelle Niels | - 22.09 - 15.10 - Done - 22.09 - 22.09 - 22.09 |