## Slide 1: NA & EA CONS meeting #8
12.10.2015

## Slide 2: Agenda
News
EN-EL breakdown for EHN1 extension
Meetings
EA CONS Budget
Next steps

## Slide 3: News
EA CONS meeting held on September 3rd
  https://indico.cern.ch/event/441413/
NA CONS meeting held on September 24th
  https://indico.cern.ch/event/446241/
Presentation @ LS2 days well received
  https://indico.cern.ch/event/436424/session/3/contribution/36/attachments/1161435/1672338/CERN_LS2Days_SEV.pptx
Several face to face discussions

## Slide 4: EN-EL breakdown for EHN1 extension
EHN1 Extension | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Annual | 0.00 | 1869121.76 | 527434.96 | 0.00 | 0.00 | 0.00 | 0.00
With 15% contingency | 0.00 | 2049490.02 | 606550.21 |  |  |  | 
Cumulative | 0.00 | 2049490.02 | 2656040.23 |  |  |  | 
NA Cons | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Annual |  | 0.00 | 0.00 | 222,233.00 | 193,771.28 | 45,520.00 | 29,901.31
With 15% contingency |  | 0.00 | 0.00 | 255,567.95 | 222,836.97 | 52,348.00 | 34,386.51
Remaining | 100,000.00 |  |  |  |  |  | 
Cumulative | 240,000.00 | 240,000.00 | 240,000.00 | 495,567.95 | 718,404.92 | 770,752.92 | 805,139.43

## Slide 5: Meetings/EDMS approval
Interlock for EA
Gas building consolidation for NA
Safety systems in the general infrastructure SBA https://edms.cern.ch/document/1365914/0.5
ECR_NA_Galeries
  https://edms.cern.ch/document/1549763/2

## Slide 6: EA CONS Budget
Minimize EA CONS budget by:
  Taking Energy savings into account 2021-2025 (RUN3)  2MCHF
  Using other budgets (PVC cable replacement)
  Prioritizing activities

## Slide 7: EA CONS Budget
Activity | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Magnets mainenance |  |  | 150 |  |  |  | 
Change magnets to laminated |  | 530 | 1000 |  |  |  | 
Rectifier upgrade original estimate | 1000 | 1000 | 800 |  |  |  | 
Rectifiers extra for energy recovery | 2000 | 2000 | 1770 |  |  |  | 
Collimators |  | 75 |  |  |  |  | 
Collimators remote control |  |  | 80 |  |  |  | 
Layout change of beam lines |  |  | 1555 |  |  |  | 
Shielding modifications |  |  | 100 |  |  |  | 
Electrical infrastructire AC |  |  | 1650 |  |  |  | 
Electrical infrastructure DC |  |  |  | 130 |  |  | 
Ventilation system in primary zone |  |  | 400 |  |  |  | 
Replacement PVC cables |  |  | 1500 |  |  |  | 
Magnet cooling |  |  | 950 | 400 |  |  | 
Controls upgrade |  |  |  | 70 |  |  | 
Beam loss monitors |  |  |  | 20 |  |  | 
Beam stoppers |  |  |  | 500 |  |  | 
Control rooms |  |  |  | 300 |  |  | 
Air conditioning building |  |  |  |  | 985 |  | 
Civil engineering |  |  |  |  |  | 500 | 1000
Asbestos removal |  |  | 120 |  |  |  | 
Various items |  |  | 200 |  |  |  | 
Savings on EL and CV infrastructure |  |  |  |  | - 666 | - 667 | -667
Total | 3000 | 3605 | 8775 | 1420 | 319 | -167 | 333
 |  | TOTAL 2016-2023: |  | 14800 |  |  | 
Budget Change Request must explain these changes

## Slide 8: Next steps
Get estimate from EN-EL and EN-CV for EA CONS (LAU)
Define cost breakdown for EN-EL (EHN1 extension versus consolidation ) (MATS) and what for EN-CV ?
Complete BCR (SEB)