## Slide 1: Controls Renovation for AB-BI
Outline:
Reminder of AB-BI-SW mandate
History of controls renovation
Renovation work-packages (-> 2012)
  Projects known at this stage
  Few small-scale projects may come later
Human resources
Conclusions
Acknowledgements:
AB-BI colleagues for their input

## Slide 2
AB-BI-SW Mandate: Software Responsibility Chart
Logging
GUIs
Fixed
Displays
BI Expert
GUIs
Alarms
BPM
BLM
Concentrators
DB
Settings &
Logging
Post
Mortem
AB-BI
Front-End SW
Business Layer
CMW
Cycle Mgnt
Front End
We DO these
green parts
(but only those)
Sharing of front-end systems
Courtesy: J. J. Gras Controls review 2005
Good experience with direct contact SW<->HW inside AB-BI

## Slide 3: Controls renovation by AB-BI
Our motivations have always been:
A) Operational reliability:
  Standardisation & modernisation
    Hardware & low-level software
    “ISOLDE” example:
      Windows NT, Visual Basic with nobody …
  Common knowledge
    Fewer need to be available (24/7)
B) Optimise use of resources:
  Maintaining outdated systems is painful and sometimes not possible
  (old HW components, source code)
Comments on history/experience
  See next (few) slides

## Slide 4: History of AB complex Controls Renovation
Started in 2003 (when PS+SL -> AB)
  Realised the large variety of “standards”
Project started large-scale in 2005 (PS, AD & SPS = ‘OFF’)
  MTV renovation AB-0801 funds ->2007
  LINAC2 + PSB (existing clients)
  LINAC3 and LEIR (LSA)
  Collaborators (K-contract) very useful
    (Missing staff) paid by AB-0801 funds ->2010
FESA2 verification with beam during 2005 meant, we could continue with:
    SPS (LSA)
    EA (CESAR) AB-0801 funds ->2009
    CPS + ISOLDE ..
Plans, progress and issues discussed during OP-days/ABOC/APC
Problems encountered discussed ->

## Slide 5
Client Compatibility
Appl. layer
Comm. layer
GM-Java
GM-RPC
JAPC client
GM-
CMW
GM-
RPC
FESA-
CMW
Device layer on front-end
‘AB-BI’ FESA devices
Courtesy: M. Ludwig
GM devices
GM2FESA (AB-CO)
adaption layer
A few points worth mentioning:
Without GM2FESA, we could not have SW renovated anything for
LINAC2, PSB and CPS:
Implications (reliability/maintenance):
GM and FESA devices mixed, difficult to debug/maintain
FEC CPU & RAM limitations (FEC splitting)
Hope to remove these extra layers before long (InCA talk)
(Hopefully, interfacing to InCA will not be time-consuming)
CO3 committee was created in 2006 (A. Butterworth):
- Essential for PS complex renovation as it gave us names of people
responsible in OP and ABP
Some new (Java) applications were developed:
- Needed debugging to reach acceptable system performance
(sometimes SW problems in the front-ends were suspected)

## Slide 6: Work-packages #1 “Well advanced systems”
1) Tune meter renovation
  Near-identical HW+SW for
    LHC, SPS, CPS, PSB, LEIR
    Funded with AB-BI exploitation budget
  (Old PSB and CPS hardware broken, SPS in worrying state)
2) Fast wire-scanner electronics
  Near-identical HW+SW for LHC, CPS, PSB
  AB-0801 funds (WU: 32753)
  Positive response from OP/ABP
  Effort to continue in 2009
3) PS orbit system renovation
  Dedicated hardware, not yet fully commissioned with beam
  EU + AB-0801 funds (WU: 19743)
  Effort to continue in 2009
  Intend to eradicate “CODD” by 2010
Have handled these projects as collaborations:
Frequent contacts with OP, ABP, ATB & CO colleagues:
  Requirements
  Applications (new/old)
  See OP talk

## Slide 7: Work-packages (#2) LynxOS->Linux #1
Problem:
VME front-end CPU module (8062) becoming obsolete (Nicolas’ talk)
Operational issues:
  10 years old (spare/repair)
  Memory upgrade not possible
  No compatible modules
Numbers (not LHC, dev. systems):
  ~150 AB-BI VME systems
    100 old type CPUs
    (majority: SPS + SPS-EA)

## Slide 8: LynxOS -> Linux #2
New CPU platform (Intel, Linux):
We take for granted that our existing FESA classes will work
as now (tests are needed to make sure) ..
AB-CO Linux support for these modules (Javier’s talk, WP7):
  MPV908, ICV196, VMOD TTL, ADC, DAC ..
  PS-TG8, CTRx, VIP626 + IP8R422
  SIS33xxx
    A lot of time spent getting these to work
    AB-CO test-bench should help
Port device drivers for BI hardware
A) Drivers developed with AB-CO tool (~20 so far)
  Believed to be straightforward (initial problems)
B) Older device drivers (SL standard, ~20 in use)
  Collaboration initiated with GSI:
    Port driver to Linux (Q2 2009) for tune system
We will need:
  Support/documentation from AB-CO
  Organise thorough testing to avoid bad surprises on the beam (new CPU, Linux, InCA etc)

## Slide 9: LynxOS -> Linux #3
Except for a few cases, our FESA (2.10)
classes are working fine on old CPUs
  Issues with OP (samplers) and
  ATB (EA motors) to be discussed
  (=> splitting of front-ends)
Worried about effort needed to
port software from LynxOS to Linux:
Systems already with FESA SW and with HW renovation is planned within 2-3 years, will most likely not be ported to Linux and will stay as is also in 2010
(List of systems to be produced)

## Slide 10: AB-BI work-packages #3 “Software renovations”
PS complex:
SEM grid renovation (GM->FESA):
  AB-OP initiative  linked to PSB FWS tests
  Existing FESA class
  Systems agreed:
    PSB measurement line (fixed grids)
    CPS injection line (PLC solution)
    ISOLDE (fixed grids)
    TT2 grids, decision AB-OP to come
  AB-BI Exploitation budget
BCT system renovation:
  Presented at APC meeting during 2007
  Systems concerned:
    Parallel tests 2009 on a few transformers PS complex
    Put into operation by 2010
      Watchdog issues being looked at
  AB-0801 funds (WU: 19743)
PSB ejection BPM system:
  Change BPM type to avoid noise issues
  Upgrade acquisition module (Struck->SIS33xx)
  Put into operation by 2010
  AB-0801 funds (WU: 19743)

## Slide 11: System renovations #1
SPS Orbit system renovation
  Project to start during 2009 and run over 3 years
  6 VME systems to come
  AB-0801 fund (WU: 32273)
TT2/TT10 BPM system renovation
  Project started in 2008
    Requirements/resources study launched
    Hope to cover all beams through TT2 by 2010
  2 VME systems to come
  AB-0801 funds (WU: 32269)
SPS Wire-scanner electronics renovation
  Expected to start 2010
  3 VME systems to come
  AB-0801 funds (WU: 32753)
SPS BTV renovation (analogue video -> CCR)
  Cost figures before end of 2008
  Aim to have all renovated by 2010
  Probably 4 new VME systems involved
  Funding to be found
EA MWPC renovation
  7 new VME systems for coming start-up (SPS)
  1 new VME system for 2010 start-up (CPS)
  AB-0801 funds (WU: 30847)

## Slide 12: System renovations #2
AD machine renovation
General strategy will depend on AD proposal
  Resources P+M to be looked at
Renovation of Schottky system
  Requirement study started
REX-ISOLDE renovation
  Working on-going for “control-boxes”
  Implementation details being discussed
REX-TRAP renovation
  Foreseen for 2010 start-up
AB-BI movement renovation
  SPS stepping-motor systems advanced
  SPS IN-OUT (G64, SL-Equip)
    Could renovate by 2010 (funds to look at)
  PS complex
    Responsibility agreement with ATB needed
    Then decide for AB-BI systems
BLM renovation (CPS, PSB)
  Received the system requirements
  Prototyping to start during 2010
  2 VME systems
  AB-0801 funds
  SPS not yet funded (presently 11*VME)

## Slide 13: Human resources (->2012)
With present number of staff members (7)
+ Russian (1+1), we believe that the here
presented renovation projects can and
should be done
On condition that:
  FESA FW and dev. tools optimised
    New releases to undergo realistic tests on supported platforms
  FESA support remains high quality
    Communicate known issues to users
  Maintaining classes = low effort:
    Frame-work version changes
    AB-BI has ~50 classes (non-LHC)
Also important:
InCA requirements to be clarified
Replacement of CPU modules:
  Must start ASAP to gain experience

## Slide 14: Conclusions
AB-BI are well advanced in terms of controls renovation
  Gained lots of experience
  Complex in much better state
Close collaboration with users (OP/ABP/ATB/CO) needed for:
  Requirements
  Implementation details
We will continue along these lines for the future renovation projects