## Slide 1: Change requests
#20, #60, #90 - Impact: 6 to 9 months delay on platforms and test area, 210 kCHF
(61 kCHF additional integration work+9 kCHF cryolines+5 kCHF floor preparation+135 kCHF control room and add space)
#50, #70 - Remaining change requests from GSI with insufficient information for analysis
#30, #40, #80 - CERN internal change requests with no impact on GSI reqts