## Slide 1: Project Breakdown Structure Tracing changes to our different baselines
I. Bejar Alonso and Project Office
TCC – 14th January 2016

## Slide 2: The Project Baselines
A Baseline is a set of attributes at a point in time.
It serves as a basis for defining change.
HL –LHC maintains Scope, Schedule and Cost Baselines.
Our PBS is our present Scope Baseline
Our MS Planning is our present Schedule Baseline
Our MTP is our present Cost Baseline
The three together are our Configuration Baseline

## Slide 3: PBS
The HL-LHC PBS v.0 was prepared for the Cost & Schedule review (March 9-11, 2015)
It was based on the Conceptual Specifications break down and on the system architectures. It contains 240 elements
Each node of the PBS is described by 6 numbers
Ex. 4.1.1.1.4.3 is the Helium vessel for the SPS Crab cavity
A new version of the PBS shall be issued before the next cost and schedule review (October 17-19, 2016)
The PBS can be changed after the periodical re baselining or following an Engineering Change request approved by the TCC.
WP | Family/ System | Equipment/ Equipment subtype | Assembly/ Component | Subassembly/ Component | Component
4. WP4 | 1. Crab Cavity | 1. CC for SPS | 1. Cryomodule | 4. Dressed cavity | 3 Helium vessel

## Slide 4: Schedule and cost
Our Master schedule and our cost was prepared for the Cost & Schedule review (March 9-11, 2015)
The structure is based as much as possible on the PBS to allow the implementation of EVM
Before the next cost and schedule review (October 17-19, 2016):
  A new version of both shall be issued
  EVM shall be implemented for the C&S Review
  A detailed costing and scheduling for WP17 shall be implemented
The Baselines can be changed after the periodical re baselining or following an Engineering Change request approved by the TCC.

## Slide 5: Tracing changes / Typology
Changes not affecting the configuration Baseline
The Template for Decisions Reporting will be used to trace decisions for an existing type of component or on components that are evaluated for the Baseline. Typically will be used to formalize a technical decision between several options, an internal re-scheduling not affecting the baseline or a revaluation of the cost, a technical decision to be shared.
They are internally discussed in the WP and brought to the TCC for final validation.
Changes affecting the configuration Baseline
The Template for HL-LHC ECR will be used to trace decisions and actions that will come from changes on components already in the configuration Baseline and that are not in the present LHC machine.
All are discussed in the TCC.
Changes affecting the present LHC
The LHC ECR template will be used to trace changes in the present LHC machine and follows the normal LHC ECR.
All are discussed on the LMC
Pre analysis to help on the decision process
To ensure or at least to help the "objectivity of the decision” exists a template to help to put the pros and cons based on the SWOT analysis

## Slide 6: Tracing change / Procedure
When a change is internal to the WP and not affecting the Baseline the WPL fills the Template for Decisions report that contains the analysis and the reason of the desired decision. The WPL sends the report to the TCC secretariat that adds it to the AOBs of the next TCC where receives the final approval
When a change affects several WPs or the Baseline the requester WPL informs the PO (HI-LUMI-LHC-PO@cern.ch) who will evaluate the request and will provide the WPL the required support documents and fix with the TCC chairman the date for the discussion.
When a change affects the LHC machine an ECR is submitted using the normal LHC ECR circuit
All decisions documents are sent to all WPLs for information and stored in EDMS
All HL-LHC-ECR and LHC-ECR after approval are sent to all members of the project and stored in EDMS

## Slide 7: Tracing change / when tracing and how
It is not considered a change when moving from a concept to a functional or technical specification. This evolution is part of the normal live cycle and will be covered by a new version of the conceptual specification (for example moving from v 1.0 to 1.1) or by a functional or technical specification.
When there is a change in the baseline the HL-LHC ECR will complement the Conceptual or Technical Specification until a new version is issued (for example moving from v 1.1 to 2.0)
Changes in the schedule that do not affect the critical path do not need a HL-ECR or a decision report. When the change is motivated by a delay the Project office together with the WPL will analyse it to understand the cause. The PO will prepare a decision report if considers useful to trace and share the findings.
Changes to the budged are traced by memorandums issued by the Project Budged Officer in all cases
The rebaselining exercises are the moment used to consolidate the changes in the different documents/baselines

## Slide 8: Rebaselining exercise
The cost and schedule rebaselining exercise stated in December and must be finished to allow a correct MTP and the implementation of EVM during the summer
The scope rebaselining will start in February and will allow a revision of the conceptual specifications and the timing for functional and technical specifications for several components and subassemblies
During January a list of HL-LHC ECRs and Decision reports will be prepared with the WP Leaders to consolidate decisions and changes already implemented (described in the TDR) but not yet documented (ex. Change on the design of Q4, number of crab cavities installed during LS3, number of 11T and installation staging, ….)

## Slide 9: A lot of interesting work ahead of us