## Slide 1: EHN1 Extension Activities Schedule
Anne Laure Perrot EN/MEF- LE
Bastien Rae EN/MEF- LE
CERN Neutrino Platform General Meeting
19th November 2015

## Slide 2
Outline
EHN1 extension integration
EHN1 access layout
EHN1 extension activities schedule
preliminary

## Slide 3
EHN1 extension integration
Building as delivered by the civil engineering at the handover
Jura side
Saleve side
Lausanne /
North side
Current North Wall

## Slide 4
EHN1 extension integration
Courtesy V. Clerc, S. Girod
Jura side
Saleve side
Lausanne /
North side
Current North Wall
Courtesy V. Clerc, S. Girod EN/MEF
EHN1 extension

## Slide 5
EHN1 extension integration
Cryogenics
external platform
WA105
detector
ProtoDune
detector
H2 beam line extension
H4 beam line extension
Courtesy V. Clerc, S. Girod EN/MEF

## Slide 6
EHN1 extension – access layout
Courtesy I. Efthymiopoulos, S. Girod EN/MEF
area 182
area 184
area
192
area 174
area 164
area 194
area 194
Current North Wall

## Slide 7
EHN1 extension – areas definition for planning
Jura side
Saleve side
Lausanne side
H2 beam line extension
H4 beam line extension

## Slide 8
EHN1 extension – areas definition for planning
Jura side
Saleve side
PIT A
PIT B
Lausanne side

## Slide 9
Timeline
Courtesy B. Rae EN/MEF
2016
2017
2018
Handover CE
delayed last week by 1 ½ month to Mid August 2016
Handover CE
EYETS
preliminary

## Slide 10
Schedule – Detectors
preliminary
March
2016
May
2017
April
2017
Dec
2017
Nov.
2017
April
2018
No access to the pits
for the other teams
commissioning
Inner detector + cryo test &CD
Cryostat Vessels construction
Courtesy B. Rae EN/MEF

## Slide 11
Schedule – Beam lines
preliminary
H4 beam line
H2 beam line
Eqpt installation
Shielding installation
Commissioning
Handover CE
Mid- August 2016
Material procurement
Dismantling area 182
August
2017
H4 beam dump dismantling
H4 quai & shielding installation
Eqpt installation in 164
Eqpt installation in 174 & 184
October
2016
April
2018
Material procurement
Commissioning
Courtesy B. Rae EN/MEF

## Slide 12
Schedule – Beam lines
preliminary
H4 beam line
H2 beam line
2016
Material procurement
Material procurement
August
2017
October
2016
April
2018
Courtesy B. Rae EN/MEF

## Slide 13
Schedule – Beam lines & Detectors
preliminary
H2 beam line
H4 beam line
detectors
Cryostat
Vessel assembly
Open points:
1. access conditions to the pits during the detectors gas thightness tests & cool down
Remark:
- Installation of clean room for Proto Dune avoids the ealier installation of the H4 quai.
no access to the pits
Current planning: access granted in the pits during the gas thightness tests and the cool down (if not delay of 16 weeks for H4 beam line installation)
Start of H4 quai installation
End of inner detect. inst.
Handover CE
Mid- August 2016
2. co-activity between H2 commissioning & detector installation – to be checked!
H2 commissioning
Courtesy B. Rae EN/MEF

## Slide 14
Schedule – Infrastructures
preliminary
EN/EL
CF section: No activity during EYETS (12 th Dec.2016 – 5th May 2017)
EYETS

## Slide 15
Schedule – Infrastructures
preliminary
Hall heating & ventilation
8 th November 2016 – May 2017
Piping network
Start: end September 2016
GAr extraction system
Start:8 th November 2016
Air pulsing system
Start: 8 th November 2016
EN/CV
Counting barracks air conditionning
Start: 7 th December 2016

## Slide 16
Schedule – Overall planning
preliminary
H2 beam line
H4 beam line
detectors
infrastructure
Hall heating and ventilation
8 th November 2016 – May 2017
End of Inner detector 2
EYETS 2016 - 2017
Handover CE
Mid- August 2016
Start H4 quai installation
EN/EL-CF: no activity during EYETS
12 th Dec.2016 – 5th May 2017
April
2018

## Slide 17
Schedule - summary
preliminary
All activities identified for
H2 & H4 beam lines extension
Infrastructure installation
Detectors installation: all main steps known.
To go ahead in the co-activity / sequences definition:
Important to know:
the installation procedure for cryostats & detectors installation
the cryogenics system integration
the constraints during gaz tightness test and detectors cool down.
Last week first circulation of overall planning