## Slide 1: WP4: microelectronics and interconnections
WP Coordinators: Christophe de la Taille, Valerio Re
Goal : provide chips and interconnections to detectors developed by other WPs
Task 1: Scientific coordination (CNRS-OMEGA, INFN-UNIBG)
Task 2 : 65 nm chips for trackers (CERN)
  Fine pitch, low power, advanced digital processing
Task 3 : SiGe 130nm for calorimeters/gaseous (IN2P3)
  Highly integrated charge and time measurement
Task 4 : interconnections between 65 nm chips and pixel sensors (INFN)
  TSVs in 65 nm CMOS wafers, bonding of 65 nm chips to sensors, exploration of fine pitch bonding processes

## Slide 2: AIDA WP4 milestones
MS4.1 Architectural review of deliverable chips in 65nm run M14 (June 2016)
MS4.2 Final design review of 65nm M30 (October 2017)
MS4.3 Test report of deliverable D4.1 M46 (February 2019)
MS4.4 Selection of SiGe foundry M14
MS4.5 Final design review of deliverable chips in SiGe run M30
MS4.6 Test report of deliverable D4.2 M46
MS4.7 Selection of TSV process M14
MS4.8 Final design review of deliverable D4.3 M30
MS4.9 Test report of deliverable D4.3 M46

## Slide 3
Deliverable chips in 65 nm
This work is carried out in the frame of the CERN RD53 international R&D program developing a first generation of pixel readout chip prototypes for ATLAS and CMS at HL-LHC
Develop expertise on TSMC 65 nm CMOS selected by CERN for HEP
Two small size prototypes will be available for testing with sensors in 2016
A large-scale prototype will be submitted end 2016 /beginning 2017 in an engineering run
This will deliver full wafers for the interconnection with pixel sensors (task 4.4)

## Slide 4: Small-medium size 65 nm CMOS prototypes
Two different chips with a 64x64 50 µm x 50 µm pixel matrix ( about 16 mm2) with different architectures for the analog front-end and the digital readout, different techniques for digital-to-analog isolation,…
FE65_P2 (Bonn, LBNL), submitted end of September 2015
CHIPIX65 demonstrator (INFN): to be submitted April 2016
These prototypes can be bonded to pixel sensors, allowing other WPs to test their devices in 2016

## Slide 5
Small scale prototypes (I)
  FE65_P2 prototype chip (Bonn-LBNL)
  [T. Hemperek et al., TWEPP 2015]
    64x64 matrix, 50x50 µm2 pixel
    Put into effect the following RD53 WG proposals:
    Top level  digital on top hierarchical flow, modular approach (4x64 pixel cores), analog islands
    Architecture  distributed latency buffering architecture (2x2 pixel region optimized for higher hit rates)
    Analog  LBNL front end
    Verification  no VEPIX53; testing oriented verification with custom Python-based framework
    Submitted: 12/2015
    Started testing phase
    chip is functional and characterization is on-going
    in the process of being bump bonded to pixel sensors

## Slide 6
Small scale prototypes (II)
  CHIPIX65 Demonstrator (CHIPIX65 Italian INFN collaboration)
  [CHIPIX Collaboration, RD53 General Meeting (14/10/2015)]
    64x64 matrix, 50x50 µm2 pixel
    Put into effect the following RD53 WG proposals:
    Top level  digital on top hierarchical flow, analog islands
    Analog  integration of 2 different flavours (Torino and Bergamo/Pavia front ends)
    Architecture  centralized latency buffering architecture (optimized) (4x4 pixel region)
    Simulation and verification using VEPIX53 framework
    IP  implementation of a set of tested RD53 IP blocks (bandgap, DAC, serializer…)
    To be submitted: 04/2016 (Europractice MPW)

## Slide 7
Main activities for 2016 – RD53A demonstrator chip (I)
  RD53A: full scale demonstrator chip
    Proposed 20x11.8 mm2 chip ( 400x192 pixels), 2500 µm2 pixel
    Goal: demonstrate in a large format IC
    suitability of 65nm technology (including radiation tolerance)
    high data/trigger rate, low threshold operation, high speed readout
    power management, serial powering
    put into effect RD53 WG proposals
    Not intended to be a production chip
    will contain design variations for testing purposes
    wafer scale production will enable prototyping of bump bonding assembly with realistic sensors in new technology  performance measurement
    To be submitted: end 2016 (prospected shared engineering run with other projects)
Project A
Project B

## Slide 8
Main activities for 2016 – RD53A demonstrator chip (II)
  Project organization
Pixel sensors and bump bonding
Template
Design flow + floorplan
Power
Building blocks
IP
Analog
Digital libraries
Digital
Pixel array
Simulation
Architecture
EoC
Control/timing
Readout
Configuration
Testing
Implementation
Test system
Support and services
Tools, design kit
Repository
Radiation effects and models
RD53A

## Slide 9
Main activities for 2016 – RD53A demonstrator chip (III)
  Planning
    3 main general project deliverables
    V0 (Q1 2016): upscaled FE65_P2
    improved design flow, normal standard cell libs, no IPs, single front end
    shared repository
    V1 (Q2-Q3 2016): near final architecture
    script-based design, multiple front ends, IPs for biasing and monitoring, near final RTL, TMR, radiation hard digital library
    functional verification, analog verification, timing verification, metal filling with verification
    V1.5 (Q4 2016): final architecture
    final RTL
    final implementation
    extensive functional and design verification
On time for MS4.1 Architectural review of deliverable chips in 65nm run M14 (June 2016)
The chip will be fabricated in an engineering run, with ≈500 kEuro paid by RD53 institutions (many are also part of AIDA-2020)
Cost sharing with other projects

## Slide 10: WP4.3 : SiGe 130 nm microelectronics
(CNRS-IPNL, CNRS-OMEGA, DESY, AGH-UST)
Coordination: CNRS-OMEGA
Select best SiGe 130/180 nm process for high speed/high dynamic range ASIC design to upgrade current SiGe 350 nm AMS process
Deliver SPIROC3 SiPM readout for calorimeter readout of WP14
Deliver RPC high timing readout chip for WP13
Share expertise within SiGe HEP community
  Study for LHC run 2, ILC…

## Slide 11
Task 4.4 Interconnections and TSVs
(CERN, INFN-GE, INFN-PV, INFN-PG, CNRS-CPPM, CNRS-LAL, MPG-MPP, UBONN, UNIGLA)
Produce through-silicon vias on wafers from Task 4.2
Connect chips with TSVs to detectors from WP7
Test radiation hardness of interconnections

## Slide 12: Candidate processes for TSV
WP4 groups are currently working with two different technology providers for Through-Silicon Vias in 130 nm CMOS FE-I4 pixel readout chips:
IZM (via last tapered TSVs)
CEA-LETI (via last TSVs + RDL + direct wafer-to-wafer bonding)
Results are expected in 2016. Plans are to extend this study to 65 nm CMOS wafers from the RD53 engineering run.

## Slide 13: Goals of TSV processing
Test processes for peripheral TSVs on the 130 nm FEI4 chip, and apply them to the 65 nm RD53A chip
  Allow for 4 side buttable modules
  Enable wafer-to-wafer assembly
  Remove wirebonds for greater module robustness
The RD53A chip will be designed so that it is “TSV enabled” (i.e. , compliant with TSV design rules); this involves the peripheral bonding pad regions
On track to MS4.7 Selection of TSV process M14 (June 2016)

## Slide 14: WP4 outlook
WP4 appears to be on track with respect to the 2016 milestones
Pixel readout chip prototypes in 65 nm CMOS will be available in 2016 for testing sensors from WP7
Thanks to synergies with RD53 (65 nm CMOS engineering in Q4 2016 - Q1 2017), also longer term schedule looks reasonable

## Slide 15: AIDA WP4 deliverables
D4.1 CMOS 65 nm engineering run (availability of the run with the “ATLAS/CMS” and CLICPIX pixel chips) (CERN)
M36 (April 30, 2018)
D4.2 BICMOS SiGe engineering run (availability of run with SiPM calorimeter-WP14 and gas detectors-WP13 chips) (CNRS)
M36 (April 30, 2018)
D4.3 Through Silicon Vias production (fabrication of TSV in wafers of deliverable 4.1) (INFN)
M42 (October 31, 2018)