## Slide 1: Proposal for timeline for yearly optic release
G. Arduini,R. De Maria, P. Fessia, M. Giovannozzi

## Slide 2
Step no. | Date | Action/document
1 | 1 month after the annual meeting | update of list of the changes already known to be implemented in the next version
2 | 15th March | freeze hardware changes to be applied to next optics version
3 | 15th April | Draft new optics/layout from optics team
4 | 15th May | 3D model of new optics and list of modifications following integration analysis.
5 | 1st June | Agreed version between optics and integration, HW modifications are frozen and review of 3D models of integration
6 | 1st July | Final Optics/layout available for other work packages
7 | 7th July | review of the final 3D model in meeting and start production of 2D drawings
8 | 15th September | last drawing into approval
9 | 15th October | Closure of approval
10 | 1st November | list of the changes already known to be implemented in the next version

## Slide 3: Main changes for next version under discussion
Q5 at Point 6: 1.9 K vs 4.5 K decision today
Revision of magnet lengths according to latest trimming data available
BPM near Q1
  BPM in Experimental area study completed
  BPM shifted in good position in the Q1
    Option 1 BPM in Q1 shift no L* change study well advanced, presentation this Friday at the integration meeting
    Option 2 BPM shift and rigid triplet movement with L* change-> improvement of position of the other BPM to be started following above results
    Change of the cooling approach for the MS: change of jumper position to be started