## Slide 1: Roadmap for Decisions Circuit Powering and Protection
Daniel Wollmann
with Inputs from B. Auchmann, A. Ballarino, R. Denz, P. Fessia, V. Parma, H. Prin, F. Rodrigues Mateos, R. Schmidt, E. Todesco, A. Verweij, M. Zerlauth
Conceptual Design Review of the Magnet Circuits for the HL-LHC 21.-23.03.2016 - CERN

## Slide 2: Outline
What is covered by this talk and what not
New HL-LHC circuits and their parameters
Global time line and milestones
Summary

## Slide 3: Covered by this talk
Time line to LS2 and beyond
Critical milestones concerning
  Configuration management
  Documentation
  Decisions
  Production and installation of hardware
Time line for all circuit elements for powering and protection:
  Magnets
  Power converters
  Superconducting Link
  Bus-bars, Distribution field boxes (DFs), splices, …
  Protection equipment: Quench Detection Systems (QDS), Coupling Loss Induced Quench Systems (CLIQ), Quench heater power supplies (HDS), Energy Extraction Systems (EE)
  Electrical Quality Assurance (ELQA)

## Slide 4: Not covered in this talk
Detailed schedules for
  Integration (see talk by P. Fessia)
  String tests (see talk by L. Bottura)
  Warm cabling, Cooling & Ventilation (see talk by L. Tavian)
  Magnet production, testing and installation (see talk by E. Todesco)
  Superconducting link (see talk by A. Ballarino)
  Power converters (see talk by J.P. Burnet)
  Breakdown between protection hardware (see talks by J. Steckert, K. Dahlerup-Petersen, … )
  Content of documents mentioned below (see talk by R. Denz)

## Slide 5: Reminder: Circuits and their parameters
Triplet: Q1, Q2a, Q2b, Q3; orbit corrector magnets, higher order corrector magnets (super ferric)
Matching Section: D1, D2, Q4, Q5, Q6; orbit corrector magnets
Main dipole circuits (sector 67 / 78): 11T dipole
TCC share-point, baseline circuit table to be updated

## Slide 6: Global time line and major milestones
Available magnets for String III Phase 1 and Phase 2

## Slide 7: Global time line and major milestones
03.2016 Conceptual Circuit Review.
Space reservations for civil engineering
TDR.V1 mid 2016 and probably yearly updates.
Cost & Schedule review 2 10.2016 and probably in the coming years.
Long shutdowns of LHC: LS2 2019-2020; LS3 2024 – 2026
String III: Phase1 2020/21, Phase2 2021 - 2023
Available magnets for String III Phase 1 and Phase 2
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation

## Slide 8: Global time line and major milestones
Operational requirements
Optics requirements
Magnet Protection
Circuit Design + Protection
Cold and warm powering (sc. Link, PCs, bus bars, … )
Protection Hardware
Cryogenics
Integration
Testing
ELQA
Planning
Budget
Available magnets for String III Phase 1 and Phase 2
Updated detailed baseline for the HiLumi circuits taking into account all relevant constraints (TDR.V1):
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Circuit baseline update

## Slide 9: Global time line and major milestones
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Prototype tests of (high field) magnets (Nb3Sn, NbTi) [SM18], superconducting link, and other novel equipment (e.g. CLIQ):
  tests ongoing
  Short model magnet tests will be finished by end 2017  verification of performance
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation

## Slide 10: Global time line and major milestones
Finalizing parameter definition for every circuit and all parts of the circuits taking into account results of prototype tests (magnets, sc. link, bus bars, splices, warm cables, PCs, instrumentation, controls, ELQA)  Protection R&D document for every circuit.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Circuit protection documentation

## Slide 11: Global time line and major milestones
Functional specifications
Integration review
Engineering specifications
Available magnets for String III Phase 1 and Phase 2
Conceptual Circuit Review
TDR.V1
C&S Rview
Circuit baseline update
Circuit protection documentation
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs

## Slide 12: Global time line and major milestones
Production readiness reviews
Procurement and Construction
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs

## Slide 13: Global time line and major milestones
Specification of individual system tests (IST).
Hardware commissioning (HWC) procedures.
Specification of ELQA tests.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
IST-HWC-ELQA procedures

## Slide 14: Global time line and major milestones
Installation and commissioning for String III.
Installation and commissioning for 11T in LHC IP7.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
IST-HWC-ELQA procedures
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
11T dipole & String III commissioning

## Slide 15: Global time line and major milestones
String III - Phase I: Prototype tests for all subsystems, verification of concepts, improvements, verification of IST and HWC procedures, ...
String III - Phase II: Final implementation and validation of magnet, powering (excl. final PCs), detection, protection and operation (incl. commissioning).
Operation of 11T dipole in RB circuits of sectors 67 and 78.  1st Nb3Sn magnet in accelerator.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
11T dipole & String III commissioning
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
IST-HWC-ELQA procedures
Validation of triplet powering & protection

## Slide 16: Global time line and major milestones
Series production for installation in LS 3
Update of IST and HWC procedures
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
11T dipole & String III commissioning
Validation of triplet powering & protection
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
IST-HWC-ELQA procedures
IST and HWC procedures updated

## Slide 17: Global time line and major milestones
Installation of Hardware in LHC tunnel and underground areas.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
11T dipole & String III commissioning
Validation of triplet powering & protection
IST and HWC procedures updated
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
IST-HWC-ELQA procedures

## Slide 18: Global time line and major milestones
Hardware commissioning & operation of HiLumi circuits.
Available magnets for String III Phase 1 and Phase 2
Circuit baseline update
Circuit protection documentation
11T dipole & String III commissioning
Validation of triplet powering & protection
IST and HWC procedures updated
Hardware commissioning
Conceptual Circuit Review
TDR.V1
C&S Review
Space reservation
Eng. Specs
Funct. Specs
IST-HWC-ELQA procedures

## Slide 19: Summary
Tight schedule: 2.5 years until LS 2 (11T installation in IP7) and 3.5 years to installation of the triplet string.
Update of circuit baseline required (mid 2016) to derive the detailed circuit parameters, protection needs, and failure cases  Protection R&D document for each circuit (Q2.2017)  Circuit review 2?
Baseline update and circuit documentation are essential input for the design of the superconducting link, bus bars, DFs, splices and protection hardware (QDS, CLIQ, HDS, EE, ELQA)  Functional specifications.
Functional and Engineering specifications could be reviewed globally or system by system ( production readiness review, integration review).
String III Phase 2 will be the ultimate validation of the triplet powering and protection scheme (excl. final power converters). The timeline of the String test leaves a (small) time window for iterations and improvements before the installation in the LHC during LS3.
String III and LS2 have significant overlap, which could cause resource issues and, therefore, risks to introduce delays.

## Slide 20: Thanks you for your attention! Question?