## Slide 1: Overall Strategy
3 phases:
  Initial phase: recover last year performance.
    How: start from last archives & references, (hopefully) small adjustments
    Goal: verify repeatability, hardware checks, “come-back point”, document status
    Duration: 4 weeks
  Full optimization
    How: systematic approach, start-to-end
    Goal: Improve beam performance, demonstrate emittance/b. length control, prepare ultimate beam(s) for experiments
    Duration: 8 weeks
  Exploitation
    How: use ultimate beam(s)
    Goal: Fully exploit beam performance to complete experiments (TBM, TBL, FF, Diags, …)
    Duration: until December 2016 (6 months?)

## Slide 2: First phase
Start with last year archive, 3 GHz
  Time 2 weeks
  Goal recover last run performance (factor 4, transport to CLEX if possible)
  Beams 3 GHz, factor (1,2,3)4
  Main Meas. current, charge stability, losses, emittance (optics checks and studies t.b.d.?)
  Experiments TBM (hardware checks, RF conditioning), Phase ff (hardware, unc.)
Last year archive, 1.5 GHz
  Time 2 weeks
  Goal recover last run performance (factor 8, trasport to CLEX if possible)
  Beams 1.5 (3) GHz, factor (1,2,3,4), 2DL, 8
  Main Meas. current, charge stability, losses, emittance
  Experiments TBM (RF conditioning), (Phase ff if needed, uncombined)
Need to define some dedicated measurements/studies during this phase, to better prepare for the next one.
  Proposal: study and document emittance evolution in the complex with consistent quad scans in the whole machine.
  And/Or: study stability of beam condition with night running / automatic quad scans
  Other? (e.g., tools testing/development)

## Slide 3: Second phase
Linac set-up
  Time 2 weeks
  Goal optimize injector and linac, take and document references
  Beams 3 GHz (1st week) – 1.5 GHz (2nd week)
  Procedure and main measurements:
    Injector set-up, long. (3 GHz – opt. for wguides, energy spread, b.length with phase scan)
    Orbit correction in the solenoid, Emitt. optimization in girder 10
    Dispersion and orbit correction (iterate)
    Transverse matching (quad scans) – iterate dispersion and orbit
    Final orbit correction
    Same procedure for 1.5 GHz (long pulse with switches)
    N.B.: Initial set-up for 3 GHz, fast 1.5 GHz, complete 3 GHz, full 1.5 GHz, verify 3 GHz
  Experiments (Phase FF if needed, 3 GHz uncombined beam)

## Slide 4: Second phase
DL set-up
  Time 1 week (+ 1 week reserve, including missing measurements in linac)
  Goal optimize DL, take and document references
  Beams 3 GHz – 1.5 GHz
  Procedure and main measurements:
    Transverse matching (quad scans)
    Magnetic inj/extr optimization
    Orbit correction (dipole strength scan + orbit corr.)
    Dispersion correction?
    Final orbit and dispersion match to TL1
    Set up of RF injection, verification of orbit, dispersion and matching
  Experiments - none

## Slide 5: Second phase
Combiner ring set-up
  Time 2 weeks
  Goal optimize TL1 and Combiner ring, take and document references
  Beams 3 GHz – 1.5 GHz
  Procedure and main measurements
    To be defined
    …
    …
  Experiments (beam to TBM for conditioning?)

## Slide 6: Second phase
Transport to CLEX set-up
  Time 2 weeks
  Goal optimize TL2 and TL2’ (initial set-up TBM/TBL), take and document references
  Beams (3 GHz) – 1.5 GHz
  Procedure and main measurements
    To be defined
  Experiments TBM, TBL checks…

## Slide 7: Third phase
In principle, we have many months for the experiments
Main activity: TBM experiments
  Conditioning to nominal, then maximum power
  RF checks, phase measurements…
  Two-Beam acceleration with nominal RF pulse length
  Max Two-Beam acceleration with short RF pulse length
  WF monitors
  Active alignment with beam
  …
TBL: consolidate 2015 results
FF: consolidate (time stability), large gain (short pulse)…
Diagnostics
…

## Slide 8: Special case: Beam-loading dog-leg experiment
Dog-leg experiment is very high priority this year
 Dedicate 1 week at the start to initial set-up and full check of
whole system
 Optimize switch, depending on results:
    Dedicate a few nights/week + week-ends to dogleg during phases 1 and 2
    Dedicate only week-ends to dogleg during phases 1 and 2