## Slide 1: Review of the 11T Dipoles at Collimator Section for the HL-LHC
Closed-out Report
Akira Yamamoto (Chair)
held at CERN, 6 April, 2016
8 April, 2016

## Slide 2: Useful Links
Overview:
https://indico.cern.ch/event/493351/overview
Presentation Indico page:
https://indico.cern.ch/event/493351/other-view?view=standard

## Slide 3: Review Panel Members
Akira Yamamoto (KEK-CERN, Chair),
Giorgio Apollinari (Fermilab),
Arnaud Devred (ITER),
Pasquale Fabbricatore (INFN),
Joe Minervini (MIT),
Pierre Vedrine (CEA).
Jean-Philippe Tock (link person)

## Slide 4: Background
HL-LHC is in the final stage of design and prototyping: all technologies for the hardware upgrade must be fully proven by beginning of 2017.
This review covers the 11T dipole, planned to substitute the LHC dipole cryo-magnets in the Dispersion Suppressor, with a new unit producing the same integrated field, requiring a bore field in the range of 11 T, and an integrated by-pass for a collimator.
Previous technical reviews addressed the engineering concepts, and cost and schedule (within the overall scope of HL-LHC).

## Slide 5: The Scope of this Review is to examine:
Magnet design status, with special attention to the cold mass, its cryostat and electrical, hydraulic, mechanical, vacuum interfaces and integration in the LHC continuous cryostat and LHC arc circuit; (AY,
By-pass and collimator design; (PV)
Results of model magnets; (GA,
Status of prototype magnets; (GA,
Conductor performance, procurement status and plans; (AD
Status of production tooling, finalization of design and procurement; (PF, GA)
Components procurement, status and plans; (JM
Test plan, QA/QC, (AD) and safety aspects; (PV),
Production schedule and global plan to installation (including constraints given by LS2). (JM, GA, AD, PF, PD, AY)

## Slide 6: Questions to the panel
Overview
Is the overall plan for the 11T dipoles at collimator section clear, realistic and coherent with the whole HL-LHC project? Does it satisfy the needs ?
Is the plan matching the request from collimation ?
Are the recommendations from the previous review adequately followed-(up)?
Models
Was the acquired experience with the models well fed into the prototype/series design ?
Have all useful tests been carried out ? If not, which ones would you recommend ?
Have the tests results been sufficiently analyzed and understood ? If not, do you recommend further analysis ?
Prototype / Series
Is the development of the design (superconductor, collared coil, cold mass, cryostat,….) appropriate wrt the overall project (in terms of quality, schedule, resources)? If not, what are the critical areas ?
Is the development of the tooling appropriate wrt the overall project (in terms of capacity, quality, schedule, resources, margins,…)?
Are all procurement aspects (superconductor, collared coil, cold mass, cryostat,….) including QA/QC in line with the needs ? If not, what is missing or should be reinforced ?
Is the protection scheme presented sufficiently robust to be compatible with the operation constraints ? If not, what is missing or should be developed or modified ?
Is the powering scheme presented adequate for the operation of the 11 T in the LHC arcs ? If not, what are the areas to improve ?
Is the test plan (throughout production and acceptance tests) sufficiently developed ? If not, which critical tests are missing ?
Is the production strategy in a maturity stage corresponding to the global project ?
As a summarizing question
The results obtained so far and a plan for the project were presented. Have you identified missing topics that would jeopardize the 11T dipoles at collimator section and prevent from installing two 11T assemblies during LS2 ?
Is the plan allowing to meet the challenges realistic ? Is the inherent level of risk acceptable ?

## Slide 7: Review Agenda to be filled
4/6 | Subjects | Speaker
8:30 | Closed Session at Prevessin site (B774-R-013) | A. Yamamoto
9:00 | Session 1 | 
 | Welcome address | Luca BOTTURA
 | Requests from Collimation | Stefano REDAELLI
 | Introduction and new 11 T plan in HL-LHC | Frederic SAVARY
 | Cryo-assembly and by-pass cryostat design | Delio DUARTE RAMOS
 | Coil winding and collaring | David SMEKENS
 | Cold mass assembly design | Herve PRIN
 | Magnet powering and operation requirements | Samer YAMMINE
14:00 | Session 2 | 
 | Model magnet test results and analysis at FNAL | Alexander ZLOBIN
 | CERN superconductor and cable design performance | Bernardo BORDIN
 | Model magnet production and plan | Juan Carlos PEREZ
 | Model magnet test results and analysis - Quench performance vs mechanics and operation requirements | Gerard WILLERIN
 | Model magnet test results and analysis - Protection and operation requirements | Susana IZQUIERDO BERMUDEZ
 | Model magnet test results and analysis - Magnetic measurements and operation requirements | Lucio FISCARELLI

## Slide 8: Review Agenda to be filled
4/7 | Subjects | Speaker
8:30 | Closed Session at BE Auditorium , Meyrin | A. Yamamoto
9:00 | Session 3 | 
 | Magnet production : agenda of the day | Frederic SAVARY
 | Safety and codes | Thomas OTTO
 | 11T QA | Rosario PRINCIPE
 | Superconductor production plan, QA/QC | Bernardo BORDINI
 | SC cable production plan, QA/QC | Jerome FLEITER
 | Collared coil procurement, status and plan, QA/QC | David SMEKENS
 | Cold mass procurement, status and plan, QA/QC | Herve PRIN
 | Quality control tests throughout production – Factory acceptance tests | Arnaud Pascal FOUSSAT
14:00 | Session 4 | 
 | Cryostat procurement, status and plan, QA/QC | Delio DUARTE RAMOS
 | Vacuum and cryogenics systems procurement : status and plan, QA/QC | Cedric GARION
 | Powering and other systems procurement : status and plan, QA/QC | Hugues THIESEN
 | Final acceptance tests – test bench readiness | Gerard WILLERING
 | New cross-section and its rationale | Emelie Kristina NILSSON
 | Feedback on the recommendations from the previous review | Frederic SAVARY et al
 | Tooling status | Friedrich LACKNER

## Slide 9: Review Agenda to be filled
4/8 | Subjects | Speaker
8:30 | Closed Session at BE Auditorium , Meyrin | A. Yamamoto
9:00 | Session 5 Restricted Session | 
 | Magnet procudction strategy (restricted) | Frederic SAVARY
 | Q & A Session | 
 | Visit Large Magnet Facility | 
14:00 | Session 6 | 
 | Panel Closed session | 
16:30 | Close-out Session | 

## Slide 10: 11T Dipole Review-Panel Report Executive Summary
The 3nd international review of the “HL-LHC 11 T dipoles at Collimator Section” was held at CERN, 6-8th April, 2016.
The committee received ~30 reports on the recent technical progress and the future project plan to meet the requirement for two pairs of 11 Tesla dipole magnets to be ready in series operation with LHC lattice main dipoles, after the LS2 completion in 2020. The committee summarizes our advice as follows:
After visiting the site for the model/prototype-work activities, the committee has been very impressed with the significant technical progress, initiated at Fermilab in the early stage, and then extended by CERN in the past several years.
Reaching the maximum field above 12 T and stable operation at 11T with the model magnet is a great milestone achievement for the HL-LHC project. The committee recognizes that the Nb3Sn magnet technology has matured and is now practical for applications in specific areas where higher magnetic fields above 10 T are critically required.

## Slide 11
Success of the 11T project will set the stage for further Nb3Sn applications in energy-frontier hadron accelerators.
The project needs to move quickly into the LS2 construction stage after the ongoing prototype work with full coil windings, magnet assembly, and demonstrated performance. No time remains for any major design changes.
The committee is pleased with the plan for the production magnets to be tested to a level having sufficient margin (> 105 %) in terms of the nominal operation current, with confirmation of the mechanical stability/margin before installation into the tunnel. It may also minimize the number of re-training quenches after periodic thermal cycling.
The committee is pleased to recognize that the magnet interface to the collimator has been well established.
The project time scale for the first set of 11 T dipoles is still very challenging for them to be ready in the LHC tunnel by 2020, even with the assumption of no failures in the fabrication process of 10 units (8 + 2 spares) over the course of ~3 years.

## Slide 12
For the LS3 program, the committee endorses the development of a 2nd strand supplier for LHC upgrade magnets. The committee recommends to move expeditiously with the manufacture of dipole magnet models with the new PIT strand layout, cable design, and magnet cross-section.
Nevertheless, design changes with respect to LS2 magnets should be minimized. It is essential to define milestones and decision points for the PIT strand adoption and the change of cross-section for LS3.
The committee encourages development and update of the manufacturing plan, including tooling usage, and under various assumptions for industry involvement, for all combined activities required by LS3 (11 T dipoles, MQXF, and other projects).
Several options for industry involvement in LS2 and LS3 were presented, and the committee encourages further development and integration of these capabilities into the project plan. This strategy, however, should not delay the construction schedule. Full production capability should be maintained at CERN.
The committee congratulates the great achievements of the team in the development of the 11T dipole with NB3Sn technology, reflecting the experiences and expertise of both US and CERN laboratories. We are also very pleased to see fresh efforts and continuity provided by much younger generation promising the future.

## Slide 13: Draft questions to the panel Overview
Is the overall plan for the 11T dipoles at collimator section clear, realistic and coherent with the whole HL-LHC project? Does it satisfy the needs ? Is the plan matching the request from collimation ?
  In general yes, the overall 11 T plan is clear and coherent although the LS2 execution part is success oriented.
  The plans for LS2 and LS3 installation do satisfy the HL-LHC schedule and performance based on needs in IR7 and the installation of 2 units (1 unit/beam) in LS2 and 2 more full units in LS3.
  The discussions with the collimation group were very successful in finding a mutually agreeable set of magnet and collimator length dimensions that results in effective operation of the collimator while allowing for enough magnet length to allow for increased operating margin.
Are the recommendations from the previous review adequately followed-(up)?
  Yes. Exhaustively and comprehensively. Congratulations to the team are in order.

## Slide 14: Models
Was the acquired experience with the models well fed into the prototype/series design ?
Impressive progress since Dec ‘14.
The model series was very useful in developing different aspects of the fabrication processes, that led to the rather successful tests of the 2-in-1 , 2m long dipole model.
5 model coils built and tested, with 4 of them operated in magnets that passed nominal and ultimate currents. Stability demonstrated at high currents.
Handsome payback from “insertable pole” and “pole loading” design choice.
Embedded outer quench protection heaters perform as expected.
Field quality issues appear manageable for the series magnets.
Very few non-critical issues: delay to quench in low field areas, decay & snapback difference with FNAL data,…

## Slide 15
Have all useful tests been carried out ? If not, which ones would you recommend ?
No other model coils are needed for LS2 design.
Many of the tests and procedures recommended from the previous review were carried out. Recommend following tests /studies to be done:
  On the dummy copper model, make several cross-section cuts of the coils near both ends and the middle to investigate if the changes to the resin header method for impregnation really resulted in good distribution of the epoxy. Check for dry areas and voids.
  Take at least one of the Nb3Sn model coils that was tested to ~11T or more and make several cross-sections to see if any affects of operation under heavy Lorentz load and stresses resulted in any visible signs internal damage, motion, voids, cracks, distortions, or displacements.
  Perform compression tests on actual Nb3Sn coil cross-sections to determine more accurate coil modulus for improvement of mechanical analysis.
  Paper studies on insulation braiding and comparison with QXF results could elucidate observations on coil wedges gaps after reaction.
Have the tests results been sufficiently analyzed and understood ? If not, do you recommend further analysis ?
Continue analysis of the quench data to determine why quench initiation in the low field region begins increasing later in time from the high field quench initiation when the operating current is reduced.

## Slide 16: Prototype / Series
Is the development of the design (superconductor, collared coil, cold mass, cryostat,….) appropriate wrt the overall project (in terms of quality, schedule, resources)? If not, what are the critical areas ?
The design based on RRP conductor is at the appropriate stage of development to transition expeditiously to prototype/series production.
The committee was impressed by the quality of preparation for all production-related activities: procurement of parts, procurement of superconductor, procurement and commissioning of tooling, establishment of procedures, QA/QC, etc.
The committee recommends to assess the PED and the impact on the helium vessel design, materials specification, and test procedure as soon as possible.
Is the development of the tooling appropriate wrt the overall project (in terms of capacity, quality, schedule, resources, margins,…)?
Tooling for winding, curing, reaction heat treatment and collaring have been validated. More work is still needed for the impregnation station and welding press.
Compatibility of the materials for the heat treatment mold should be reviewed. The present use of austenitic steel is questionable.
In present situation, a potential bottleneck seems to be identified, especially after the “LS2 Production”, in the impregnation equipment shared by 11T and QXF coil manufacturing for LS3.
Manufacturing plan for cable production was presented and appears credible. Backup solutions should be investigated with the US partner.
No coil and magnet “Manufacturing Plan” with expected “tooling occupancy” was presented. Also, there is obviously space to improve “Production Rates” by duplicating some inexpensive tooling, such as impregnation molds, curing setups or winding support.
The impression is that the 11T production will not have a major conflict for resources at the beginning (production for LS2) but will have to coordinate with MQXF and other magnets production later in the preparation for LS3.
In general, when assessing “Production” in future reviews, it would be beneficial to have integrated “production plans” between 11T, MQXF and other magnets, especially on items completely under CERN control (SM18 testing, etc.)
When the industry participation has been decided, their role and resources should be integrated into the production plans.

## Slide 17
Are all procurement aspects (superconductor, collared coil, cold mass, cryostat,….) including QA/QC in line with the needs ? If not, what is missing or should be reinforced ?
Yes, especially for LS2 magnets and RRP strand. No, for PIT strand and changed coil cross-section for LS3 magnets.
Proceed with the procurement of RRP strands for LS2 and LS3 and proceed with the production of cables and LS2 magnets based on the present design.
It is desirable to maintain 2 strand suppliers and to continue the development of PIT strands for Hi-Lumi LHC upgrade magnets.
It is essential to define milestones and decision points for the PIT strand adoption and the change of cross-section for LS3. Design changes with respect to LS2 magnets should be minimized.
QA/QC plans are well under development. QC measurements on strand could benefit from involvement of other organizations, so CERN concentrate on benchmarking and specialty measurements.
Is the protection scheme presented sufficiently robust to be compatible with the operation constraints ? If not, what is missing or should be developed or modified ?
The protection system appears to be well developed. The system relies on outer layer quench protection heaters.
Improvements in detection time and dump time might be sufficient, but the committee recommends continued analysis and model development of interlayer heater in case it is found to be required for sufficient hot spot temperature margin. Nevertheless, decision of implementation of interlayer QP heaters in production magnets should be very carefully assessed for its implication on the basic magnet design.

## Slide 18
Is the powering scheme presented adequate for the operation of the 11 T in the LHC arcs ? If not, what are the areas to improve ?
The committee recommends to study the possibility of Trim coil circuit test at SM18. In particular, the powering system in SM18 should be representative of operating conditions in the tunnel.
Is the test plan (throughout production and acceptance tests) sufficiently developed ? If not, which critical tests are missing ?
In general, yes. Plans for production and tests are well developed, including a “system test” with 2 magnets and bypass cryostat test in SM18
Plans/schedules for testing should be developed for 11T, QXF and other magnets testing. SM18 hardware capacity is expected to be more than sufficient to support all magnet testing.
Is the production strategy in a maturity stage corresponding to the global project ?
For LS2 and RRP the production strategy is approaching maturity. However, since the schedule is “success-oriented”, the committee suggests to consider anticipating LS2 series production of coils before completion of prototypes cold test.
For LS2 and RRP production strategy, the committee endorses the present plan of executing production on CERN premises.
The production strategy for LS3 is still at a development stage
Several options for industry involvement in LS2 and LS3 were presented, and the committee encourages further development and integration of these capabilities into the project plan. This strategy, however, should not delay the construction schedule. Full production capability should be maintained at CERN.

## Slide 19: As a summarizing question
The results obtained so far and a plan for the project were presented. Have you identified missing topics that would jeopardize the 11T dipoles at collimator section and prevent from installing two 11T assemblies during LS2 ?
Is the plan allowing to meet the challenges realistic ? Is the inherent level of risk acceptable ?
The risks and mitigation strategies presented by the WP Leader in the closed session appear well thought-out and reasonable.
In general, the level of risk is small in transitioning the project to “prototype execution” and then “construction” for LS2 given the successful model program based on “generation 1 cable” and the RRP superconductor.
A competent crew is in place for all activities (magnets production, cryostat production, powering and protection schemes, QA/QC, etc.) and insures a low risk for the LS2 production.
The introduction of a “generation 2 cable” and PIT superconductor (and subsequent design change) introduces an element of risk for LS3 production that needs to be addressed immediately with an aggressive model program.

## Slide 20: Acknowledgments
Many thanks everybody for his/her effort involved in the HL-LHC 11T dipole project, and to contribute to the review. Congratulations for the successful review !
Review Panel: G. Apollinari, A. Devred, P. Fabbricatore,
J. Minervini, P. Vedrin, and A. Yamamoto