## Slide 1
Future Accelerator Studies Section SMB-SE-FAS
John Osborne
Group Meeting 5 Feb 2016

## Slide 2
Charlie COOK
Martin MANFREDI
Joanna STANYARD
Future Accelerator Studies Section (FAS)
SL: John OSBORNE
Engineers
Future Circular Collider (FCC)
High Luminosity LHC (HL-LHC)
Laguna
SHIP
Linear Colliders
R2E
LHeC
SMB/SE/FAS : 2015
SMB

## Slide 3: HL-LHC WP17 SubWork Packages
WP17.1 Civil Engineering
J. Osborne, M.Manfredi
WP17.2 Electrical Distribution
G. Cumer, N. Dos Santos, JC. Guillaume
WP17.3 Cooling & Ventilation
M. Battistin, P. Pepinster
WP17.4 Access & Alarms
T. Hakulinen, P. Ninin
WP17.6 Survey & Alignment
H. Mainaud Durand
WP17.8 Upgrad. & Cons. of Test/Assembly Facilities for HL-LHC
I. Bejar Alonso
WP17.9 Logistics & Storage
I. Bejar Alonso
WP17.10 Operational Safety
T. Otto
WP17.5 Technical monitoring
T. Hakulinen, P. Ninin
WP17.7 Transport
C. Bertone, B. Feral
General Infrastructures Services Department
From Sept 2015 : Jo Stanyard SE-FAS, Pieter Mattelaer SMB-DI, DOP Section &
M.Poehler for permits/local affairs

## Slide 4: SE:FAS HL Underground Works (in red)

## Slide 5: HL Underground Civil Works at Point 5
General Infrastructures Services Department

## Slide 6: Civil Engineering : Layouts Point 5 CMS France IT-4155/SMB/HL-LHC

## Slide 7: Proposed site boundary enlargement for civil works : Point 5 CMS
Worksite Area
(approx. 30% increase in CMS surface area)

## Slide 8: The Works for HL-LHC at Point 5

## Slide 9: The surface works for HL-LHC at Point 5
Electrical Building
Ventilation Building
Helium Liquefier Building
Head Shaft Building
Rectifier Building
Cooling Towers
Compressor Building

## Slide 10: The surface works for HL-LHC at Point 5 – Concrete buildings
= concrete building
Ventilation Building
Rectifier Building
Cooling Towers
Compressor Building

## Slide 11: SF57 - Cooling Towers

## Slide 12: The surface works for HL-LHC at Point 5 – Steel Buildings
= steel building
Electrical Building
Helium Liquefier Building
Head Shaft Building

## Slide 13: Typical sections of Underground works at Point 5

## Slide 14: Typical section of underground works

## Slide 15: Civil Engineering : Layouts Point 1 ATLAS Switzerland IT-4144/SMB/HL-LHC

## Slide 16: Site Boundary enlargement for civil works : Point 1 ATLAS
Worksite area (approx. 20% increase in ATLAS surface area)
Worksite access

## Slide 17: The Surface Works at HL-LHC at Point 1
Electrical Building
Ventilation Building
Helium Liquefier Building
Head Shaft Building
Rectifier Building
Cooling Towers
Compressor Building

## Slide 18: Results from Dr Hiller’s (Arup) studies - Vibration from tunnelling
45m
0.2 mm/s
2x10-4 m/s
200µm/s
At 45m, tunnelling vibration would give ~200µm/s peak
General Infrastructures Services Department
The main ‘vibration’ activities are driving the civil engineering planning
More testing planned with EN/MME
Roadheaders will be used for excavation
New measurements needed for concrete pump, hydraulic hammer, roadheader,
Jumbo

## Slide 19: Site Investigations
In addition to existing geotechnical information from LHC, site investigations were undertaken at Point 1 and Point 5 for HL-LHC.
Site investigations at P1
Site investigations at P5

## Slide 20: Preliminary findings from geotechnical survey
Point 5 :
Layer of made ground above glacial formations with a maximum depth of 50m, covering Molasse.
These conditions are in agreement with results from existing geotechnical surveys of the area.
At the new shaft location the depth of the Moraines is approximately 25m.
Point 1 :
A thin layer of made ground above 3 to 10 m of moraines.
Hydrocarbons were detected in 3 of the coring locations. Lab testing is on-going.
The full factual report will be provided as soon as it is available (most likely March ‘16)

## Slide 21
Agreed HL-LHC CE Contract Strategy
Packages 1 :
1a : Architect contract for building permit submission (CH)
1b : Consultants for design of underground and surface
1c : Contractor for underground and surface works
Packages 2 :
2a : Architect contract for building permit submission (F)
2b : Consultants for design of underground and surface
2c : Contractor for underground and surface works

## Slide 22: Agreed Civil engineering planning in Consultants Tender
24hr working for underground

## Slide 23
15 companies attended
46 participants
Deadline for replies extended to 9 March (at CERN)
June FC
Early start in May ?
HL-LHC Bidders Conference 29 Jan 2016

## Slide 24
Progression of CE Study
FCC CE Workshop
CE/Geology and Optimisation Meeting 5
Quasi-circular machine proposed of lengths 80km, 87km, 93km & 100km.
Injection lines studied
Narrowed down to four options; 1a (93km), 2a (100km), 1b (93km), 2b (100km)
26/09/14
19/11/14
FCC CE study presented at FCC week, Washington 2015
Footprint, positioning and planarity assessed by review panel – Decision taken to focus on 100km FCC machine
25/03/15
11/06/15
FCC Week, Washington
FCC Review Meeting
Geological profile of the Prealpes, upgrades to TOT, general risk assessment and comparison of 100km options
Up to FCC week, April 2016
Study Phase 2
SE-FAS : Future Circular Collider
John Osborne, Charlie Cook GS-SE-FAS

## Slide 25
20,800m
Avoids Jura limestone: No
Max overburden: 650m
Deepest shaft: 392m
% of tunnel in limestone: 13.5%
Total shaft depths: 3211m
100km Intersecting Option
Lake
Geneva
Vallée de l‘Arve
Mandallaz
Le Rhône
Challenges:
7.8km tunnelling through Jura limestone
300m-400m deep shafts and caverns in molasse
Point A Campus: Prevessin (large potential area)

## Slide 26
100km Non-intersecting Option
Avoids Jura limestone: Yes
Max overburden: 1350m
Deepest shaft: 383m
% of tunnel in limestone: 4.4%
Total shaft depths: 3095m
Lake
Geneva
Vallée de l‘Arve
Mandallaz
Le Rhône
Les Usses
Challenges:
1.35km tunnel overburden
300m-400m deep shafts and caverns in molasse
Point A Campus: Meyrin (small potential area, next to airport)
Limestone in this area
is yet to be included in TOT

## Slide 27
Twin Solenoid detector cavern with shaft
Cavern Option | Access solution | Shaft/tunnel diameter [m] | Detector design | Required dimensions for installation [m] | Width of metallic structures [m] | Cavern dimensions (LxWxH) [m] | Span [m]
Option 1 | Shaft | 28 | Twin Solenoid | 65x30x36 | 8 | 65x38x36 | 38
Option 2 | Inclined tunnel | 14 | Toroid | 86x36x42 | 8 | 86x44x42 | 44
42 m
44 m
86 m
8 m
13 m
First Draft

## Slide 28
FCC Study Phase 2
FCC Risk Assessment (AMBERG)
FCC Comparison Study (AMBERG)
Geological representation of the Prealpes (GADZ)
Upgrades to TOT (ARUP)

## Slide 31
ILC Site Candidate Location in Japan: Kitakami
Oshu
Ichinoseki
Ofunato
Kesen-numa
Sendai
Express-
Rail
SE-FAS : International Linear Collider ILC
John Osborne GS-SE-FAS

## Slide 32: A New Boring at a Candidate Interaction Point
IP Region, candidate
A new boring test progressed to demonstrate the “vertical access feasibility” for detector hall at IP
Courtesy: T. Sanuki

## Slide 33
SE-FAS : CERN/KEK Collaboration to develop TOT for ILC Optimisation

## Slide 34
Digital and Technology Arcadis with Transport for London (TfL) Arup with CERN Atkins with Department for Education Baringa Partners with Nationwide CSC with Network Rail Deloitte with Philips Efficio with Network Rail Elixirr with TUI Group GE Healthcare Finnamore with Health Education England North Highland UK with Sainsbury's
TOT now being developed for tunnel under Stonehenge

## Slide 35
SE:FAS : Search for Hidden Particles (SHiP)
Feasibility report (Technical Proposal) issued in 2015
Major CE works required in North Area
John Osborne, Martin Manfredi GS-SE-FAS

## Slide 36
2016 Outlook
HL:LHC
  TDR CE Chapter
  External Independent Engineers appointed and managed
  Assist in Adjudicator Selection and co-ordination of visits
  Freeze Layouts
  Issue Geological reports
  Vibration measurements
  Consultants Bid analysis
  Consultants appointment in June FC, (early start may ?), Preliminary Design to be Completed in 2016
  Building Permits submitted
  Safety Co-ordinators MS / IT required
  Cost and Schedule reviews (April and October)
  MS for contractors
FCC
  Single tunnel v double tunnel decision
  Tunnel Optimisation Studies on-going using TOT
  Advising FCC-ee lattice design on CE constratints
  Cost/Schedule studies
  Interface with various working groups (hh, ee, he, I&O, MDI, Injectors)
  Workshop April 2016
Linear Colliders
  CLIC : New Baseline Layouts (One detector only, revised energies)
  ILC : TOT fully developed for Japan Site, Change Requests, TDR design refinements
SHiP : Design developed towards CDR
LHeC : Request for Layout studies to continue, especially in relation to FCC

## Slide 37
Charlie COOK
Martin MANFREDI
Joanna STANYARD
Future Accelerator Studies Section (FAS)
SL: John OSBORNE
Engineers
Future Circular
Collider (FCC)
HL-LHC
Contract preparation and monitoring
SHIP
Linear Colliders
Richard Morton
Vanessa Di Murro
Tunnel Asset Management
SMB
SMB/SE/FAS : 2016