## Slide 1: SPS Technical Stop
Tuesday 5th/6th July 2011
(Week 27)

## Slide 2: BA 1
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Jeremie Bauche | 164332 | 5th July | 1 day | Change magnet in position 13090. Water leak on a junction bloc of the hydraulic circuit | We will need as usual transport, survey, cooling and vacuum teams.(sector 142) | Y | Y | N | Y | 
Damien LAFARGE EN/HE | 168786 | 5TH July | 1 day | Condemnation des palans en zone “TA” en bas des ascenseurs pour descendre dans le tunnel SPS |  | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 2 hrs | Changeover PS pumps Purge MM sextant 1+ |  | N | Y | N | N | 
Gael Bellotto TE/ABT/FPS | 165038 | 5th July | 1.5 hr | Check level oil on MKP System (LSS1) MKP Kicker |  | Y | N | N | N | 
Nicolas Perez EN/HE | 169285 | 5th July | 07:00-09:00 hrs | Maintenance of lift AS510 | The lift will be out of service during this time. | N | N | N | N | 

## Slide 3: BA 2
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Cedric BAUD TE/ABT | 162338 | 5th July 14:00h | 10 mins | Visite de contrôle circuit eau septa MS Circuit indépendant 214 | Equipe: Robert BONTHOND, Cédric BAUD, Bruno BALHAN | N | N | N | N | 
Bruno BALHAN TE/ABT | 160059 | 5th July 14:00h | 1 hr | Inspection visuelle ZS et maintenance station 3M LSS2 | Intervenant: Bruno Balhan, Antoine Prost | N | N | N | N | 
Damien LAFARGE EN/HE | 168786 | 5TH July | 1 hr | Remplacement ampoule gyrophare sur pont roulant SDI2 sur le pont roulant Surface works |  | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 1 Day | Changeover PS pumps Test Septa pump 214A Modify ED circuit plc Tests Septa circuit Fit new Beam Damper safety valves Install new pump puisard DP523 | Stop all ED circuits Stop Beam Damper circuit | N | Y | N | N | 
Franck BAIS EN/MEF | 165467 | 5th July |  | Galerie TT20 (odm 17380394). GTM Entreprise |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 5th July | 07:00-10:00 hrs | Maintenance of Monte-Charge AS504 | The Monte-Charge will be out of service during this time. | N | N | N | N | 

## Slide 4: BA 3
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Klaus Fischer TE/EPC | 163452 | 6th July PM 16:00hrs | ½ Day | power tests of the QS power converter BA3- surface work | EPC asks for half a day for us to pulse Main Quadrupoles and Main Dipoles of the SPS. THE SPS MUST BE CLEARED!! | N | N | N | N | 
Michael Jaussi BE-RF | 169297 | 5th July 10:00hrs | 30 mins | Update of a micro-controller (CFB-LSS3-APWLATTEN1). It need to be done locally with a serial cable. BA3 tunnel, just in front of the lift. |  | N | N | N | N | 
Damien LAFARGE EN/HE | 168786 | 5th July | 1 day | Condemnation des palans en zone “TA” en bas des ascenseurs pour descendre dans le tunnel SPS |  | N | N | N | N | 
Damien LAFARGE EN/HE | 168786 | 5th July | 2 days | Réparation radio palan BA3 en surface, dans le local des armoires electriques d’alimentation du SPS |  | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 1 Hr | Changeover PS pumps |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 6th July | 09:30-11:30 hrs | Maintenance of Monte-Charge AS507 | The Monte-Charge will be out of service during this time. | N | N | N | N | 

## Slide 5: BA 4
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Cedric BAUD TE/ABT | 162338 | 5th July 10:00hrs | 10 mins | Visite de contrôle circuit eau septa MS circuit indépendant 414 | Equipe: Robert BONTHOND, Cédric BAUD, Bruno BALHAN | N | N | N | N | 
Guillaume GROS EN/EL | 163920 | 5th July AM | 1 day | Tests électriques sur câbles existants | Travail sur transparent durant l’arrêt du SPS quelques heures Pas de mesure de sécurité spécifiques a prendre | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 1 Hr | Changeover PS pumps Test Septa pump 414B |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 5th July | 09:30-11:30 hrs | Maintenance of lift AS511 | The lift will be out of service during this time. | N | N | N | N | 

## Slide 6: BA 5
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 5th July AM | 2 days | Démontage des racks RA1143 a 1150 et des câbles | Consignations TE/EPC nécessaires | Y | N | N | N | 
Antonio Gonzalez Puertas EN/EL/CF | 160454 | 5th July AM | 1 day | Optical fiber installation (First part of the installation was done already week 19) Installation of two optical fibers boxes to the floor, underneath beam line + fiber termination. (LSS5). Start Point: XRPH.51991 End Point: TAL.52196 The VIC was already done in the previous TS week 19. | 1.- Fixation of optical fiber box to the floor 2.- Fiber termination and measurements (a folding table will be in that area with the optical fiber instrumentation but it should be ok for people to pass y). | N | N | N | N | 
F.LOPRETE/ J.LENDARO EN-STI | 164535 163942 | 5th July 08:00h | 2 days | UA9 experiment : Installation and test of the Mini Roman Pot 52202 (ECR 1147957 ) . Works on motorizations and detectors, installation of new scintillators | Vacuum sector 550 | N | N | N | Y | 
Slawomir OLEK EN/EL | 163172 | 4th July | 4 days MD+TS | Consolidation of the 18kV network Modification of the false floor metallic structure (cutting and dismantling of existing steel supports and profiles, installation of new supports and profiles). Dismantling of the steel grid fence. These works will require welding and cutting of steel bars and profiles. Zone R013 | IS37, fire detection system | Y | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 1 Hr | Changeover PS pumps |  | N | N | N | N | 

## Slide 7: BA 5
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Mauro Taborelli TE/VSC | 163890 | 5th July AM | 2 days | Exchange of three liners in magnets: MDHW(XSD1)51832, MDHW(XSD2)51836, MDHW(SDNEG)51853 Exchange of mobile sample in magnet MDVW (mobile) at position 51734 | Vacuum sector 530 only. | N | N | N | Y | 

## Slide 8: BA 6
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Cedric BAUD TE/ABT | 162338 | 5th July 09:00hrs | 10 mins | Visite de contrôle circuit eau septa MS circuit indépendant 614 | Equipe: Robert BONTHOND, Cédric BAUD, Bruno BALHAN | N | N | N | N | 
Guillaume GROS EN/EL | 163920 | 5th July AM | 2 days | tirage câbles BI entre BA6 été BA7 | Pas de cohabitation possible dans le puits Minimum de cohabitation a prévoir dans le tunnel Consignations TE/EPC nécessaires | Y | N | N | N | 
Guillaume GROS EN/EL | 163920 | 5th July AM | 1 day | Tests électriques sur câbles existants | Travail sur transparent durant l’arrêt du SPS quelques heures Pas de mesure de sécurité spécifiques a prendre | N | N | N | N | 
Gilles Le Godec TE/EPC | 165288 | 6th July | 1 Day | Power tests of the MST6177 power converter BA6- surface work | EPC needs to pulse at the same time the following circuits (same 400Vac electrical feeder): TT60 power converters + MST6177 (Ring). Remark: it could be possible to drop from the list this job if the slots given during the operation of the machine allow to solve a stability issue with this converter. | N | N | N | N | 
Bruno BALHAN TE/ABT | 160059 | 5th July 09:00h | 1 hr | Inspection visuelle ZS et maintenance station 3M LSS6 | Intervenant: Bruno Balhan, Antoine Prost | N | N | N | N | 
GRENIER Damien EN/STI | 164339 | 5th July | 2 hrs | Prise de mesures pour changement de tuyauterie TED in TT60 | Seront presents pour cette visite : Franck MORO (EN/CV), Ste Inizative, Mathieu DONZE (EN/STI) et Damien GRENIER | N | N | N | N | 

## Slide 9: BA 6
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Damien LAFARGE EN/HE | 168786 | 5th July | 1 day | Condemnation des palans en zone “TA” en bas des ascenseurs pour descendre dans le tunnel SPS |  | N | N | N | N | 
Jerome LENDARO EN-STI | 163942 | 5th July | 2 hrs | Check water flow-meter of the TED.610321 in TT60 |  | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 5th July | 1 Day | Changeover PS pumps Tests Septa circuit Repair leak Power Supply circuit Fit ED counter Repair leak EP regulating valve | Stop Power Supply circuit | N | Y | N | N | 
Antonio Mongelluzzo TE/VSC | 165116 | 5th July | 1 hr | Cleaning of the feed through of the Ion pump 61633 BaA6 sector 631 |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 5th July | 13:30-15:30 hrs | Maintenance of lift AS508 | The lift will be out of service during this time. | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 5th July | 10:30-12:30 hrs | Maintenance of Monte-Charge AS509 | The Monte-Charge will be out of service during this time. | N | N | N | N | 

## Slide 10: BA 7
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Bill Bannister EN/CV | 163495 | 5th July | 4 hrs | Install new pump puisard DP534 |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 6th July | 06:00-08:00 hrs | Maintenance of lift AS512 | The lift will be out of service during this time. | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 6th July | 06:00-09:00 hrs | Maintenance of Monte-Charge AS513 | The Monte-Charge will be out of service during this time. | N | N | N | N | 

## Slide 11: TI 2
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Franck BAIS EN/MEF | 165467 | 5th July | ½ DAY | Peinture au sol devant portes TI2 Pose de panneaux ''Fin de zone SPS ou LHC'' sur porte TI2 | Work to be done by Antoine VASSALO and his team | N | N | N | N | 
Katy Foraz EN/MEF | 160540 | 5th July | 1 day | EL m’a annoncé cette activité dans le TI2 pour un accès côté LHC : TI2 : Fiabilisation de la chaine d’urgence (pas d’impact) |  | N | N | N | N | 

## Slide 12: TI 8
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Bill Bannister EN/CV | 163495 | 5th July | 4 hrs | Hadron Stop Install new ventilation plc Install ED circuit supervision PC Re-calibrate level Tx TNM41 |  | N | N | N | N | 
Franck BAIS EN/MEF | 165467 | 5th July | ½ DAY | Peinture au sol devant portes TI8 Pose de panneaux ''Fin de zone SPS ou LHC'' sur porte TI2 | Work to be done by Antoine VASSALO and his team | N | N | N | N | 
Antonio Mongelluzzo TE/VSC | 165116 | 5th July | 6 hrs | Leaktest at Ti 8 sector 1803 |  | N | N | N | N | 

## Slide 13: Other Areas
Person Responsible | Contact Details | Starting when? | Duration of work | Location of Work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Franck BAIS EN/MEF | 165467 | 6th July AM | 1 Day | SPS | Inspection et pose de panneaux Evacuation dans le tunnel SPS | With J. Pedersen | N | N | N | N | 
Jeremie Bauche | 164332 | 5th July 08:30 | morning | SPS | Inspection of magnets in the ring and the transfer lines |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 6th July | 08:30-10:30 hrs | BA80 | Maintenance of lift AS513 | The loft will be out of service during this time. | N | N | N | N |