## Slide 1: SPS Technical Stop
Tuesday
8th November 2011
(Week 45)

## Slide 2: BA 1
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 8th Nov 14h | 1 day | visite pour préparation chantier de reprise des racks Multiconducteurs (TA11) |  | N | N | N | N | Y
Bill Bannister EN/CV | 163495 | 8th Nov 14h | 2 hrs 1 hr 2hrs | Inspection Beam Dump circuit Inspection compressed air – tunnel Soupape vase d'expansion (Surface) |  | N | N | N | N | Y
Christophe TROMEL DGS/RP/AS | 163199 | 8th Nov 16h00 | 15 min | Retrait de 10 dosimètres en LSSS1.Intervention à faire avec Peter Burkel |  | N | N | N | N | Y
Frederic Galleazzi EN/MEF | 164552 | 8th Nov | 2hrs | Au cours de la modilisation 3D du SPS et des verification de plans associes ? ces equipements, j ai detecte plusieurs choses suspectes que je souhaiterais verifier dans le tunnel afin de modeliser ce qui est vraiment installe, et mettre tous les documents en concordance. |  | N | N | N | N | 
Wim Weterings TE/ABT |  | 8th Nov PM | 10 mins | Visual inspection on MKDV 2 in LSS1 in LSS1 kicker dump |  | N | N | N | N | 

## Slide 3: BA 2
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 8th Nov 15:00 | 1 day | visite pour préparation chantier de reprise des racks Multiconducteurs (TA21) |  | N | N | N | N | Y
Cédric BAUD TE/ABT | 162338 | 8th Nov 14:00 | 1 hr | Inspection visuelle septa MSE/MST LSS2 (21710-21872 | Equipe intervention: BAUD Cédric / BONTHOND Robert | N | N | N | N | Y
Bill Bannister EN/CV | 163495 | 8th Nov 14:00 | 1 hr 2 hrs 1hr 2 hrs | Repair leak demineriliser (Surface) Inspection Beam Dump circuit Inspection compressed air – tunnel Inspection TT20 puisard pipework |  | N | N | N | N | Y
Eric Montesinos BE/RF | 164235 | 8th Nov 13:00 | ½ Day | We will have to exchange a SPS Damper amplifier in LSS2. |  | N | N | N | N | Y
Eric Montesinos BE/RF | 164235 | 8th Nov 14:00 | 2 hrs | Regular inspection visit on SPS Dampers |  | N | N | N | N | Y
Nicolas Perez EN/HE | 169285 | 8th Nov | 9:30-11:00 hrs | Maintenance of lift AS503 | The lift will be out of service during this time. | N | N | N | N | N
Nicolas Perez EN/HE | 169285 | 8th Nov | 1 hr | Inspection of Monte-charge (AS504) in preparation of replacement of the doors during the winterstop. | J-P Lappe and outside company | N | N | N | N | N

## Slide 4: BA 2
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Frederic Galleazzi EN/MEF | 164552 | 8th Nov | 2hrs | Au cours de la modilisation 3D du SPS et des verification de plans associes ? ces equipements, j ai detecte plusieurs choses suspectes que je souhaiterais verifier dans le tunnel afin de modeliser ce qui est vraiment installe, et mettre tous les documents en concordance. |  | N | N | N | N | 
Yann HUPKINS EN/CV |  | 8th Nov 15:00 | 1 hr | Visite en TT20 pour préparation du chantier de démantèlement et réinstallation des tuyauteries des puisards |  | N | N | N | N | Y

## Slide 5: BA 3
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 8th Nov 08:30 | 1 day | Visite pour préparation dépose de câbles projet RF (TS3 – et TS3+) |  | N | N | N | N | N
Urs WEHRLE BE/RF | 164348 | 8th Nov 08:30 | 8 hrs | Repair of amplifiers for HFTFB (31901) |  | N | N | N | N | N
Bill Bannister EN/CV | 163495 | 8th Nov 08:30 | 8 hrs 1 hr 8 hrs | Install temp pump DP510/check coupling Inspection compressed air – tunnel Ventilation Cage faraday - Changing the bearings (Surface) |  | N | N | N | N | Y
Eric Montesinos BE/RF | 164235 | 8th Nov | 2 hrs | Regular inspection visit on TWC200, TWC800 and all RF pickups | All services must remain ON. | N | N | N | N | N
Frederic Galleazzi EN/MEF | 164552 | 8th Nov | 2hrs | Au cours de la modilisation 3D du SPS et des verification de plans associes ? ces equipements, j ai detecte plusieurs choses suspectes que je souhaiterais verifier dans le tunnel afin de modeliser ce qui est vraiment installe, et mettre tous les documents en concordance. |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 8th Nov | 1 hr | Inspection of Monte-charge (AS507) in preparation of replacement of the doors during the winter stop. | J-P Lappe and outside company | N | N | N | N | N

## Slide 6: BA 4
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 8th Nov 08:30 | 1 day | Visite pour préparation tirage Fibre Optique (PA4 + TA4 + TS4) |  | N | N | N | N | Y
Didier Vaxelaire GS/ASE | 162498 | 8th Nov AM 09:00 | ½ jour | Preparation travail PPG 4003 |  | N | N | N | N | Y
Christophe Vuitton BE/BI | 162903 | 8th Nov AM 09:00 | 1hr | Visit to the BWS to be modified during the Christmas break. 516, 514 |  | N | N | N | N | Y
Sylvain Girod EN/MEF | 165082 | 7th Nov 13:30 | 1 day | Installation diamond detector on CNGS hadron stop (Il y aura transport de matériel depuis BB4 vers TJ8-TI8-Hadron stop le 07/11. Avec dépose des chambres a vide en TJ8) | (TT41 position 410124 and TI8 position 80110) , Jarmo and Paolo have been informed | N | N | N | Y | Y
Cédric BAUD TE/ABT | 162338 | 8th Nov 09:30 | 1 hr | Inspection visuelle septa MSE/MST LSS4 (41837-41891) | Equipe intervention: BAUD Cédric / BONTHOND Robert | N | N | N | N | Y
Bill Bannister EN/CV | 163495 | 8th Nov 08:30 | 1 hr | Inspection compressed air – tunnel |  | N | N | N | N | N
Nicolas Perez EN/HE | 169285 | 8th Nov | 15:00 17:00 hrs | Maintenance of lift AS511 | The lift will be out of service during this time. | N | N | N | N | N
Pascal Brunero EN/HE | 163011 | 8th Nov |  | In preparation for the changing of a kicker tank during the winter stop, transport will put a new tank into the SPS. | Access via BA3 | N | N | N | N | 

## Slide 7: BA 4
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Frederic Galleazzi EN/MEF | 164552 | 8th Nov | 2hrs | Au cours de la modilisation 3D du SPS et des verification de plans associes ? ces equipements, j ai detecte plusieurs choses suspectes que je souhaiterais verifier dans le tunnel afin de modeliser ce qui est vraiment installe, et mettre tous les documents en concordance. |  | N | N | N | N | 

## Slide 8: BA 5
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Jerome Lendaro EN/STI | 163942 | 8th Nov 08:30 | 8 hrs | UA9 experiment : General works on motorizations and detectors to prepare the following MD. Check detectors in XRP.51991 | BA5-TS5-ECX5 secondary vacuum of XRP.51991 | N | N | N | Y | Y
Christophe Vuitton BE/BI | 162903 | 8th Nov 08:30 | 1hr | Visit to the BWS to be modified during the Christmas break. 517, 519, 521 |  | N | N | N | N | Y
Bill Bannister EN/CV | 163495 | 8th Nov 08:30 | 8 hrs 1 hr | Test functionality TIM (Surface) Inspection compressed air – tunnel | To check the correct operation of TIM, there is a requirement to stop the cooling circuits at BA5 (Main Magnet and Power Supplies) | N | N | N | N | N
Nicolas Perez EN/HE | 169285 | 8th Nov | 07:30-09:30 hrs | Maintenance of lift AS506 | The lift will be out of service during this time. | N | N | N | N | N
Didier Vaxelaire GS ASE | 162498 | 8th Nov |  | Il s’agit d’installer une grille sur une porte à cote de la PPG 5139. | Access with Antonio Foreste | N | N | N | N | 

## Slide 9: BA 6
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Guillaume GROS EN/EL | 163920 | 8th Nov 08:30 | 1 day | Terminer la connectique sur BLM commence à l’arrêt technique précèdent TA61 et TS6 en 61776) |  | N | N | N | N | Y
Cédric BAUD TE/ABT | 162338 | 8th Nov 08:30 | 1 hr | Inspection visuelle septa MSE/MST LSS6 (61773-61872) | Equipe intervention: BAUD Cédric / BONTHOND Robert | N | N | N | N | Y
Ewald Effinger BE/BI | 164950 | 8th Nov 09:30 | 2 Hrs | Install diamond detector LSS6 after the cabling has been finished. Close to the TPSG | Ewald Effinger Erich Griesmayer Ion Savu Raymond Tissier | N | N | N | N | Y
Bill Bannister EN/CV | 163495 | 8th Nov 08:30 | 4 hrs 4 hrs 4 hrs 2 hrs 2 hrs 1 hr | Fit ED counter (Surface) Repair leak EP regulating valve (Surface) Beam Dump pressostat Test function 'capteur debit fuite (Surface) Inspection Beam Dump circuit Inspection compressed air - tunnel |  | N | N | N | N | Y
Frederic Galleazzi EN/MEF | 164552 | 8th Nov | 2hrs | Au cours de la modilisation 3D du SPS et des verification de plans associes ? ces equipements, j ai detecte plusieurs choses suspectes que je souhaiterais verifier dans le tunnel afin de modeliser ce qui est vraiment installe, et mettre tous les documents en concordance. |  | N | N | N | N | 
Stephane Burger BE/BI | 164941 | 8th Nov | 1 hr | Change camera or CCD box on BTV610252 | Access with K.Kessi | N | N | N | N | 

## Slide 10: BA 7
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Didier Vaxelaire GS/ASE | 162498 | 7th Nov AM 11th Nov PM | ½ jour and 2H (DSO test) | Remise dans l’interlock PPG 712 BA7 |  | N | N | N | N | 
Bill Bannister EN/CV | 163495 | 7th Nov | 4 days 4 days | Commissioning HiRadMat ED circuit Commissioning HiRadMat vent |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 7th Nov | 09:00-11:00 hrs | Maintenance of lift AS512 | The lift will be out of service during this time. | N | N | N | N | N
Nicolas Perez EN/HE | 169285 | 7th Nov | 13:00-16:00 hrs | Maintenance of Monte-Charge AS513 | The Monte-Charge will be out of service during this time. | N | N | N | N | N

## Slide 11: TI 2
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Serge Deleval EN/CV | 160382 | 7th Nov | 2 days | Nous avons prévu le remplacement de la pompe du circuit de refroidissement du TI2 |  | N | Y | N | N | 

## Slide 12: TI 8
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum
Person Responsible | Contact Details | Starting when? | Duration of work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Gyorgy Balazs IT/CS | 161200 | 8th Nov | 1 day | Modification des alimentations électriques des BTSs dans les alvéoles du LHC --> travaux réalisés par EN/EL, à coordonner avec Sunrise pour les swaps des BTSs sur les nouvelles alimentations |  | N | N | N | N | 

## Slide 13: Other Areas
Person Responsible | Contact Details | Starting when? | Duration of work | Location of Work | Description of work | Other factors to consider | Consignation | Water | Comp air | Vacuum | RP present
Bill Bannister EN/CV | 163495 | 8th Nov | 1 day | Hadron Stop | TNM42 electrical fault |  | N | N | N | N | 
Nicolas Perez EN/HE | 169285 | 8th Nov | 13:00-15:00 hrs | TT70 | Maintenance of lift AS104 | The lift will be out of service during this time. | N | N | N | N | N
Nicolas Perez EN/HE | 169285 | 7th Nov | 07:30-09:30 hrs | TT70 | Maintenance of lift AS514 | The lift will be out of service during this time. | N | N | N | N | N
Jeremie Bauche EN/MSC | 164332 | 8th Nov | ½ day | SPS | Tour of the SPS to inspect the magnets |  | N | N | N | N |