## Slide 1: Cryogenics Tender Schedule

## Slide 2: Sequence of operations
3 March 2016 : Discussion on the 4 P&IDs
8 April 2016 : Technical specification document delivered to the spec committee.
14 April 2016 : Review (=CERN spec committee) of the final tender technical specifications: 1 person per detector + CERN ATS experts + CERN HSE
22 April 2016 : Tender sent to the selected firms
22 April – 17 June 2016 : Firms prepare and send the answers to the CERN tender
20 June 2016 : Tender opening
24 June 2016 : Tender result delivery to CERN TE department
13 July 2016 : Documents ready for the CERN FC peer reviewers
19 July 2016 : Procurement documents delivered to CERN management for approval
14 September 2016 : CERN FC approval
19 September 2016 : LOI letter sent to the firm gaining the contract
30 September 2016 : Contract out