## Slide 1: WP10.2 – Status
L. Bottura
March 18th, 2016

## Slide 2: Tapes and cables
Three of four 100(+100) m orders in house and two delivered to KIT: SuperOX, Sunam, Fujikura (Amalia)
Restarted tape production at Bruker-HTS (Alexander)
Restarted cable production at KIT (Anna)

## Slide 3: What do we need to do ? Material
Need to complete the promised material production and delivery. From last records:
  Dummies: 40 m + 2x20 m (KIT/Bruker), note that this requires final Cu-coating – new demands ?
  Feather-0 lengths (4x6 m) – new demands ?
  Final cable lengths for AB (3x30 m) and CT winding (2x20 m) – new demands ?
Tape unit length: minimum 50 m, target 100 m
Magnet UL
  Aligned Blocks: 20 m (1.1 mm thick cable) to 28 m (0.9 mm thick cable)
  Cos Theta: 17 m (1.1 mm thick cable) to 21 m (0.9 mm thick cable)

## Slide 4: Tape lengths required for 1 magnet
Magnet | Tape thickness | Cable thickness | Tapes | Cable UL | Tape length
AB | 0.14 | 1.1 | 13 | 2x24 | 2x312
AB | 0.1 | 0.9 | 15 | 2x32 | 2x480
CT | 0.14 | 1.1 | 13 | 2x20 | 2x260
CT | 0.1 | 0.9 | 15 | 2x24 | 2x360
Minimum length of 0.14 mm tape for 1 magnet: 624 m + drop-out
Minimum length of 0.1 mm tape: 960 m + drop-out
EuCARD2 “contractual” quantity: 750 m of 0.14 mm tape from EU Beneficiary Bruker HTS
CERN has proposed to match with 750 m of 0.14 mm tape, and cover the 1000 m required of 0.1 mm tape

## Slide 5: What do we need to do ? Tests
Ic measurement on Roebel cables
  Two samples available at CERN
Transverse pressure experiment on Roebel cable
  KIT has produced cables, CERN provides insulation (Twente impregnates – training required)
  AC loss measurement and analysis: CERN to fabricate 2/3 new samples for inter-tape measurement/AC loss
  A final effort on striation? Discussion
Quench experiment
  KIT/Bruker delivered 2 mm tapes at Twente
  Cable test as final characterization ? Discussion
BSCCO cable test
  On hold given limited availability of OPHT furnace