## Slide 1: Measurement program at 100 MeV
A Lombardi

## Slide 2: LLRF – on behalf of PB
LLRF status , discussed/negotiated with Philippe Baudrenghien
  4 cards for amplitude control out of 7 in house. Some problem already identified probably need version 3 (cfr PB presentation on https://indico.cern.ch/event/492344/)
  6 april : 50 MeV recommissioned
  13 april : first 4 CCDTL equipped , probably a patch to make cards work
  25 april : all CCDTL modules equipped and upgraded

## Slide 3: 6-13 April: 50 MeV
Re-commission 50 MeV :
  Trasmission vs RFQ voltage
  Beam size in MEBT
  Bunchers phases/voltage
  DTL tank amplitude and phase
  Beam goes to the 100MeV dump except for low energy commissioning (chopper on)
  Need all instrumentation until 50 MeV + transformers on the Bench

## Slide 4: 13-24 april : 80 MeV
Turn on CCDTL modules 1-4 one by one
  Transmission vs phase
  Set phase and amplitudes
  Test CCDTL4 as debuncher (for proton mode)
  Estimate transverse emittance via quad scan
  Estimate longitudinal emittance via
  Beam goes permanently to the 100MeV dump)
  Need ToF, BSM, SEM grids wirescanner , Laser?

## Slide 5: 25 april –end : 105MeV
Turn on CCDTL modules 5-7 one by one , then PIMS1
  Transmission vs phase
  Set phase and amplitudes
  Estimate transverse emittance via quad scan
  Estimate longitudinal emittance via
Other tests :
  Laser tests ?
  ADAM ionisation chambers
  Timing tests ?
  Beam goes permanently to the 100MeV dump
  Need ToF, BSM, SEM grids wires,canner , Laser

## Slide 6: Preparation
Source caesiation – we will commission the 100MeV beam wit the source presently installed in the tunnel. New source in the test stand for validation from may
Beam permit : missing bunchers on the EIS chain?