## Slide 1: Review of baseline following the cost-reduction process of June 2016
L. Rossi
HL TCC 23 June 2016

## Slide 2: Reasons of the exercise -1
At the C&SR n.1 (March 2015) the WP17 (Infrastructure, Logistics and C.E.) was presented with a budgetary evalution of 170 MCHF:
    100 MCHF for C.E., 70 MCHF for the rest,
    10 MCHF for SM18 upgrade (managed by TE).
    Beginning of 2015 the evaluation of about 100 MCHF was agreed with CE group based on the lay-out of the time (for both options: surface-based and underground-based)
    In June 2015 the baseline was then changed to UG-option
    WP15 then worked with CE and all teams to define lay-out and amount of space.
    Based on needs and layout of November 2015 a substantial increase in cost estimate of about 55 MCHF was announced by CE, due to extra building surface and larger UG volume;
    Then an effort in UG volume reduction (13%) and of surface building (-11%) was more than offset by further increase in CE cost estimation, see next.

## Slide 3: Reasons of the exercise -2
On May 27, 2016 an internal WP17 C&SR was organized by L. Tavian (A. Ball, chair).
Presentation were well prepared, main outcome was.
    180 MCHF for C.E.
    110 MCHF for all other T.I and logistics.
An extra-cost of 120 MCHF to the 950 MCHF of CtC just approved for HL-LHC by Council of 15 June 2016 is not acceptable and could put in danger the project.
HL TCC of June 2: decision to launch a vigorous action :
  Reduction of the technical equipment (WP1-WP16), reducing also the needs of C.E. and remaining T.I. (otherwise the 120 MCHF must be absorbed all by technical equipment!).  minimizing performance reduction
  Meeting between HL and SMB management to define how to deal with the the two new 10 MCHF contracts being signed for HiLumi CE consultancy!
  Agreed 3 months max to redefine the new layout for CE  3 weeks to define the new baseline based on which the new CE layout is designed

## Slide 4: Scope redution criteria and procedure
Minimizing impact on perfomance, while optimizing lay-out: a crises is not only a nuisance, it may be turned into opportunity!
Drop the ultimate as a secondary target and concentrate on the nominal
  Llev of 51034 cm-2s-1 (140 P.U.)
  3000 fb-1 (  250 fb-1 /full year)
Possibly make de-scopings that could be recovered fully or partially later on (LS4, LS5…)
Two weeks of meetings with each single WPs (many multi-WPs).
Attendance: WP leaders with experts, GLs, HL, HL-PO
10 formal meetings in two weeks, many more informal and prepratory meetings.

## Slide 5: THANKS to all of you for the availability, the effort and the genuine project spirit and CERN-interest attitude.

## Slide 6: After 2015 C&SR, optimization and cost-reduction were ALREADY going on…
Decision for lamination in MQXF structure.
Reduction in operating current for Q4 (affecting WP6A/B)
One circuit for the triplet powering (affecting WP6A/B)
Protection via QH rather than EE, when possible.
Top of Q6 (P1 and P5) at 4.2 K (not 1.9K)
Avoiding doubling MQY magnet for Q5 in P6 by operating at 1.9 K instead of 4.2 K.
No 11 T dipole in DS around IP2 for ions (but confirming DS collimators in a new Connection Cryostat)
Reduction of SC link length following new UG baseline
Optimization of WP14
This has allowed to reduce cost of about 30 MCHF, however mostly offset by about 20 MCHF of other increase (mainly WP1, WP15 for personnel, WP4 for SPS test crises, more complex devices in WP8, new budget for the IT string)
 10 MCHF saving (and some potential volume reduction)

## Slide 7: Outcome of June 2016 «crises excercise» (Impact on performance: see G. Arduini)
Reduction of CC system from 4 to 2 cavities/ beam-side (1 CM/b-side)  16 CCs + 4 spares (8+2 CM). Impact on perfomance: visible but not dramatic
    Revision of the power/CC and volume of the power conv.
Staging installation of new MQYY as new Q4 (90 mm aperture) to after HL-LHC end (i.e in LS4), if needed, mantaining present 70 mm MQY, i.e. Q4 modified for 1.9 K operation.
    Small impact on baseline performance, more pronounced for flat beams).
QPS for the MQXF maintaining all systems (QHout, Qhinn, (Qhintr), and CLIQ) however with a minimal configuration with redundancy.

## Slide 8: Outcome of June 2016 «crises excercise» - cont. 2
Reduction of TCLD (DS collimator in P7 from 4 to 2 per side). This entails no 11 T for LS3. Reduction of TCTPM from 16+3 to 8+2.0
New integration layout for miniTAN of P8, more integrated with D2
New cryobox lay-out (with external distribution box)
Improved LSS vacuum layout (WP12) and partial manpower internalization via resource optimization.
Minimal reduction of Beam Diagnostics (WP13)
Modularity optimization of TCDS (WP14)
Powering the IPQs (Q6-Q5-Q4) from the RR, via existing EPCs, DFBLs (and links?)...

## Slide 9: Summary of saving WP1 to WP16 (HL CtC and HL Spares and Consolidation)
Exercise done in a hurry, may be some consequence forgotten, needs to check coherency and consolidate saving.
We already know from this morning that an important power cable has been missed (1-3 MCHF?). Other similar? TRANSPORT?
Uncertainty? +/- 5 MCHF
So our reference for the moment is that we found 70 MCHF, solidly.
We have been able to do so in a short time (TDR preparation, and reviews already done proved to be essential!!), without dramatic change of scope, no cut of approved R&D and studies and without loosing any of the project landmarks and technology innovation!!!

## Slide 10: See slides of G. Arduini on new performance estimate

## Slide 11: Rebaseline: impact on WP17 via WP15
Change proposal | Impact of CE
Installed ½ of crab-cavity | Reduction of the UA diameter or suppression of the UL Reduction of the UW volume Reduction of the SR surface Reduction of UR length Reduction of cooling the ventilation Reduction of electrical distribution
Powering of the Q4-Q5-Q6 from the RR | Reduction of the UR diameter Reduction of cooling and ventilation Reduction of electrical distribution
Integration of CLIQ in LHC UL | Reduction of UR diameter
Supply of demi water from LHC | Reduction of UW volume Reduction/suppression of SF building. Reduction of cooling and ventilation
Split of the cryo cold box (external diameter reduction and suppression of the second QXL) | Reduction of the UR diameter Reduction of the shaft diameter

## Slide 12: CE cost saving
CE changes | CE impact [MCHF] | 
 | Min | Max
Reduction of the UA diameter from 6 m to 5 m |  | 
Suppression of the UL |  | 
Reduction of the UR diameter from 7 m to 6-6.3 m |  | 
Reduction of the UR length 4 to 8 m |  | 
reduction of the UW/US volume by 10-20 % |  | 
Reduction of the shaft diameter from 10.2 m to 9.7 m |  | 
Reduction of the SR surface by 30 % |  | 
Reduction of SF building (12 MW to 8 MW) 16 % surface |  | 
Suppression of SF building |  | 
Total % of CtC |  | 

## Slide 13: CV cost saving
CV changes | CV impact [MCHF] | 
 | Min | Max
Reduction of ventilation |  | 
Reduction of cooling (CC rebaseline) |  | 
Reduction of cooling (Q4-Q5-Q6 from LHC) |  | 
Reduction of cooling (UA-UR from LHC) |  | 
Total % of CtC |  | 

## Slide 14: EL cost saving
EL changes | CV impact [MCHF] | 
 | Min | Max
Reduction of electrical distribution (CC rebaseline) |  | 
Reduction of electrical distribution (Q4-Q5-Q6 from LHC) |  | 
Reduction of DC cables (Q4-Q5-Q6 from LHC) |  | 
Reduction of electrical distribution (demi from LHC) |  | 
Total % of CtC |  | 

## Slide 15: How to proceed
The TCC will examine the technical and performance impact as well the Coherency.
We see if we can increse the saving a little bit (but no exaggeration…): the HL PO will continue to discuss with WPLs & GLs to consolidate budget and ventilate few further cuts in a reasonable way.
Freeze all changes and ask each WP to write a short document as basis for the C&SR II, followed by mandatory ECR.
A new version of the project description will be issued, to be validated by CERN management (as usual).
WP15 and WP17 will work hard to provide the new basis for CE (and all T.I.) to evaluate saving also in WP17.
We need to save 120 MCHF to keep CtC at 950!! Job is not over, however now the technical challenges can re-take their place in our project!

## Slide 16: Ad astra per aspera Thanks a lot