## Slide 1: Startup of linacs - Analysis
D. Küchler

## Slide 2: Linac2
start-up interrupted several times due to power tests
  schedule of linac start-up not taken into account at TI
detection of vacuum leak at tank1 had to be paused over the weekend as there were no operators in the CCC to give access
  operator schedule

## Slide 3: Linac3
WIC refurbishment delayed start of the beam in the LEBT
  insufficient communication (scope of the renovation was unclear) + misinterpretation of the schedule
non-conformities delayed installations or made installation impossible
  insufficient integration drawings + insufficient checks in the workshop + production delays
some beam instrumentation at the end of the YETS still not ready to be installed
  lack of man power