## Slide 1: ALICE & LHCb LS2: PLANNING
Arturo Tauro
Eric Thomas
On behalf of ALICE and LHCb Collaborations

## Slide 2
LHCb & ALICE
major upgrade
ATLAS & CMS
major upgrade
Phase II
LHCb detector
consolidation & improvement
2 ¼ years left
ATLAS & CMS
Phase I upgrade
2 Years

## Slide 3
ALICE & LHCb upgrades
Notes: We have two years for preparations and two years for installation of the ALICE upgrade.
Most subsystems go into production phase early 2017.

## Slide 4
Motivation: Focus on high-precision measurements of rare probes at low pT
  Cannot be selected by hardware trigger
  Need to record large sample of events
Goal: Pb-Pb recorded luminosity ≥ 10 nb-1, (plus pp and p-Pb data)
  8 x 1010 events to gain a factor 100 in statistics over the Run1+Run2 programme
Strategy:
Read out all Pb-Pb interactions at a maximum rate of 50kHz (i.e. L = 6x1027 cm-1s-1) upon a minimum bias trigger
Perform online data reduction based on reconstruction of clusters and tracks
Improve vertexing and tracking at low pT
 New Inner Tracking System (ITS)
ALICE, LS2 upgrade scope
Notes: We have two years for preparations and two years for installation of the ALICE upgrade.
Most subsystems go into production phase early 2017.

## Slide 5
ALICE, LS2 upgrade scope
New Inner Tracking System (ITS)
improved pointing precision
less material  thinnest tracker at the LHC
Time Projection Chamber (TPC)
new GEM technology for readout chambers
continuous readout
faster readout electronics
MUON Arm
continuous readout electronics
Muon Forward Tracker (MFT)
new Si tracker
Improved MUON pointing precision
New Online/Offline computing farm (O2)
new architecture
on line tracking & data compression
50kHz PbPb event rate
TOF, TRD
Faster readout
New Trigger Detectors (FIT)

## Slide 6
The ALICE Upgrade, 5 TDRs
  Silicon Inner Tracking System (ITS) upgrade
  Time Projection Chamber (TPC) readout chamber upgrade
  Muon Forward Tracker (MFT)
  Upgraded readout for all detectors to cope with the higher rate (SAMPA, CRU) Upgraded Central Trigger Processor Upgraded Fast Interaction Trigger (FIT) based on Quartz+MCP & Scintillator New Radiation requirements
  Upgraded Online-Offline (O2) system to handle the continuous readout at 50kHz PbPb collisions and reconstruction
Notes: We have two years for preparations and two years for installation of the ALICE upgrade.
Most subsystems go into production phase early 2017.

## Slide 7: The way to LS2
LS2
Preparation
LS2 preparations since end LS1
LS2 duration: 102 working weeks (2 weeks in Dec 2018 and 2x50 weeks in 2019-20)

## Slide 8: LS2 preparation

## Slide 9: New central beampipe 1/2
OD 38 mm
ID 36.4 mm
 | Present beampipe | LS2 beampipe
Outer diameter | 60mm | 38mm (only central part)
Wall thickness | 800um | 800um
Length | 482cm | 550cm
Beryllium length | 395cm | 88.8cm
Bellows/flanges | SS | Al
Nb. of supports | 3 | 3
New ALICE beampipe geometry officially approved in September 2014 LMC

## Slide 10: New central beampipe 2/2
Engineering design completed (now under approval)
Order
Delivery to ALICE
Delivery to VSC
Installation in ALICE
> one year contingency
18 months

## Slide 11: New O2 data centre at P2 (CR0) If no data centre in Prevessin
EL and CV infrastructure
MDC delivery
Example of MDC
CR0 location at P2
EL infrastructure
CR0 ready
Noise simulation done and put as requirement in ITT

## Slide 12: Optical fibers 1/2
19’920 links, 145 trunk cables
Architecture and technology selected: trunk cables 144F & MPO
CERN offer received in May (EN-EL), other suppliers contacted
Synergy with LHCb
4U Patch Panel
MPO-MPO
Trunk cable 100-150mt
MPO-MPO
MPO-MPO
Patch-cord
MPO-LC
Patch-cord
DET.
4U Patch Panel
MPO-MPO
CRU
Cavern CR1

## Slide 13: Optical fibers 2/2
Cable-trays CR1-UX + validate prototype
Purchase
fibers
Installation of fibers CR1 to SXL2 cleanroom and CR0-CR1
Installation and test of fibers CR1-UX
TPC re-installation

## Slide 14: Cleanrooms
June 17’: TPC cleanroom (ISO7)
ITS cleanroom (B.167)
A
D
B
C
Zone A (Assembly hall)
Zone B (Insertion Test)
Zone C (Counting Room& Cooling Plant)
Zone D (Control Room)

## Slide 15: LS2 schedule

## Slide 16: LS2 schedule
One shift/day
‘Long’ days foreseen for transport tasks
24h/24 for few specific tasks (e.g. TPC RO tests)
Sep-Dec (15 weeks)
Recommissioning
2
  Mar-Dec (40 weeks)
  TPC upgrade
3
  Dec-Aug (37 weeks)
  Reinstall TPC/ITS/MFT/FIT/beampipe + close Experiment
1
  Dec-Feb (10 weeks)
  Open Experiment + TPC/ITS/beampipe de-installation

## Slide 17: Open Experiment + TPC/ITS/beampipe de-installation
 | Duration
Open cavern, L3 doors, comp.magnet/miniframe | 3.5
Remove ITS & beampipe | 5.5
Bring TPC to cleanroom | 1
 | Total: 10 weeks
ITS
Miniframe
TPC
Key resources: transport, P2 technicians, ITS and TPC groups

## Slide 18: TPC upgrade
 | Duration
Remove electronics and services | 5
Swap chambers | 8
Survey and align chambers and end plates | 3
Sealing, T sensor installation and leak test | 4
Reinstall electronics | 8
Readout test | 7
Close sectors | 1
Contingency | 4
 | Total: 40 weeks
ISO5 tent
MWPC installation (photo 2006)
Yellow platform and installation jig

## Slide 19: Reinstall TPC/ITS/MFT/FIT/beampipe + close Experiment
 | Duration
Reinstall TPC | 3
Install ITS cage and new beampipe (incl.bakeout) | 6
Reinstall miniframe | 2
Install & commissioning MFT/FIT/ITS | 18
MFT/FIT/ITS commissioning, close L3 doors and cavern | 8
 | Total: 37 weeks
MFT
ITS
Resources:
Survey and transport
P2 technicians
TE-VSC (beampipe)

## Slide 20: Other activities: detectors
Uninstall all 4 PHOS modules (fix FEE/TRU cards)
Install 2 CPV modules
These interventions imply to de-install also the 3 A-side DCal modules
CPV installation (LS1)
DCal
PHOS
CPV
In parallel to TPC upgrade

## Slide 21: Other activities: services
Miniframe modification (PP0 and PP1)
TPC/ITS/MFT/FIT cables
Remove all cables from C-side (absorber area)
New ITS/MFT water cooling plants (incl. new lines)
New ITS ventilation duct
Optical fibers
Miniframe
PP0
PP1
Key resources:
Dedicated FSU team coordinated by ALICE TC
Outside companies (e.g. new inox pipes)
CERN cabling and scaffolding contracts (EL, EA)
CERN EN-CV and EN-EL
In parallel to TPC upgrade

## Slide 22: Detailed LS2 schedule

## Slide 23: Conclusions
Well on track with LS2 preparations, as we started since end of LS1
New beampipe will be ordered before end of the year. More than one year contingency before installation in ALICE
Fibers will be installed in 2019, cable-trays in place already during upcoming EYETS
LS2 schedule: TPC upgrade and ITS installation must be done in sequence for obvious reasons
Dedicated FSU team for services modifications. Lot of support needed from CERN service groups (transport, survey and safety coordination) and cabling (and scaffolding) contracts!
Four months foreseen for global ALICE re-commissioning at the end of LS2

## Slide 24: LHCb Upgrade parameters
To cope with the enormous increase of events to be evaluated, a larger CPU farm will be unavoidable. As space and cooling/power capacities are limited in the UX, a new ‘Data Center’ at the surface is in planning.
Luminosity
Run2 4 x 1032 cm-2 s-1 (2 x nominal)
->Upgrade: 2 x 1033 cm-2 s-1 (10 x nominal)
(Triggerless) Read-out
Run 2 1 MHz
 Upgrade 40 MHz
Increasing the read out to 40 MHz and the higher luminosity necessitates replacing all front-end electronics and the majority of detector systems.
LHCb is a high precision experiment devoted to the search for new physics beyond the Standard Model by studying CP violation and rare decays

## Slide 25
RICH1 Shielding
RICH2 box, mirrors
ECAL HCAL MUON
(but NOT r/o electronics)
What stays in place?
New detectors and r/o electronics
New r/o electronics

## Slide 26: LS2 preparation

## Slide 27: Detector assembling facilities at P8
SX8
b. 3852
SX8
SX8
SX8
b. 3852
b. 3852
b. 3852

## Slide 28: Data Centre (2MW) – Optical links (15k)
LS1:
Trays installed
Install 2x144 TEST fibres trunk cables FROM UX to SX
Validation of installation technique
Mini test data centre at surface
Test & validate DAQ chain
Option: Data Centre at P8 or Prevessin

## Slide 29: Services
CO2 transfer lines (VELO-UT cooling)
Cooling plants, pipes, optical links, copper cables: specs, design, integration, procurement and installation

## Slide 30: LS2 schedule: 3 phase
2
  Sept19-Jul20
  Install detectors services
3
  Jul20 Nov20
  close Experiment
  Survey
  Recommissioning
1
  Dec19-Aug19
  Open Experiment +
  Dismantling
3
2
1

## Slide 31: LS2 phase 1: Dismantling / Detectors
Open detectors
Dismantle beam pipe
Dismantle detectors and services
Extra constraints
Working detector environment
Radio Protection overhead
  Protection of personnel – risk assessment prior to any destructive work
  Logistic – waste sorting – waste disposal

## Slide 32
LS2 phase 1: Dismantling / services

## Slide 33
Detector assembling in surface facilities
(SciFi, UT, VELO)
Tests & Survey
Descent and installation in the pit
LS2 phase 2: Detectors Installation
R. Wallet
R. Wallet

## Slide 34
Most critical path: strong correlations between
UT
RICH1
VELO
BEAM PIPE
Stringent constraints on installation sequence
LS2 phase 2: Detectors Installation

## Slide 35: Phase 3 Closure & commissioning
Final connection between detectors and services
Beam Pipe installation and Bake-out (section 2-4)
Closing LHCb detectors
Final survey and alignment of detectors
Commissioning
Expected end date for Installation work: Nov 2020

## Slide 36: Planning: simplified schedule

## Slide 37: Conclusion
EN – Engineering dpt.
    Survey (detector assembly and positioning)
    EL (power, copper cables, optical links)
    CV (Detector and Data Center Cooling)
    Handling,
    Safety Coordination,
    EA support
    …
TE – Technology dpt.
    Vacuum Chamber operation
    …
HSE – Radioprotection
    Radioprotection
    …
Tight schedule
The current planning does not foresee any contingency
Delays will be absorbed by shift work or week-ends
The success relies on strong involvement of participating Institutes and CERN: