## Slide 1: Recommendations of previous reviews
J.Ph. Tock (TE-MSC)
International Review of the Inner Triplet Quadruples (MQXF) for HL-LHC

## Slide 2: Which reviews ?
Hi-Lumi-LHC/LARP International Review of the Superconducting Cables for the HL-LHC Inner Triplet Quadrupoles (MQXF) [5-6 November 2014]
Arnaud Devred, ITER-IO (Chairman)
Herman ten Kate, CERN
David Larbalestier, NHMFL
Bruce Strauss, DoE
Akira Yamamoto, KEK.
HL-LHC/LARP International Review of Inner Triplet Quadruples (MQXF) Design [10-12 December 2014]
Joe Minervini (MIT, Co-Chair),
Jim Kerby (ANL),
Shlomo Caspi (LBNL),
Alexander Zlobin (Femilab),
Akira Yamamoto (KEK-CERN, Chair)

## Slide 3: Margins (1/2)
The design goals need to be conservative because Nb3Sn accelerator magnet technology is still experimental, and impregnated Nb3Sn coils operated at 1.9 K are prone to self-field instabilities. (A)
Maximizing the operating margin of the superconductor by all means possible, such as lowering the nominal gradient, increasing the magnet length in an appropriate balance of the magnet reliability with achievable integrated luminosity, revisiting the Cu-to-non-Cu ratio, and so on (A)
Some optimization of IR optics and magnet parameters is needed to reduce the risk of magnet production and LHC operation. Increase MQXF operation margin by setting the magnet nominal operation current to be 75%, lowering from 80%, of the magnet short sample limit (SSL) along the load-line (LL). This can be realized by extending the magnet length and by lowering the peak field. The space for the extension should be available because of a major space saving realized by using the superconducting magnet, D1, located after the Inner Triplet. (B)
Further optimization should be given in the short model program to demonstrate appropriate margin, [including addressing the issues listed above] (B)
Included in the design,
Several presentations

## Slide 4: Margins (2/2)
The relationship of superconductor properties to magnet performance has not been clearly defined, making a realistic definition of the margin for the magnet unclear. (A)
The new constraints of Nb3Sn in magnets need to be much better understood and a more pragmatic and suitable operating margin defined that would include: cabling degradation, self-field instabilities, stress degradation, and so on. (A)

## Slide 5: QA/QC of the superconductors (1/2)
Development is necessary of an integrated qualification plan, from virgin and extracted strand tests, to local and full-size cable tests, to magnet model and prototype tests to validate conductor and magnet designs and to assess operating margins; the qualification tests should be the same for both LARP and Hi-Lumi (A)
A convincing QA/QC plan and inspections procedures in writing must be finalized during the upcoming model and prototype phase. It shall be reviewed before launching of wire and cables series production contracts (A)
It is recommended to split the series productions in several phases to enable establishment of control limits of statistical process control (SPC). (A)
Promote the development of in-line video quality control of cable, in particular at the thin edge to see out of range local strand damage, as this presently is the only technique that will enable 100% inspection of the cable unit lengths. (A)
Better identify qualification tests and series production tests (A)
On-going
See presentations by L Cooley, B Bordini & J Fleiter

## Slide 6: QA/QC of the superconductors (2/2)
Better integrate the QC plan on virgin wires, extracted strands, local measurements and full-size cable tests to ensure consistency and suitable monitoring of wire and cable productions. (A)
A requirement on strand cleanliness and surface conditions during transport, cabling and temporary storage, especially for bare OFHC copper strands that are prone to difficult to control oxidation effects, is required. This may have consequences for finding predictable electrical properties between strands and resin wetting and binding quality during impregnation (A)
Clarification of the scheme for approval of unit lengths originating from certain billets. Excessive number of breakages during the processing of a billet may be a sign of hidden defects or insufficient homogeneity which cannot be discovered when unit length approval is not referred to billets. (A)
The present are the technical specifications of the conductor, all of which are challenging and ones not yet being met in production strands (strand Ic: 361 A at 4.2 K and 15 T / RRR: 150 on virgin strand/100 on extracted strand). The allowable values of Ra and Rc in the cables need to be addressed (A)
For series productions: all acceptance tests should have clear criteria. The acceptance test requirements and criteria should be identical for both LARP and Hi-Lumi. (A)
On-going
See presentations by L Cooley, B Bordini & J Fleiter

## Slide 7: Nb3Sn - RRP
It is recommended to go ahead with the 132/169 and lower Sn content layout as proposed by OST. A final decision on strand layout can be made in one year for the series production contract (back up being the 108/127 layout) (A)
Seriously consider the proposal to reduce cable keystone angle from 0.55 deg to 0.4 deg in view of the effort to increase margin and reduce risk, however, the committee does not consider it as a show stopper if for good schedule and procurement reasons the LARP part of the project decides to stay with 0.55 deg (A)
A parallel effort to continue optimization of heat treatment is recommended (A)
Applied : See especially presentations by L Cooley, B Bordini & J Fleiter
108/127 is the present baseline
Keystone angle changed to 0.4 deg
Work in progress

## Slide 8: Nb3Sn - PIT
In the meantime, CERN should go ahead with RRP strands and cabling for its model magnet production and should optimize phasing of strand and cable deliveries between RRP and PIT in order to create maximum flexibility for using the best possible PIT wire and coping with delivery delays. (A)
PIT cable has not yet met the Ic requirements. (B)
In support of the above, define a clear timeline for the decision making process regarding PIT wire development and production (A)
Reducing the cable keystone angle in the PIT based cables from 0.55 deg to 0.4 deg is a must in order to avoid unnecessary performance risk. (A)
The coil cross-section is being corrected for use of PIT cable. (B)
Prepare for an alternate design with the Nb3Sn cable, using a smaller keystone angle, as it was proposed by the SCD team/section and encouraged in the previous superconductor and cable review, particularly when using strand prepared via the PIT process, to ensure availability of superconductor from multiple vendors. In the production stage, it would be preferable to have the same coil design, using cable with a small keystone angle, for both the RRP and PIT strands. (B)
On-going : See especially presentations by L Cooley, B Bordini & J Fleiter

## Slide 9: Second supplier of superconductor
If one supplier shows less maturity in their wire production, more resources shall be allocated to foster its development or industrialization. (A)
In view of the crucial 2-supplyer policy at CERN that is essential for this project and beyond, the panel highly recommends a substantive support program for the PIT wire to further optimize strand properties and establish performance baseline for series production. (A)

## Slide 10: Risk mitigations (1/2)
To limit schedule risks and to allow corrective actions in an efficient and cost-efficient way, clearly defined decision points between the phases of the R&D model, the first prototype and construction programs shall be developed in the USA and at CERN. (A)
It is vital to clearly identify risks, such as failure of a wire supplier or cabling machine, so as to enable realistic risk mitigation measures, such as transfer of wire procurement to the other supplier, or arranging a back-up cabling machine. (A)
Since the project apparently shows a significant risk for serious delay in wire procurement and coil manufacturing because of the volume of wire orders and number of coils to be made; also a plan B covering the case of partial completion has to be addressed in the case goals of magnet production are not met on time for installation in the tunnel. (A)
On-going : See especially presentations by L Cooley, B Bordini & J Fleiter

## Slide 11: Risk mitigations (2/2)
Keep a backup option for the Q2A/B magnet length, currently 6.8m, to be a half that length, because as yet there is no experience with a Nb3Sn accelerator magnet of length greater than 5 m. This may be important also from the viewpoint of the design with regard to quenching, due to the choice of a small Cu stabilizer ratio (Cu/no-Cu ratio of 1.2). (B)
The current schedule is tight, even though less tighter than the 11 T dipole program, in order to meet the plan to install the MQXF during the LS3 currently planned in 2023 - 2024. No failures are assumed in the current model work, and reasonable redundancy needs to be considered. For example, additional coil winding with a level of 15 %, already considered, should be well taken into account in the nominal schedule. (B)
Contingency plans need to be developed to hold the schedule, and to be included in the general project plan. (B)
Plan for expanding/strengthening the production and test facilities at HL-LHC/LARP laboratories involved in this program. It is critically important and imperative that they will be completed and available on time. (B)
For discussion during the restricted session on “Production” ; Many information during talks and visits

## Slide 12: Magnet specifications
Magnet acceptance parameters need to be formulated and included in the specifications. (B)
The interfaces across work packages need to be well defined and integrated into the specifications. (B)
With respect to component manufacturing tolerances, the committee recommends to take into account the tolerances achieved during the fabrication of the US-LARP HQ magnet which could allow for some relaxation of the tolerances and potential cost savings. (B)
The thermal analysis needs to include sensitivity to heat load variation due to uncertainty with beam absorber design and parameters. (B)
The coil insulation need to be sufficiently radiation hard against to the radiation dose to be integrated. It should be carefully confirmed in comparison with the coil insulation using “glass+mica tape” planned in the 11 Tesla magnet program in the same HL-LHC program. (B)
Overall safety issues with respect to design and inspection should be confirmed as soon as possible. (B)
Development of alignment specifications and the overall scheme should start soon (B)
The two full-scale prototype program, at least, is necessary to ensure the performance reproducible. (B)
Each MQXF model work, whether by US-LARP or CERN, should have a clear list of design and performance goals, in addition to the clear objectives of each model and prototype program, in order to determine a credible level of the performance of production magnets. (B)
Work in progress

## Slide 13: Magnet (cold) tests
Test (train) all the production magnets up to 110% of the nominal operating current at the pre-installation test on the surface, as already considered in the design, in order to ensure the quench and mechanical margins and redundancy for long term operation. Thermal cycling tests should also be performed during the surface test to insure the magnets have good training memory after the thermal cycling. (B)
See presentations by M Bajko, J Muratore, G Chlachidze

## Slide 14: Quench protection
The quench protection analysis should include the voltage distribution during quench in the nominal and heater failure scenario, and the cryostat quench protection analysis. (B)
The inner-layer and inter-layer heater concepts needs to be critically evaluated including their impact on magnet production and operation risks. (B)
More work should be done on establishing a reliable quench protection system. The CLIQ scheme should be implemented in addition to the regular protection system using heaters, in order to provide redundancy (B)
See especially presentation by G Ambrosio

## Slide 15: Design
The cable expansion during reaction needs to be further understood and implemented in coil cross-section design. (B)
The coil preload level needs to be coordinated with the ultimate design gradient. (B)
Design credibility may be enhanced by using common tools: especially in magnetic and structural design and analysis, thermal modeling, powering, and quench protection. (B)
See especially presentations by P. Ferracin and G Vallone

## Slide 16: Cryomagnet reliability and replacement in-situ
The procedure of the magnet replacement under high radiation environment should be well established in the design stage, and it should include fixtures, tools, and remote handling, transportation, and the time scale which impacts on the machine availability, resulting in an effect on integrated luminosity. (B)
The time-period and work-flow sequence in case of a failure and necessary repair work should be well established. It is especially important to take into account that MQXF replacement work is not easy under the high-radiation and confined environment in the tunnel. (B)
The loss of integrated luminosity in such incident should be well evaluated and justified with the information shared among the relevant groups and persons. (B)
The MQXF program, together with the 11T dipole program, is a critical proof of Nb3Sn magnet technology for high-energy accelerators. The reliable and stable operation of the MQXF magnets has to be the primary design and construction issue, because these magnets are to be operated in a demanding high radiation environment with very limited accessibility after the installation into the LHC-IR regions. For this reason, reliability and stable operation must be properly addressed during design and construction (B)
Taken into account but not yet mature to be presented

## Slide 17: Conclusions
Hope this will be useful inventory for this review
…. But also for the next ones.
A long term review process with the same committed committee would be beneficial to the project.
Status update
Some redundancy so some recommendations can be combined/reformulated
Looking forward for your feedback
    Thank you for your attention