## Slide 1: International Review of the Inner Triplet Quadrupoles (MQXF) for HL-LHC Review Panel Report for the Close-out (Draft)
10 June, 2016
MQXF Review Panel
Arnaud Devred (ITER), Pasquale Fabbricatore (INFN), Mauricio de Lima Lopes (FNAL),
Joe Minervini (MIT, Co-Chair), Pierre Vedrine (CEA), and
Akira Yamamoto (KEK-CERN, Chair)

## Slide 2: Introduction
HL-LHC is in the final stage of design and prototyping: all technologies for the hardware upgrade must be fully proven by beginning of 2017.
This review covers the cornerstone of the upgrade plan, the new IR quadrupoles (MQXF), featuring 150 mm aperture and peak field in the range of 11.5 T.
The previous technical reviews addressed the conductor, the preliminary design, including the engineering concepts and the cost and schedule (within the overall scope of HL-LHC) ), and further progress (model work achievement and prototype/production plan) has been reviewed.

## Slide 3: Scope of this Review
To examine:
The magnet requirements and design status, including the cold mass with its interfaces (cryostats, electrical, hydraulic, mechanical, vacuum) and integration issues (cold mass and integration will be assessed at the level of preliminary design stage);
The major design alternatives considered (conductor, aperture, length, operating temperature, etc.);
The results of model magnets (including previous smaller aperture ones) and the status of prototype magnets;

## Slide 4: Scope of this Review (cont.)
The conductor performance, procurement status and plans;
The status of production tooling, finalization of design and procurement;
The components’ procurement, status and plans;
The test plan, QA/QC, and safety aspects;
The strategy for magnet construction and/or procurement and the overall schedule (assuming the US contribution for Q1 and Q3 magnets);
The risk registry and mitigation measures.

## Slide 5: Agenda
To be filled

## Slide 6: Executive Summary (I)
The HL-LHC/LARP international review of Inner Triplet Quadrupole (MQXF) for HL-LHC was held at CERN on 7 – 10 June, 2016.
The MQXF program, together with the 11T dipole program, is a critical proof of Nb3Sn magnet technology for high-energy accelerators. The reliable and stable operation of the MQXF magnets has to be the primary design and construction goal.

## Slide 7: Executive Summary (II)
The committee received 33 reports on the recent technical progress in the MQXF design and R&D efforts for model works and preparation for the prototype/production magnets integrated in cooperation between the US-LARP and CERN. The reports also described the project plan and schedule to meet the requirement for the MQXF magnets to be developed and ready for operation in the HL-LHC project, after the LS3 in 2024-2026.
The committee congratulates the team on the progress achieved in the MQXF design and R&D work, in particular for the model magnets successfully accomplished. We recognize the excellent teamwork, between CERN and US-LARP, and the significant roles and contributions made by young scientists and engineers to ensure the future project success.

## Slide 8: Executive Summary (III)
The committee supports the current/baseline magnet design which is based on the bladder and key technology with an aperture of 150 mm, developed in the US and transferred to CERN. This has been demonstrated by several successful short models.
The committee is pleased to receive the report for the magnet design which reflects the advice given with the previous review. Recent tests have demonstrated the effectiveness of the decision to lower the nominal operation current from 80 to 75%, of the magnet short sample limit along the load-line.
The critical issue for the scale up for the long magnet (4m) will be addressed in the coming months.

## Slide 9: Executive Summary (IV)
The presented protection scheme relies on quench heaters and CLIQ units. The committee supports the proposed solution which seems sufficiently robust and compatible with the operation constraints. He also supports the on-going developments but suggest to define a milestone in the MQXF roadmap where the final quench protection configuration for the series will be decided.
The committee assesses that the specifications for both RRP and PIT wires are suitable for MQXF needs and strongly recommends to freeze all parameters and manufacturing processes for both suppliers.

## Slide 10: Executive Summary (V)
The presented schedule shows sequential and continuous activities from prototypes to mass production. The committee suggests to consider a readiness review before starting the mass production.
Plan for expanding/strengthening the production and test facilities at HL-LHC and US-LARP/AUP laboratories involved in this program. It is critically important and imperative that they will be completed and available on time.

## Slide 11: Executive Summary (VI)
CERN should consider the involvement of the industry for the series production. The scale of this project is ideal to help introduce industry to Nb3Sn accelerator magnets technology in view of future projects.
Efforts should be made for harmonizing safety, QA/QC, procurement between CERN and US-LARP/AUP.

## Slide 12: Questions/Responses to/from the Review Panel

## Slide 13: Are the magnet requirements in-line with the HL-LHC requests? Are they realistic/achievable with sufficient margin ?
A: The short models have demonstrated that the HL-LHC requirements can be met. Of course the final demonstration is demanded to the results on prototypes. It is noticeable the present capability to predict the field quality, allowing a very good controls of each multipole.
Facts and Findings :
Documents were circulated regarding the magnet specifications fulfilling the HL-LHC requirements. A field quality table has been shown, with values of multipoles coming from the design and from error analysis. These values are acceptable for the beam dynamics and are considered target values rather than specified values.

## Slide 14
The construction of short models has shown that the target field quality can be achieved. But some deviations of few units for geometrical b3, a3, a4 and b5 have been found. Clear solution have been found for b3, a3 and a4. For b5 (order of 2.5 units) an hypothesis is being investigated about the displacements in coil cross sections generating large high order harmonics.

## Slide 15
Comments:
The definition of a field quality table on the basis of target values, rather than specified values, seems to be sound for these challenging triplet magnets.
The present B5 multipole seems clearly related to a displacement (0.5 mm) of some blocks due to the Nb3Sn conductor growth during the heat treatment. In this case a large decrease of B5 can be expected by taking care of this aspect during the construction.

## Slide 16
Recommendations:
The High Order Harmonics are not clear defined and they are, at present time, a target specification. We recommend to have two sets of specifications the “threshold specification” that must be met and the “objective specification” that should be the target for the performance.

## Slide 17: Have design alternatives been considered ? Are they correctly managed ?
A: Yes, alternatives have been considered and properly managed.
Comments:
The basic bladders and keys technology involved in the triplet lay-out has been developed for many years in the framework of the LARP collaboration and this technology is approaching maturity.
Many alternative technologies such as the one based on coil collaring were studied. The bladder and key has been selected as the best one.
Presently the options still under study are limited to quench protection-related issues such as heater lay-out and the feasibility of CLIQ. For this specific case a solution should be chosen as soon as possible.

## Slide 18
Recommendation
For the quench protection a solution should be chosen as soon as possible.

## Slide 19
Is the present and future models programme providing sufficient information ? If not what else could be necessary/useful ? Have all necessary analyses been done ? What further tests/analysis would you recommend ? Does the overall plan allow to acquire the necessary experience with the models and prototypes before engaging in the production phase ?
A: Yes, see comments and recommendations.
Facts and Findings
Due to the change in the in the conductor keystone angle from 0.55 to 0.4 there are now two generations of conductor and therefore two generations of short model coils.

## Slide 20
CERN built 1 Cu, 1 low-grade RRP, 3 RRP, 2 PIT coils using the first generation conductor geometry. 3 RRP coils were built using the second generation and 2 PIT coils are underway for the same generation.
LARP has produced 6 RRP coils using 1st generation cable and 1 RRP for the 2nd generation. Another RRP 2nd gen is under way.
Three LARP and two CERN short coils were successfully tested.
Some differences were report between LARP and CERN with respect to coil fabrication techniques, in particular the post instrumentation.
Three mechanical models were build and tested at 77K. Two others were built using laminated structure; one tested at 77 K and the other has been shipped to US to be assembled in MQXFS4.

## Slide 21
MQFS1M was a mirror quadrupole successfully test in May 2015
MQFS1 was a complete quadrupole made out of 2 LARP coils and 2 CERN coils. Test completed in April 2016. This magnet will be re-tested (then MQFS1b) with increased pre-load.
MQXFS2 will be used to test non-conformity coils of first generation cable and it is schedule to be tested at the end of calendar year 2016.
MQXFS3 will be used to test coils produced with second generation cable formed by 3 CERN coils and 1 LARP coil. The test is schedule for summer 2016.
Two other short models will be produced using 2nd generation conductor and they will be tested in Q1 of 2017 and 2018.

## Slide 22
The present plans foresee the construction of two long (7.15 m) prototypes at CERN (first autumn 2018 and second on summer 2019) and three long prototypes (one 4m and two 4.2 m) in USA.
CERN is considering the construction of a mirror magnet before the construction of the two prototypes.
The first LARP prototype (spring 2017) involves one coil of first generation and three of the second generation. This prototype, of slightly reduced length with respect the nominal one, is not suitable to be integrated into a cold mass. The second prototype magnet (2017-2018) is made of 4.2 m coils of the second generation and is not yet involving thin laminated yoke. A third prototype magnet (early 2019) is foreseen reusing first prototype structure and, for the first time, thin laminations. This third prototype is not yet funded.

## Slide 23
Comments:
CERN and LARP collaboration experience with Nb3Sn since 2003 allowed the development of what is now a matured technology for the LHC high luminosity upgrades.
The short models are successfully demonstrating the technology choices and they also provide the possibility of fine tuning those technologies choices.
The bladders and keys technology has been fully demonstrated for short models and should be assessed in next months for long magnet (4m). The critical issues are related to the assembly of long structures, the use of thin laminations and the achievement of the required alignments
The scale-up to 7.15m is even more challenging and the occurrence of possible issues should be considered.

## Slide 24
If a third prototype magnet is not coming from USA collaborators (for budget restrictions), a prototype cold mass of Q1/Q3 cannot be composed.
Provided that a full cold mass with two long prototype magnets can be provided by LARP, this component together the two prototypes of Q2 being constructed at CERN constitute a solid basis before engaging the production phase. The time plan for completing this task appears however optimistic not considering the intrinsic risks of a scale-up process.
Given the tight schedule and the related risks for prototype developments at CERN, it appears not obvious the construction of a mirror magnet. The main risk here is to concentrate on the mirror issues, which could differ from the real magnet issues.

## Slide 25
Recommendations :
The committee supports the construction of a third prototype (4.2 m long) within LARP activities as a fundamental step for finalizing a complete cold mass of Q1/Q3. To this aim it is important that the two magnets of the cold mass involve similar structures; consequently thin lamination should be used in the second prototype as well.
Add contingency in the planning for the long prototypes being developed at CERN due to the possible difficulties arising from the scale-up by a factor two in the magnet length.
The committee recommends to CERN to carefully re-evaluate, if the mirror prototype be beneficial and effective.

## Slide 26
The presented schedule shows sequential and continuous activities from prototypes to mass production. The committee suggests to hold a readiness review before the starting of the mass production both at CERN and in USA.

## Slide 27
Is the conductor strand and cable production advancing adequately ?
Does the production meet the specification (Ic, RRR, degradation, geometry, stability, unit length,…) ?
Is the conductor and cable production QA/QC plan sufficiently developed and answering the needs ?
A: Yes. See comments and recommendations.
Strand
Findings and comments
9 x 108/127 RRP billets and 6 x bundle barrier PIT billets have been produced and measured and meet all technical requirements, incl. IC, RRR and filament diameter.
The IC spec for PIT wire is 6% lower than for RRP wire at 12 T, but is comparable at 15%.

## Slide 28
There was a raw material issue at the RRP strand supplier which resulted in a delivery delay to CERN, that will be compensated by the use of PIT wires.
Both CERN and US are ready to place contracts for series production.
The committee acknowledges the excellent results obtained on both RRP and PIT wires and, in particular, notes that it is the first time that consistent results are obtained for PIT, indicating that the process may have reached maturity.
The committee assesses that both CERN and US/AUP are ready to launch their series production contracts.
The committee re-emphasizes the need for 2 strand suppliers in order to mitigate production and schedule risks.

## Slide 29
Recommendations
The committee assesses that the specifications for both RRP and PIT wires are suitable for MQXF needs and strongly recommends to freeze all parameters and manufacturing processes for both suppliers
The committee recommends to reinforce the requirements for strand supplier qualification, including the production of full-length cable unit lengths successfully tested in a model magnet.

## Slide 30
Cable
Findings and comments
The cable keystone angle has been reduced from 0.55 to 0.4 for both RRP and PIT, resulting in an Ic degradation below 4% and RRR of extracted strands above 100.
CERN has developed and implemented a new on-line cable edges deformation system.
CERN is confident that it has sufficient production capability to cope with all productions, with a contingency for recovering delays in case of long shutdowns.
The committee acknowledges the good results achieved for both types of strands with the reduced keystone angle and assesses that the present cable specifications are suitable for MQXF needs.

## Slide 31
Recommendations
The committee recommends, for each type of cables, to introduce a process qualification unit length to validate and freeze all manufacturing parameters and processes to be used for series production.
The committee recommends to clarify and formalize the business flows for control point clearance during cabling operations.
The committee re–emphasizes the criticality of the cabling equipment and, as recommended during the 11 T dipole review, encourages CERN and US/AUP to develop common risk mitigation strategies in case of long shut down of one of the facilities.

## Slide 32
Production QA/QC
Facts and Findings
CERN and US/LARP-AUP presented their QC plans for both strand and cables.
The plan appears to differ both in terms of tests and in terms of the testing rates to be applied during production.
Comment:
Both CERN and LARP/AUP presented production schedule for strand and cables with suitable lead times with respect to needed dates.
It has been shown a complete plan for the QC and QA for the conductor that includes the automatic video recording of the SC cable and several dimensional checks. However, the insulation of this cable will be outsourced to a vendor.

## Slide 33
The conductor can be damaged during the handling of this conductor by the vendor, for instance during handling or re-spooling operations, and the insulation will mask this potential defects.
Recommendation
The committee strongly recommends that CERN and US partners agree on a common, minimum set of QC tests and QC testing rates to be applied to their respective productions; this should in particular be the case for the strand supplier they have in common.
In case one of the two cannot comply with this minimum requirement for schedule or cost reasons, the committee strongly recommends that the other reduces the amount of extra tests it is carrying out and compensate for this lack.

## Slide 34
The review committee recommends that special attention should be paid during the insulation to assure that the cable will not be damaged during this process.

## Slide 35
Is the protection scheme presented sufficiently robust and compatible with operation constraints ? If not, what should be developed or modified ?
A: Yes.
Findings and comments
The quench protection plan has been extensively studied and relies on no energy system extraction, quench heaters, CLIQ units and voltage taps for detection.
Quench heaters system appears to be well developed. The system relies on outer layer quench heaters for protection & some redundancy and inner layer quench heaters for redundancy and to limit the hot spot temperature.
Use of IL QH reduces the coil to ground voltage but the CLIQ system increases the mid-plane voltage between coils up to 500 V.

## Slide 36
Tests and simulations have demonstrated that MQXF magnets can be protected using outer layer heaters. In nominal conditions, with only the outer quench heater system, the peak temperature reaches 320 K. Outer layer quench heater are very reliable and survived large number of quenches.
Different scenarios for peak temperatures and voltages have been studied. Additional redundancy can be provided by inner Layer heaters and/or CLIQ
360 K peak temperature has been calculated in case of failure scenario with only outer quench heaters. Use of IL QH and/or CLIQ reduces hot spot temperature by 100 K
Coupling-Loss Induced Quench system (CLIQ) has been successfully tested on Nb3Sn short models and NbTi long magnets and a conceptual design study has been made for MQXF and further investigations are under development.

## Slide 37
A good agreement has been obtained between measurements and simulations for OL QH but not for IL QH (epoxy layer control is more difficult). Bubbles appear on the inner layer quench heaters after extensive quench campaigns

## Slide 38
Recommendations:
Hot spot temperatures appears to be “at the limits” in some failure scenario. The committee recommends to clearly define the design criteria for maximum hot spot temperatures and voltage limits in the coils.
The committee recommends to continue the development of the three quench protection solutions as the baseline but suggest also to define a milestone in the MQXF schedule with the decision to include or not the IL QH and/or CLIQ system for the series?
The committee recommends enough redundancy for the voltage taps for protection.

## Slide 39
Considering that work is on-going, is the cryostat and equipment integration development status in line with the overall progress of the project ? Are there critical missing information ?
A: Yes. The design level is appropriate for this stage of conceptual design.

## Slide 40
Are the production facilities adequate? Is the tooling development appropriate wrt the overall project ?
A: Yes at this early stage of prototyping. Further developments will be required for the series production.
Comments
The production facilities for long coils and magnets both in US and at CERN have been shown in detail in 4 presentations. Moreover the committee has had the opportunity of a specific visit to the building 180.
The general impression is that the procured or under procurement tools for the triplet construction is adequate for guarantee a high quality of the magnets. The technical staffs are enthusiastic, of high level and have been trained by the models developments.

## Slide 41
Are all procurement aspects (conductor, collared coils, cold mass, cryostat,…), including QC adequately covered ? If not, what is missing or should be reinforced ?
A: Yes for the conductor. See comments and recommendations for the rest.
Is the production scenario in a maturity stage compatible with the overall project ? Are the mitigations measures of technical, cost and schedule risks adequate ?
A: Not completely. US plan is mature but the funding profile is not suitable to meet the required schedule; CERN plans needs to be optimized. See comments and recommendations.

## Slide 42
Comments
A relevant aspect of the production scenario is the degree of occupancy of the tooling involved in the construction. This information was given for both CERN and US facilities. For CERN facility it appears that the occupancy of some tooling (reaction oven and impregnation tool) if practically 100%, whilst a much lower occupancy fraction is recommended for being sure to respect the schedule. Also considering the intrinsic contingency (10% on the number of coils), it is advisable to take some adequate measure for mitigating the risks wrt the schedule.

## Slide 43
Recommendations
For the US portion of the Risk Registry, the present stage shows to be adequate. The committee recommends the inclusion of “shortage of resources”. This should be entered once in each major fabrication step.
CERN should consider the involvement of the industry for the series production. The scale of this project is ideal to help introduce industry to Nb3Sn accelerator magnets technology in view of future projects.

## Slide 44
Is safety level acceptable? Are there critical areas?
A: Yes.
Findings and comments
CERN safety policy for the project has been presented and is convincing. Its impact on the MQXF magnet design is being evaluated between project team and CERN-HSE in particular for the Pressure Equipment Directive (PED).

## Slide 45
CERN Safety rules are based on regulations, directives and standards of the European Union. For cases not covered by CERN Safety Rules, the regulation applicable in the competent Host State is used.
MQXF cold mass assembly must comply with CERN’s Launch Safety Agreement (LSA) for IR Magnets (WP3) which contains a list of applicable rules, codes and standards which currently are being discussed with US HL-LHC-AUP. LSA describes also the minimal contents of the Work Package safety file needed to meet the Safety Requirements.
Compliance with applicable Essential Safety Requirements from PED is compulsory. No CE marking or ASME stamp is expected as part of the U.S. deliverable

## Slide 46
Harmonized European standards are used wherever applicable (presumption of conformity) for design, manufacturing and testing.
Foreign standards may be used provided compliance with ESRs is fully demonstrated. ASME code mainly covers all the ESR required by PED. An equivalent procedure have been demonstrated for the delivery of the crab cavity.
Eventual non-compliances will be assessed individually by HSE. In that case the project shall propose compensatory measures to ensure commensurate level of Safety.
Assessment of conformity to the ESRs will be carried out by CERN-HSE acting as an ‘independent’ party and involvement of external Notified body is not required. This is also applicable to the US-LARP deliverables.

## Slide 47
Pressure vessel requirements are needed by US HL-LHC-AUP before a couple of months to fully estimate the efforts needed to fulfil PED and to agree on the exact terms of these requirements. This is a potential cost and schedule driver for the U.S. project, we need soon.
US HL-LHC-AUP deliverables shall fulfil ASME requirements to be able to be tested at Fermilab
In case of a material provided by CERN to US HL-LHC-AUP is not completely fulfilling ASME requirements, for example for the low cobalt stainless steel or 316 LN steel, Fermilab Director has the authority to accept deviations.

## Slide 48
MQXF magnet requirements are almost complete except High Voltage Withstand levels. Discharge test voltages have still to be defined by the High Voltage Withstand Levels WG. The impact on the design is not completely finalized

## Slide 49
Recommendations:
The committee recommends to define as soon as possible the CERN’s Launch Safety Agreement (LSA) for IR Magnets (WP3) and assess the impact of the ESRs on the helium vessel design, materials specification, and test procedure in order to come to a good consensus between CERN-HSE, HL-LHC and US HL-LHC-AUP.
The committee recommends to define as soon as possible discharge test voltages to assess their impact on the MQXF design.

## Slide 50
Are the recommendations from the previous reviews adequately followed(-up) ?
A: Yes.
Are CERN and US HL-LHC AUP activities well integrated ? Are the interfaces well managed ? Is the work sharing efficient in terms of cost, schedule and risks mitigation ?
A: Generally yes at this stage. Better integration is expected for the series production.

## Slide 51
Is the project on good tracks to fully prove the necessary technologies for the MQXF for beginning of 2017 ? What are the critical areas ?
A: Yes on a good track but not completely. Some topics still need to be addressed on short models and prototypes.
Is the overall plan allowing to meet the challenges of the HL-LHC project ? Is it clear, realistic and coherent ?
A: Yes on a good track but it requires consolidation.
Findings and Comments:
The different schedules presented during the review are not always coherent. Recommend to present a unique and consistent schedule between CERN and LARP with the appropriate assumptions.
Is the inherent level of risk acceptable ? Are mitigations measures adequate ?
Finding / Comment
Risks management for the project should be centralized at CERN with a risk register followed by the MQXF project leader

## Slide 52
The production schedule with a minimum acceptable float of 6-months is not supported by the current DOE funding profile guidance. The US HL-LHC funding profile is driving today the critical path of the project.

## Slide 53: Are test facilities (including the IT String) adequate and timely?
Response:
Yes, extensive test facilities are ready or under preparation at both CERN and in the US.
Summary for CERN
At CERN extensive renovations and upgrades are either completed, in progress, or in planning.
The present vertical cryostats are not long enough to handle a 7m long magnet and no new ones are planned to do vertical testing although Cluster G is being upgraded to include a 4th cryostat (30 kA @ 1.9 K, 800 mm x 4.8 m long). This is long enough to test the short model magnets for Q2 and will be ready this summer (2016).
A new pit has been completed and a new 25 overhead crane added.
The long prototypes and eventual series production magnets will be tested in the horizontal test stands (Clusters A-F, 10 available) but 2 clusters will be upgraded to 4.2 K and 1. 9 K, Max. current: 20 kA, 2x 2 kA .
  Extensive upgrades include more water flow, larger DCCT (20 kA), and a refurbished current lead, new power supplies for CLIQ and other uses.
  Cluster A ready in 2017, Cluster F ready in 2020.
Other improvements include a new control room in 2016 and increased cryogenic refrigeration capacity in 2019.
A very thorough test plan and test sequencing schedule has been developed indicating facilities should be ready to handle the prototype magnets and series production magnets when required by the project schedule. The test planning is not on the critical path.
A string test is planned. Facility is named HL-LHC IT STRING and will be located in SM18 This will follow prior experience with an LHC string test and improvements based on those results. It will be operational 2020-2022 and have full capabilities to test the magnets to 18 kA at 1.9 K and 4.2 K. All subsidiary power and refrigeration equipment will be ready .
It will include a superconducting link and be able to test the complete string or only partial string depending on the availability of the QX magnets in the schedule.

## Slide 54
Summary for US LARP
In the US, vertical tests of Q1/Q3 magnet cold masses will be tested at BNL.
Preparations and equipment and system upgrades are being performed or planned to be able to test the magnets as they become available.
  A 30 kA PS has been reconfigured for 24 kA and new IGBT switches and energy extraction system installed. The EE may be required depending on the final selection for the quench protection methods (QH and/or CLIQ).
  A 4.2 m useful depth vertical test dewar is designed . This includes a new top plate with 24 kA vapor-cooled leads, new Lhe vessel, new 4.5 K thermal shield, new lambda plate for 1.8 K operation, heat exchanger, and water-cooled power cables.
The committee members thought that, because of the limited length of the dewar, the lambda plate was too close to the bottom of the VCL’s leaving only a very short length for 4.2 K Lhe in the upper chamber. The problem could be either very high heat leak and helium consumption, or inability to establish a superfluid volume below the lambda plate.
There are two very large helium refrigeration systems at BNL that are ~40 years old. But the BNL administration has self-funded an impressive amount of upgrades in almost all cryogenic system components, including expansion engines, compressors, diagnostic and monitoring instrumentation with PLC, purifier, etc. the DAQ and data loggers and software are also new.
The systems have been operated are functioning very well.
The committee commends BNL management for their internal funded support of this project through these facility upgrades, backup system, critical spares, and preventative maintenance.
Note that horizontal tests of the Q1/Q2 magnets will be done at FNAL using a reusable cryostat (present baseline). The cryostat is still be designed and fabricated.

## Slide 55
Recommendations
When the vertical test dewar is ready for commissioning use a dummy load mass similar to the MQXF magnets, and operate the cryogenic system to measure the ability to cool down to 1.9K, to maintain adequate helium levels, and to measure the actual boil-off rate. VCL’s should be in place for this test. If the system does not perform as planned determine the maximum duration for completing a full set of magnet qualification tests including one thermal cycle.
Refrigeration and power supply equipment is presently available at FNAL but the VCL’s should be upgraded to at least 18kA.
The review committee recommends to consider that the horizontal test of the cold mass should be done using the final cryostat provided by CERN instead of a reusable one.

## Slide 56: Schedule: Design and Manufacturing Process Consolidation
Findings and comments
Due to cost and time constraints, the present plan calls for a limited number of model magnets and full-scale prototypes for both performance and process qualifications.
These “nominally” identical magnets and prototypes have already a number of variants built-in (e.g., PIT vs. RRP strands, different braiding types, different manufacturing processes at CERN and in the US).

## Slide 57
The committee acknowledges the time and cost constraints of the project, but wishes to stress that Nb3Sn accelerator magnet technology is still very novel and that design features and manufacturing processes need to be thoroughly qualified to ensure suitable and durable operation in the machine.
Recommendations
Limit the number of variants implemented in the model magnets and prototype programs; it also strongly recommends to identify the issues that still need to be resolved and to develop a comprehensive roadmap on how they will be addressed in the model magnets and prototypes manufactured on both sides of the Atlantic.

## Slide 58
Re-assess whether the number of model magnets and prototypes presently foreseen is sufficient to fulfil the roadmap; if not, the committee recommends to develop a plan on how to address the remaining issues in a timely fashion with respect to series production.

## Slide 59: Schedule: Prototyping
Findings and comments
The teams at CERN and in the US exhibit a high degree of confidence and optimism, based on extensive and comprehensive analyses and the success of the model magnet programs, that the scale up to full-length prototypes will be successful.
The schedule developed by CERN and the US both assume a success-oriented prototype program, with little float or contingency in case of problems.
The committee is very impressed by the quality and quantity of the work and by the enthusiasm of the staff involved in the program on both sides of the Atlantic, but wishes to issue a word of caution, that the scale-up of manufacturing processes (such as coil production or key and bladder implementation) may offer more challenges than initially anticipated and result in delays in the finalization of prototype manufacturing and testing.
Recommendantion
The committee recommends to anticipate such situation and to start developing recovery scenarios.

## Slide 60: Schedule: Series Production at CERN
Findings and comments
CERN has carried out a detailed analysis of the resources (tooling and manpower), duration and, to some extent, of the risks associated with each process and is developing a consolidated schedule for 11 T and MQXF prototyping and series productions.
The present need dates for LS2 and LS3 can only be met with the existing facilities at CERN by assuming occupancy rates for several work stations that are beyond reasonable.
The committee acknowledges the CERN efforts to develop a consolidated schedule for both 11 T and MQXF programs which was a request of the 11 T dipole review .
The committee emphasizes that the on-time delivery of the 11 T magnets for LS2 should be the number 1 priority of CERN.
The committee recommends to use 70% as an upper limit for the occupancy rate of critical work stations such as heat treatment furnace and vacuum impregnation and to develop risk mitigation strategies in case one of these equipment is out of order for several months during production.

## Slide 61
Recommendations
Develop and implement strategies for industrial involvement during series production so as to maintain industrial interest and know-how in view of future programs.
Study the pros and cons of at least 3 different scenarios for alleviating the schedule risks on series production:
  Extending the present MQXF assembly line at CERN by upgrading the critical work stations and/or optimizing their usage
  Subcontracting part or all of the MQXF scope, to an industrial partner, with installation of an assembly line at the industrial partner premises
  Subcontracting part or all of the MQXF scope, to an industrial partner, with installation of a second assembly line on the CERN partner premises (this sentence to be revised)

## Slide 62: Schedule: Series Production in US
Findings and comments
US LARP/AUP has developed a very comprehensive and solid schedule for prototyping and series production based on a detailed and credible analysis of the resources (tooling and manpower), duration and risks associated with each process.
The present schedule has little or negative float with respect to CERN need dates and appears to be constrained by the funding profile over FY 17 through FY 19, that is well below the project needs, while it exceeds the project needs over the remaining years and the overall funding is adequate.
The committee commends the US team for its very thorough efforts; the schedule basis appears sound and the applied contingency level appropriate.
Recommendations
Create a suitable float of at least 6 months with respect to the CERN need dates and to limit the schedule risks by correcting the funding profile over the next 3 years to complete prototyping in a timely fashion and to enable a faster production ramp up.

## Slide 63: Acknowledgments
We would thanks everyone’s effort and contribution to the review successfully made, and we would express our sincere thank to your warmest hospitality during the review.
We wish further successful progress in the MQXF program in close cooperation between the HL-LHC and US LARP/AUP project teams.