## Slide 1: Linac4-PSB 160 MeV connection readiness review
Tuesday 30th August
https://indico.cern.ch/event/548092
Reviewers: Enrico Cennini, Paul Collier, Katy Foraz, Mike Lamont (Chair), Roberto Losito, Jose Miguel Jimenez, Heinz Vincke
With due acknowledgement to Malika, Giovanni and team…

## Slide 2: Aims of review
Derive a comprehensive plan to execute the Linac4 to the PSB connection for 160 MeV operation.
Review all details of the plan, disseminate information, and make sure nothing is forgotten or overlooked.
Estimate how long is needed from the "go-ahead" signal to the first beam operation.
List the associated risks.
Clarify what should be completed prior the ‘go-ahead’.
What could be the earliest go-head time ?

## Slide 3: Initiation of plan
Serious incident in the LHC, requiring of order 6 months to repair and re- hardware commission.
NOT a Linac2 failure scenario
  which, as of today, could be replaced by Linac4 within a couple weeks to produce 50 MeV protons

## Slide 4: Boundary conditions
Full 160 MeV connection
  Including H- injection
PSB to 1.4 GeV
  Not energy upgrade
Beams to reproduce today’s beams
  Not LIU targets
Would run under these condition until LS2 when the full LIU upgrade could be completed.

## Slide 5: In particular 1/2
Review the readiness of the Linac4-PSB connection for the full 160 MeV connection
Covering:
  all accelerators/transfer line equipment (incl. electronics and controls)
  power/controls cables and electrical infrastructure
  cooling and ventilation
  building, civil engineering
  transport equipment
  access system/doors
  machine protection/interlock systems
  operation, controls/software,
  safety files, procedures (DSO tests…)
  layout, drawings, database, documentation…

## Slide 6: In particular 2/2
Review the full connection planning and assess the risks
Covering:
  essential preparation activities (cool-down, …)
  decommissioning and removal of old equipment (incl. storage conditions)
  infrastructure changes (de-cabling …)
  equipment installation, survey, controls
  individual system tests and HWC (incl. access conditions…)
  beam commissioning and operational ramp up
  overall connection planning
  risk analysis

## Slide 7: Deliverable - beam
User | Kinetic energy swing (GeV) | Intensity (1010 p/ring) | ex (mm) | ey (mm)
LHCPROBE | 0.16 – 1.4 | <1 | <1 | <1
LHCINDIV |  | 10 – 50 | 1 – 2 | 1 – 2
LHC25 |  | 170 | 2.0 | 2.0
LHC_BCMS |  | 90 | 1.1 | 1.1
ISOGPS(HRS) |  | 900 | 12 | 8
STAGISO |  | 200 – 350 | 5 | 4
TOF |  | 900 | 12 | 8
AD |  | 400 | 9 | 5
SFTPRO_MTE |  | <600 | 6 – 8 | <4
EAST1 and 2 |  | <50 | 1 – 2 | 1 – 2
These are the current beams produced at the PSB
New kinetic energy swing 160 MeV to 1.4 GeV (NB no 2 GeV)
Giovanni Rumolo

## Slide 8: Beam
User | Kinetic energy swing (GeV) | Intensity (1010 p/ring) | ex (mm) | ey (mm)
LHC25 | 0.16 – 1.4 | 170 | 1.5 | 1.5
LHC_BCMS |  | 90 | 1.1 | 1.1
ISOGPS(HRS) |  | <1200 | <9 | <5
With Linac4, beams in the PSB can be potentially produced with transverse emittances lower by a factor ~2 than nowadays
Potential reach for ISOLDE beams and LHC beams, as discussed in LIU-PSB Injection WG meetings (J. Abelleira et al.) and RLIUP Workshop (G. Rumolo et al.) are given in this table
  Due to space charge in the PS, we would target anyway:
    Only 50% gain of the total potential gain for the standard 25 ns beams
    No gain for the BCMS beams
  ISOLDE beams will still be limited to values below 1.2e13 p/ring due to RF power (and Linac4 current?)
Giovanni Rumolo

## Slide 9: Program
Session 1: Setting the scene
  Aims
  Layout overview, list of equipment, list of associated services – Julie Coupard
Session 2: Linac4 and LIU status
  Linac4 (incl. source) – Alessandra Lombardi
  LIU-PSB 160 MeV (incl. HST) – Klaus Hanke
Session 3: Equipment status (Linac4 and LIU-PSB)
  TE/ABT, EPC, MPE, VSC, MSC, BE/BI, RF, EN/STI
Session 4: Services status (Linac4 and LIU-PSB)
  EN/EL (2 talks), CV (invited, no talk), HE, SMB/SE, BE/ISC, BE/CO
Session 5: Installation and commissioning (Linac4 and LIU-PSB)
  Safety – Christelle Gaignant
  Timeline for dismantling/installation/survey – Julie Coupard
  HW commissioning – Bettina Mikulec
  Beam commissioning- Vincenzo Forte
  Risks analysis / spares situation – Brennan Goddard
Session 6:
  Wrap-up and next steps – Review team