## Slide 2: Linac4-PSB 160 MeV connection readiness review
Tuesday 30 August 2016

## Slide 3: TE-MSC
Antony Newborough
Table of Contents:
Equipment dismantling
Equipment installation
Risks / Mitigation
Additional information
Summary

## Slide 4: Equipment dismantling
System | Equipment | Estimated activation | Cooldown requested + duration | Particular requests for removal | Storage / Waste | DEC Done | Updates needed | Group ressource | Remarks | ECR/SRR EDMS
 |  |  |  |  |  |  | Database / Integration / Controls … |  |  | 
LBE.QFW.10 | Magnet | 1µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 
LBE.QDW.10 | Magnet | 1µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 
LBE.DHV.10 | Magnet | 1µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 
LBE Vacuum |  |  |  |  |  |  |  |  |  | 
LBE Magnet interlock |  |  |  |  |  |  |  |  |  | 
LBE Supports |  |  |  |  |  |  |  |  |  | 
BI.DHZ.DVT10 | Magnet | 5µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.DHZ.DVT20 | Magnet | 5µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.DHZ.DVT30 | Magnet | 5µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.DHZ.DVT40 | Magnet | 315µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
Bi(1:4).DHZ.DVT50 | Magnet | 60µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI(1:4).DHZ.DVT70 | Magnet | 240µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI Corrector Magnet Interlock |  |  |  |  |  |  |  |  |  | 
BI Corrector Vacuum |  |  |  |  |  |  |  |  |  | 
BI.BVT10 | Magnet | 162µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
Magnet Interlock |  |  |  |  |  |  |  |  |  | 
Vacuum |  |  |  |  |  |  |  |  |  | 
BR.BHZ11 | Magnet | 2000µSv/40cm | 6wks | Transport to Workshop: to be fitted with new vacuum chamber + minor mods |  | NA | Database / Integration / | MNC |  | 1422358
BR.BHZ162 | Magnet | 240µSv/40cm | 6wks | Magnet Storage | Storage | NA | Database / Integration / | MNC |  | 1422358
BR Vacuum |  |  |  |  |  |  |  |  |  | 
BI.QNO10 | Magnet | 236µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.QNO20 | Magnet | 310µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.QNO30 | Magnet | 92µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI.QNO40 | Magnet | 350µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI(1:4).QNO50 | Magnet | 60µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI(1:4).QNO60 | Magnet | 60µSv/40cm | 6wks | Buffer Zone | Waste | ? | Database / Integration / | MNC |  | 1494503
BI Quadrupole Interlock |  |  |  |  |  |  |  |  |  | 
BI Quadrupole Vacuum |  |  |  |  |  |  |  |  |  | 
Considering dose rate could be performed <6wks cooldown
First Out – Last In?
Changed for Consolidation reasons, not directly linked to L4 connection
Changed for Consolidation reasons, not directly linked to L4 connection

## Slide 5: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
LINAC 4 and L4T Magnets | Magnets | 56 | Y | Installed |  |  |  |  |  |  |  | Y | 4 | 4 days / tunnels |  | MNC |  | Available | Magnets already installed and some commisoned. Additional tests required.
LT.BHZ20 | Magnet | 1 | Y | 16 | Transport / Lifting | Existing |  | 1083362 | Other info: | EN / EL |  | Y | 2 | 2 days / tunnel |  | MNC |  | 1 | Coils from the installed magnet will be installed on a new yoke to become dedicated spare
 | Vacuum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Interlock |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Powering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
The new BHZ 20 magnet delivered 2015

## Slide 6: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
LBE.QFW.0015 | Magnet | 1 | Y | 4 | Transport / Lifting |  |  | 1054490 | Other info: | EN / EL |  | Y | 0.10 | 0.5 days / tunnel |  | MNC | ABP | 4 | 
LBE.QDW.0020 | Magnet | 1 | Y | 4 | Transport / Lifting |  |  | 1054490 | Other info: | EN / EL |  | Y | 0.10 |  |  | MNC | ABP |  | 
LBE.DHV.0010 | Magnet | 1 | Y | 4 | Transport / Lifting |  |  | 1165034 | Other info: | EN / EL |  | Y | 0.10 |  |  | MNC | ABP | 1 | 
LBE Vacuum | Vacuum |  | TBC by VSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LBE Magnet interlock | Interlock |  | TBC by MPE (WIC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LBE Magnet Powering | Powering |  | EPC responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LBE Supports | Supports |  | ABP responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L4 type magnets available in storage

## Slide 7: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
BI.DHZ.DVT10 | Magnet | 1 | Y | 8 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.1 | 1 day / tunnel |  | MNC | 1494503 | 2 | Magnet replaced for consolidation purposes, linked to the replacement of the power converter for the other corrector magnets
BI.DHZ.DVT20 | Magnet | 1 | Y | 8 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.1 |  |  | MNC | 1494503 |  | 
BI.DHZ.DVT30 | Magnet | 1 | Y | 8 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.1 |  |  | MNC | 1494503 |  | 
BI.DHZ.DVT40 | Magnet | 1 | Y | 8 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.1 |  |  | MNC | 1494503 |  | 
Bi(1:4).DHZ.DVT50 | Magnet | 4 | Y | 16 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.3 |  |  | MNC | 1494503 |  | Required for L4 – Supports to be ordered in coming weeks
BI(1:4).DHZ.DVT70 | Magnet | 4 | Y | 16 | Transport / Lifting |  |  | 1277962 | Other info: | EN / EL |  | Y | 0.3 |  |  | MNC | 1494503 |  | 
BI Corrector Magnet Interlock | Interlock | 24 | TBC by MPE (WIC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BI Corrector Vacuum | Vacuum | 12 | TBC by VSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BI Corrector Powering | Powering | 24 | EPC responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22 corrector magnets delivered and tested

## Slide 8: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
BI.BVT10 | Magnet | 1 | Y | 16 | Transport / Lifting | Existing |  | 1188530 | Other info: | EN/EL |  | Y | 1 | 0.5 days / tunnel |  | MNC | 1494503 | 1 | 
 | Interlock | 4 | TBC by MPE (WIC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Vacuum | 4 | TBC by VSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Powering | 3 | EPC responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
first Magnet delivered to CERN – measurements and a few modification still to be made.
The spare magnet to follow by the end of the year.

## Slide 9: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
BR.BHZ11 | Magnet | 1 | Other information: If required the spare BHZ magnet can be used however it is the only non-radioactive spare which is destined to become the new reference magnet for 2 GeV, the ideal solution would be to remove and modify the existing magnet | 16 | Transport / Lifting | Existing |  |  | Other info: | NA |  | Y | 1 | 0.5 day / tunnel |  | MNC | 1422358 | 0 | A dedicated spare will become available for 2 GeV, in the meantime a repair would need to be made for which all components exist.
BR.BHZ162 | Magnet | 1 | Other information: If required the spare BHZ magnet can be used however it will need to be exchanged again for 2 GeV operation | 16 | Transport / Lifting | Existing |  |  | Other info: | NA |  | Y | 1.00 | 0.5 day / tunnel |  | MNC | 1422358 | 1 | A new dedicated spare will become available for 2 GeV, the existing magnets will need to be upgraded for 2 GeV operation.
 | Vacuum |  | Other information: TBC by VSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10: Equipment installation
System | Equipment | Quantity | Readiness by December 2016 | Installation duration (in hours) | Specific EN/HE Installation requests | Cooling and Ventilation requests |  |  | EN/EL needs |  | Controls needs (FESA, BIS, Expert) | Individual System Tests |  | HW commissioning duration + Access condition | Beam commisionning duration | Group ressource | EDMS ECR / SRR Number | Number of spares | Remarks
 |  |  |  |  |  | Water cooling | Ventilation requests | Functional Specification / Engineering Specification Number | DIC Done | Other information |  |  |  |  |  |  |  |  | 
BI.QNO10 | Magnet | 1 | N | 8 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.10 | 1 day / tunnel |  | MNC | 1494503 | 2 | Magnets replaced for consolidation purposes, linked to the replacement of the power converter for the corrector magnets
BI.QNO20 | Magnet | 1 | N | 8 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.10 |  |  | MNC | 1494503 |  | 
BI.QNO30 | Magnet | 1 | N | 8 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.10 |  |  | MNC | 1494503 |  | 
BI.QNO40 | Magnet | 1 | N | 8 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.10 |  |  | MNC | 1494503 |  | 
BI(1:4).QNO50 | Magnet | 4 | N | 16 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.30 |  |  | MNC | 1494503 |  | 
BI(1:4).QNO60 | Magnet | 4 | N | 16 | Transport / Lifting |  |  | 1297809 | Other info: | EN/EL |  | Y | 0.30 |  |  | MNC | 1494503 |  | 
BI Quadrupole Powering | Powering | 12 | Other information: TBC by EPC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BI Quadrupole Interlock | Interlock | 12 | Other information: TBC by MPE (WIC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BI Quadrupole Vacuum | Vacuum | 12 | Other information: VSC responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series magnet expected in the coming weeks

## Slide 11: Risks / Mitigation
Proven technology - low risk

## Slide 12: Additional information
Strong interdependences with other groups?
  TE-EPC
  TE-VSC
  TE-MPE
  EN-HE
  EN-EL
  EN-ACE
Manpower: FSU team available. Additional resources have already been requested for connection during LS2 to help cover the work in the other areas of the PS complex

## Slide 13: Summary
All of the magnets required for the connection of the L4 to the PSB are available at CERN. Some support structures still need to be ordered.
The main PSB BHZ magnets need modification for L4 connection and 2 GeV.
The BI quadrupoles (cons.) should be available by the end of 2017.