## Slide 1: HL-LHC IT STRING
M. Bajko CERN
for TCC 15th September 2016

## Slide 2: Outline of the presentation
WP16 in the HL-LHC Structure and IT STRING Scope
Brief return to the past
Experience with LHC Triplet
Relevance of HL-LHC IT String
ID Card
Main facilities of the IT String
Organization of the work
Limitations and solutions in space
Limitations and solutions in time
Status of the work

## Slide 3: The HL-LHC IT STRING in the organigram
[…] THE WP16 covers the coordination of the commissioning of the HL-LHC equipment as part of the accelerator system. […] The first important system test will be the Inner Triplet (IT) STRING test.
The IT STRING should comprises all magnets with their cold and warm powering and associated cryogenics systems from Q1 to D1 magnets including DFX. […] The IT STRING will have conditions as similar as possible to the operational ones and will constitute an integration and system test of the most critical part of the upgrade.
Ref. HL_WP16 Conceptual specification : https://edms.cern.ch/document/1586706/1
Ref. HL_WP16 IT STRING Mandate: https://edms.cern.ch/document/1513780/1

## Slide 4: The HL-LHC IT STRING SCOPE
INTRODUCTION
In the HL-LHC configuration, the Inner Triplet (IT) region of IR1 and IR5 of the present LHC will be heavily modified. In particular the Q1-Q2-Q3-D1 magnets will be completely different from the present LHC magnets, mainly due to the new technology they are based. In particular the
D1 magnet will be superconductor instead of normal conductors as is today in the LHC. The IT quadrupoles (Q1-Q3) will use Nb3Sn superconductors instead of the Nb-Ti used by the present ones.
The powering of the magnets will be with higher current than the present LHC IR magnets and will be made via a superconducting link. The protection of the magnets based on Nb3Sn superconductor technology will be different from the present ones (ex. Cliq and new QH) due to its particulate characteristics at low and medium field and the high magnetic energy stored in the magnets in operational conditions.
In addition, the aperture will be much larger, the cold mass configuration will be completely different and the corrector package will be substantially modified as configuration and technology, too.
[…]
MAIN GOAL
The HL LHC IT STRING will be a test stand to STUDY and VALIDATE the COLLECTIVE BEHAVIOURE of the different systems: magnets, magnet protection, cryogenics for magnets and superconducting link, magnet powering, vacuum, and interconnections between magnets and superconducting link, alignment.
Ref. HL-LHC IT STRING Scope https://edms.cern.ch/document/1693312/1

## Slide 5: System architecture WP16
IT STRING
Magnets Cryostats and Connections (MSC)
Cold Powering System (MSC)
Warm powering system (EPC)
Magnet Protection System (MPE)
DAQ
Vacuum (VAC)
Utilities
Design and Integration
Cryogenic System (CRG)
Cryogenic Cooling
Cryogenic Distribution
Controls Instrumentation and Software
Magnets (Q1,Q2A,Q2B,Q3,CP,D1)
DFH
Magnet Interconnects
Controls Instrumentation and Software
Measuring Systems
SC Link
Current leads (DFX)
Control Instrumentation and Software
Power Converters (EPC)
Warm Power Distribution (EL)
Control Instrumentation and Software
Protection Heater Supplies
Cliq System
Energy Extraction
PIC
Control Instrumentation and Software
Hardware
Control, Instrumentation and Software
Civil Engineering ( GS)
Network (Including Wfip)
Demineralized Water ( EN CV)
Water Cooled Cables (EN EL)
Survey System (EN ACE)
Transport and Handling EN-E)
Control Room( TE-MSC)
Safety (HSE,HL LHC)
https://edms.cern.ch/document/1690890/1.0

## Slide 6: Previous experience - past
In the past STRINGs tests were run for
SSC
Hera
Tevatron,
RHIC and
LHC
DESY
Magnet string tests
A 36 metre chain of superconductive­ magnets built for the HERA electron-proton collider has been under test since April at DESY in Hamburg. The magnet string is composed of three full-sized prototype dipole magnets (with coils made at DESY and mounted in cryostats at BBC-Mannheim) and two quadrupoles
(made at Saclay).
[..] It has been quenched more than 20 times at magnetic fields between 1.8 and 5.8 tesla, the latter corre­sponding to a proton beam energy of 1010 GeV
CERN Courier, December 1987

## Slide 7: Previous experience @ CERN
STRING-1 (1994-1998)
One half LHC cell:
  3 MB (10 m) + 1 MQ
Validation of:
  Cryogenics (6 CD’s)
  Vacuum
  Quench (172) and protection
  Powering and energy extraction
STRING-2 (2000-2004)
One full LHC cell
  6 MB (15 m) + 2 MQ + correctors
Validation of:
  Cryogenics,
  Vacuum
  Quench and protection
  Powering
  Accelerator relevant operation (e.g.tracking of MQ and MB)
String-1 in SM-18
String-2 in SM-18
Courtesy of L. Bottura

## Slide 8: Previous experience : LHC triplets
STRING of Q1 Q2 Q3 (2005)
  Validation of:
  Cryogenics,
  (Insulation) vacuum
  Quench and protection
  Powering
  Accelerator relevant operation
Inner triplet linked via the “W” bellows ( not interconnected) in B. 181
What we have learned from it?
When pumping the vacuum magnets moved
Info from H. Prin

## Slide 9: Previouse “InExperience”: LHC triplets
STRING of Q1 Q2 Q3 (2005)
  Validation of:
  Cryogenics,
  Vacuum
  Quench and protection
  Powering
  Accelerator relevant operation
What we could have learned from a more complete IT STRING :
The supporting of the present triplet is largely hyperstatic and loads are not distributed as foreseen in the chain of the triplets. Some of the supports takes higher loads ( load on Q2 central jack up to 17 t). The straps been installed to overcome the problem.
The alignment is also laborious.
The default of the heat X tube that collapsed during the pressure and leak test in the tunnel at < 10 bar. The NCR was due to a bad procedure of welding . Discovered in the tunnel and implied a serious intervention and so delay!
This NC hided the next one (see below)
The default of the spiders: a design problem in the supporting system of the cold mass, only being seen once interconnected and ready for cooling.
The spider (supporting system very good radially but not longitudinally) broke and an other serious intervention on this implied once again a delay !
Info from H. Prin and L. Bottura

## Slide 10: LHC vs HL-LHC triplet
Comparison of main magnet characteristics
NbTi against Nb3Sn technology
1.3-1.5 times the cold ass OD (to 630 mm)
2.14 times the aperture: (to 150 mm)
~ 4 times the e.m. forces in straight section
~ 6 times the e.m. forces in the ends
2- 4.8 times the stored energy (to 1.2 MJ/m)
MQXB
MQXA
LHC
HL-LHC
Courtesy of P. Ferracin and G. Willering and E. Ravaioli
Is one of the most complex electrical circuit in the tunnel
MQXF
Quench analysis

## Slide 11: Ex. of future experience to gain with IT String
Flux jumps show up in Nb3Sn magnets as a “noise”, both in the terminal and compensated voltage
  The effect propagates from one spot along the cable length
  Poles are coupled magnetically, attempting to reduce flux changes
Flux jumps are random in location, amplitude and occurrence
They can influence powering (1 ppm control) as well as the detect-ability of normal transitions
HQ01 flux jumps
HQ01 current control
Features related to Nb3Sn :
Features related to the HL-LHC IT Circuit:
Q1
Q2a
Q2b
Q3
Cold masses powered and protected individually by cliq and quench heaters but once in a circuit the effect can propagate : the ringing, the HV. Return currents in the trim bus bars and main bus bars aswell as in the Sc link
Cold mass test
Circuit test
All these aspects can be simulated but test needs to validate the simulations
Courtesy of H. Bajas
Courtesy of E. Ravaioli

## Slide 12: Relevance for the HL-LHC IT STRING
The HL-LHC IT-String can provide relevant experience (same object as in the LHC), validation (“first time” test) and advanced operation information on:
Magnet positioning, alignment, interconnection procedures (do not under-estimate)
Mechanical behavior of the IT continuous cryostat (Q1 to DFX) and other components (DSH, DFH) under pressure, vacuum, cool-down, operation and warm-up
Cryogenic behavior and operation under static (and dynamic) conditions
Insulation and beam vacuum static (and dynamic) behavior
Powering behavior of the system with Sc links, dynamic response (and associated field quality), interaction of circuits
Cross talk between magnets in operation and during a quench, detection, propagation and protection of the complete superconducting circuit
These aspects, especially the collective behavior, can only be tested in a representative test, a so-called STRING
Develop methods, techniques
Develop tooling
Develop procedures
for
definition of
Installations
Test
Operation
to
support
HWC and OP of HL-LHC
GOALS in parallel:

## Slide 13: ID Card of HL-LHC IT-String
Test Facility name: HL-LHC IT STRING
Test Facility location: SM18 (b. 2173)
Test date: 2021-2023
Operational temperature: 1.9 K
Operational current: 108% Inominal = 18 kA?
Magnets: Q1, Q2a, Q2b, Q3, CP, D1
Cold powering: SC link (60 m or 110 m) HTS leads DFH and DFX,
Warm powering: 1 x PC 18 kA , 3 Trim Q1-Q3, 6 x 2 kA , 1 x 12 kA, 9 x 0.1 kA Water cooled cables
Protection: CLIQ , QH and EE
[…] a FULL INTEGRAL TEST of the equipment from Q1 till D1 including the DFX is foreseen in the HL-LHC project, in CONDITION AS SIMILAR AS POSSIBLE to the operational one.
The IT STRING of the HL-LHC will be composed by systems previously tested individually at least in nominal operational conditions.
HL_WP16 Conceptual specification : https://edms.cern.ch/document/1586706/1

## Slide 14
  CRYOGENIC COOLING PRODUCTION: + 35 g/s LHe to 60 g/s
  NEEDS essentially for the running of the HL LHC IR STRING in parallel with magnet testing
  DEMINERALISED WATER PRODUCTION: + 150 m3/h
  NEEDS FOR DEMINERALISED WATER ENTIRELLY COMING FROM MAGNET operation
  POWERING FROM THE NETWORK: 3 MVA
  NEEDS FOR NEW OR MODIFIED PC COMING FORM MAGNETS and IR STRING
Remarks
UPGRADE DRIVEN BY the recommendation enabling to carry out the full test programme with no contraints
Main Facilities needed for the HL-LHC IT STRING
SM18-UPG project of the TE department under the responsibility of V. Mertens:
the upgrade of all necessary services to cover the needs for the test stands operation ( this includes the HL-LHC STRING as a test stand of a complete system).

## Slide 15: Test stands : cryogenics upgrade
An additional 35 g/s liquefier (thus bringing the total production capacity for LHe at 4.2 K to 60 g/s)
The existing total pumping capacity in SM18 at 1.8 K is 12 g/s, combining the capacity of WPU1 and 2.
If need for IR STRING a dedicated 3rd WPU shall be installed.
Foreseen for 2019
Ref. L. Serio

## Slide 16: Test stands : demineralized water production
In the past SM18 had a demineralised water station with a thermal capacity of 800 kW limiting the operation to two test stands
The demands for the magnet test stations, including the IT String, will rise to a peak need to 1.7 MW (142 m3/h).
Operational from April 2016
Ref. A. J. Broche

## Slide 17: Test stand : electrical powering
The new transformer will feed HL-LHC IT STRING (Cluster J ) and the new Cluster F with the 20 kA power converter.
Foreseen for 2019
Ref. C. Giloux, F. Formenti, N. Dos Santos
To allow some flexibility and margin with new requests that are not formulated yet, the proposal is to INSTALL a TRANSFORMER OF a 3 MVA CAPACITY

## Slide 18: How we are organised for the work?
Integration and Construction
Test plan and results
Antoine Kosmicki EN ACE integration
Estrella Vergara EN ACE planning
Hugues Thiesen, Samer Yamine TE-EPC
Jean-Claude Guillaume EN-EL
Amalia Ballarino, Andre Jacquemod TE MSC
Vittorio Parma TE MSC
Ezio Todesco TE MSC
Herve Prin TE MSC
Luigi Serio, Serge Claudet +… tbd during summer 2016 TE CRG
Markus Zerlauth TE MPE
Felix Rodriguez Mateos TE MPE (Mr. Circuit)
Patrick Viret TE MSC ( TSO B. 2173)
Paul Cruikshank, Cedric Garion TE VAC
Carlos Arregui Rementeria HSE
Dominique Missiaen EN ACE
Helene Mainaud Dourand EN ACE
Serge Pelletier EN-HE
Adriaan Rijllart EN STI
Regular meetings every 3 weeks: Friday afternoon in SM18
The team is made of persons appointed by the GLs.
Meetings to define the test plan to be reported to the HL-LHC TCC . ….later regular reports on the results .
The team is made of the concerned WP leaders and HL-LHC and TE management.
M. Pojer is deputy of HL-LHC STRING

## Slide 19: Main components and schematics
Power Converters (PC)
Water Cooled Cables (WCC)
Current Leads (CL and DFH)
Superconducting Link (DSH)
Connection Module (DFX)
Magnets (D1,CP,Q3,Q2a,Q2b,Q1)
EE and Protection
Interlock and DAQ systems

## Slide 20: Limitations in space in SM18
CLUSTERS
F E D
CLUSTERS
C B A
STRING and SC LINK
LN2 TEST ZONE
CRYOGENIC ZONE
Superconducting RF CAVITY TEST ZONE
HORIZONTAL BENCHES
THE SUPERCONDUCTING MAGNET TEST STAND AT CERN in SM18
Is in a building of 7200 m2 over which the test stands for magnets occupies about 50%.
VERTICAL BENCHES
VISITORS
What boundary conditions we considered?
EXIT
EXIT
EXIT
EXIT
Marta Bajko for the TCC 15th September 2016

## Slide 21: Conflict or synergy between test stands
SC link test stand (110m)
Vertical test cryostat
Horizontal benches
IT String (80 m)
Overlap with Vertical cryostats
Overlap Sc link test stand and STRING
The integration is driven by a possible synergy as following:
Share time, cryogenic cooling and electrical powering systems between Sc link test stand and IT String

## Slide 22: Options in space: where we are today
Cooling side
Powering side
Extremity

## Slide 23: The latest proposal for integartion

## Slide 24: IT STRING the earliest possible?
2021
2022
2023
INSTALLATIONS
OPERATION
2020

## Slide 25: Current status of the work
Integration ongoing with all elements that we know today
Estimate of budget ( 4.5 MCHF) have been done and now is under verification by the members of the integration team. The strategy is that
  All main components usable in the HL-LHC are part of the WP ( prototypes or series)
  All components that are not usable in the HL-LHC are to be payed by the WP16 budget
  All services are assured within the SM18 UPG project ( financed by both TE dep and HL-LHC project)
Estimate of manpower has been done and now is under verification by the members of the integration team
In case of missing man power management support will be required
Few WPs gave already a wish list for the complete test plan

## Slide 27
Thanks for your attention

## Slide 28
Quench: provoked, natural, holding current, propagation, detection, protection, clic, dump, switch
Cryogenics: cooling- warming speed ( Nb3Sn), heat load, recovery after quench, pressure, temperature, shielding
Integration: layout, interconnections, systems around ( racks, cables trays, control cables et), total weight
Powering: bus bar, connections, current leads, power distribution at warm and at cold, converters, water cooled cables
Electrical integrity: splice resistance, electrical insulation
Interlock
Vacuum: leak detection, beam screen
Instrumentation , DAQ systems, DB , QA, QC: specific or not to string
Alignment
Validation of a layout- integration
Validation of installation sequence and procedures
Validation of a system (of components)
Validation of their collective behaviour
Develop methods, techniques
Develop tooling
Develop procedures
X
definition of
Installations
Test
Operation
2
support
HWC
OP
GOALS in parallel:
HL LHC STRING preliminary TEST PLAN

## Slide 29: MPE goals of HL-String test
Validation of interlock loops and quench loops (for potential improvement of topology/diagnostics)
Validation of final versions of the interlocks, quench detection system (QDS) and controls interfaces (including new phenomena as flux jumps,…)
Validation of CLIQ layout and magnet protection for full magnet string
Validation of transient effects and electromagnetic coupling in full magnet string + sc link during normal operation and during protective actions (CLIQ/heater firing). Verification of simulation models with obtained measurements.
Validation of EE systems for IT corrector magnets (600A, 2kA)
Validation of IST procedures for protection equipment
ELQA procedures for full string
Validate fully automated analysis of faults + automated/remote fault recovery (QDS, MP3 and Software)
Transient heat load test (studies of beam/UFO induced quenches)
Note:
  Validation of the 11T topology should follow the same approach, using already on the test beds configurations as close as reasonably possible to the final LHC installation
  String test and LS2 have a significant overlap, which might cause manpower issues for the hard- and software sections of MPE

## Slide 30: VAC goals of HL-String test
String (2019 - ):
Beam screen:
  Quench
  Thermal contraction
  Heat loads to the cold mass (supporting system)
  Flow induced vibrations
Interconnections:
  Assembly procedure and tooling for the PIM installation and beam screen cooling circuit
  Measurements of the displacements at cold, during cool down and warm-up
  Behaviour of the RF fingers
Insulation vacuum:
  Leak tests
  New O’ring or seals
Beam vacuum:
  Pump down time before cool down
  Static vacuum gas analysis
  He, H2, CO, CO2 propagation tests with a-C coating at different beam screen operating temperature in the range 40 – 70 K
  Study impact of quench and beam screen temperature on vacuum levels along the line and at cold warm transitions (with possibly dedicated vacuum gauges located at interconnects)