# LIU-PM-MIN-0263	EDMS 1715468

# LIU project team meeting

# Notes from the meeting held on 25 August 2016

# Rehearsal of the Linac4-PSB 160 MeV connection readines

Present:	J. Coupard, D. Carloni, G.P. Di Giovanni, V. Forte, A. Funken, B. Goddard, A. Lombardi, M. Meddahi, G. Rumolo, R. Scrivens

Excused: K. Hanke, M. Vretenar

- Arising matters

- A. Funken introduced Dario Carloni, new fellow, who acts as the alternate safety responsible for the LIU project, following Lisa’s departure.

- Layout overview, list of equipment and associated services (J. Coupard)

- The first talk of Julie is an overview on the areas of work and equipment involved - the slides are still being finalised.

- Since the full dismantling of Linac2 is not needed, this should be reflected in the color code in the first slide e.g. by using a different filling pattern. Only the areas of interventions needed for the early connection should be highlighted in full color, and in particular the interface Linac2-Linac4.

- Lots of civil engineering will be needed at the interface Linac2-Linac4, with new wall, shielding, chicane. The move of the access system will be proposed in another talk and is not in the minimum set of work needed for the connection.

- BI line: only the blue elements need to be exchanged, while the exchange of the yellow ones, which is planned within CONS, is not strictly needed (although it would be desirable to change them together with the other). The beam stoppers are upstream, now it has been clarified that it is not necessary to change them as they can withstand LIU beams. However, their replacement is now in the LIU baseline for questions of standardization and spares (see Klaus’ talk).

- The KSW stack is planned to be installed in EYETS and will not be powered until it needs to be used after the connection.

- Concerning the list of equipment and services, some orphan equipment was found. This should be highlighted in the talk.

- The lists of the layout drawings (EN-ACE) and equipment design (EN-MME) could be color coded according to the status.

- Although the points highlighted on last slide (risks, mitigations) are more general than concerning the emergency connection, this review could be the good opportunity to raise these points and pose the questions to the management.

- Linac4 including source (A. Lombardi)

- This is a general talk on the status of source + Linac4, the timelines, what is done and what not, risks and mitigations.

- Current status is with HST + vertical chicane after HST already installed.

- The improvements applied to the ion source are shown together with the target H- current values to fulfill the LIU requirements (as was shown in Chamonix and updated with the latest value of current reached, i.e. 28 mA – reflecting the first phase of improvements that was supposed to get to 30 mA). The line showing the beyond LIU value (60 mA) should be removed.

- The word ‘Missing’ in the title of the slides ‘Missing items for connection’ is misleading.

- Inauguration of Linac4: does it mean the achievement of the nominal parameters for LIU? Anyway, it should be taken out of the schedule because any discussion on this point is not relevant for the goal of the review.

- The schedule should not begin with ‘Spare time for HST’. Rather, this slot should be renamed as ‘Source/Linac4/HST short reliability run’ and then used as spare time for HST, if necessary (the baseline should be to finish the HST by the end of 2016). The second part of 2016 could be added in the schedule.

- On the last slide, the ion source program will be impacted by the early connection because after the connection it won’t be possible anymore to change the source and check the effect on the provided current, so the current might be stuck for some time to a value lower than the desired 40 mA.

- The overall conclusion on connection readiness from Linac4 point of view should be stated clearly on one slide before highlighting the risks associated.

- Risk assessment, mitigation and spares (B. Goddard)

- In this presentation the risks are ranked only for the event of early connection, and they are given at the system level and not at the level of the single piece of equipment.

- The methodology for the ranking is explained and risks are ranked with respect to shutdown schedule, operational availability and beam performance.

- In the schedule risks (II), points 2 and 4 could be merged into a single point.

- The slides with the points of no return should stay in this presentation.

- It is important to highlight what was learnt from the SNS experience, however the detailed slide could be put in spare (as well as the slide on the spares).

- LIU-PSB 160 MeV (including HST) (G.P. Di Giovanni on behalf of K. Hanke)

- General talk on readiness of the PSB to the early connection.

- As remarked above, the present baseline of LIU is that the beam stoppers will be prepared and then installed in YETS 2017-18, however the old ones can be used in case of early connection.

- Few items on the critical path are found in the PSB rings. The target parameters after the Linac4 connection should be provided (in Mike’s talk). The new tune pick up will make possible to measure the tune for very low intensities during beam commissioning, operating without it is however possible.

- Julie would like to re-discuss together the slide on infrastructure to be sure that consistent information is presented.

- HST schedule: to be adapted following comments to Alessandra’s talk. Anyway, the 160 MeV beam commissioning should be extended also beyond November 2016 and in principle the two lines on 160 MeV beam commissioning and HST could merge into a single source/Linac4/HST reliability run for the first three months of 2017.

- The question of the reliability run of Linac4 from CCC (raised in both Brennan’s and Klaus’ talks) should be discussed more in detail in terms of the goals and the way it could be done.

- Detailed timeline for dismantling complete installation, including survey (J. Coupard)

- This talk shows the schedule of the Linac4 connection (6 months for installation).

- The color code for different areas of intervention used in the first talk is now used also for the schedule. The part of hardware commissioning and beam commissioning can be further completed with information from Bettina and Vincenzo.

- The schedules for the different parts are shown on the general master schedule – all details are provided on the slides but won’t be discussed for lack of time.

- The question on civil engineering for the alcove to start not before March 2017 should be clarified (why not before, its impact on operation).

- For the work in the PSB, it is not possible to start working before the end of the decabling campaign (end of the EYETS)

- A slide with a summary of the timeline in words should be included as conclusion (for people who are not familiar with the schedule).

- Linking with Christelle’s presentation – the safety milestones provided by Christelle will be added into Julie’s master schedule.

- Operational requirements for beam commissioning activities (V. Forte)

- The difference between first three phases of commissioning and LHCPROBE commissioning is that during the LHCPROBE commissioning also the desired transverse and longitudinal parameters will be targeted.

- The 50 ns beam should be removed from the list of beams to be commissioned.

- Although the commissioning of all beams will overall take 7 months, it should be well highlighted when LHCPROBE is ready (after 2.5 months) and maybe it can all be shown on a timeline.

- The presentation should be slightly shortened to fit well in the allocated 15’.

- AOB

- The next general LIU-PT meeting will take place on 1st September 2016.

Minutes by G. Rumolo