## Slide 1: 43nd Bi-weekly meeting F. Sanchez Galan, 20-09-2016

## Slide 2: News
Visit Staubli last Thursday, very compact connectors look promising.
Mini-TAN @ P8. Solution found, no impact on BRAN, Y-chamber or collimators. Start design.
Next meetings & reviews
CMAC CSR
EFCA, Annual meeting
HL-LHC, Collaboration meeting
HL-LHC TCC (mini-TAN)
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016

## Slide 3: CMAC CSR
the 2nd Cost & Schedule review of the HL-LHC and LIU projects will be held at CERN on 17-19 October 2016.
  A plenary session addressing the status of both projects and providing an overview of the HL-LHC technical infrastructure work-package and its challenges is organized on the 17/10 in the morning.
  On the 17/10 afternoon and on the 18/10, the review is organized in parallel sessions as follows (HL-LHC sessions here mentioned):
  Session 2: HL-LHC – Magnets, powering and cryogenic systems (Convener: J.-M. Jimenez)
  Session 3: HL-LHC – Superconducting RF and other accelerator systems (Convener: P. Collier)
  Session 4: HL-LHC – Technical Infrastructures, Integration and (de)installation (Convener: L. Tavian)
  Session 5: HL-LHC/LIU – Cost, schedule and change management methods (Conveners: L. Rossi/M. Meddahi)
  A preliminary version of the agenda of each session is available on Indico.
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016

## Slide 4: CMAC CSR
The talks will include the following elements:
  Impact of 1st Cost & Schedule review
  Changes to the baseline since the 1st Cost and Schedule review
  Status of work in progress
  Budget related items (Material cost, Manpower, level of uncertainty)
  Schedule related items (schedule, critical path)
  Risks and mitigation measures
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016

## Slide 5: WP8 – Collider-Experiment Interface Installation Overview (oct 2016)
TAXS
TAXN for ATLAS | 2 units (1 per IP side) | P1
TAXN for CMS | 2 units (1 per IP side) | P5
TAXS for ATLAS | 2 units (1 per IP side) | P1
TAXS for CMS | 2 units (1 per IP side) | P5
Equipment | Quantity | Location
TAXN for LHCb | 2 units (1 per IP side) | P8
TAXN

## Slide 6: WP8 – Collider-Experiment Interface Installation Overview for LS2
TAXN
Equipment | Quantity | Location
TAXN for LHCb | 2 units (1 per IP side) | P8
Shielding modifications (option)
New Vacuum pump support (option)

## Slide 7
Description | WP | Period | Location
NON-BASELINE (options) |  |  | 
CMS New support for vacuum pump at FIN | 8 | LS2 | P5
ATLAS JFC3, JFC3 Shielding modification | 8 | LS2 | P1
Summary table of LS2 activities (2/2)

## Slide 8: Risks and mitigation
Equipment / Systems | Risks | Risk level class | Mitigation

## Slide 9: News
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016
https://indico.cern.ch/event/549979/timetable/#20161116.detailed
HL-LHC Collaboration Meeting day 3. “Final solution for VAX integration”.
BPM
Vacuum layout
Connectors, survey &alignment
Cabling
Survey
Motorization
Q1-TAXS
IP far side: JTT, New pump

## Slide 10: News
https://indico.cern.ch/event/549979
Next steps
Finalise integration replaced VAX
Prototype (CMS chassis design).
Define operations that could be advanced to LS2
Test alignment capabilities, remote operation.
Internal review together with experiments in 2017
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016

## Slide 11: WP8 – Collider-Experiment Interface Schedule
F. Sanchez Galan, 43nd WP8 Bi-weekly meeting 20-09-2016