## Slide 1: Planning and discussions
Access restrictions of the LHC machine
Some Examples
General Schedule with Powering Tests

## Slide 2: What is not detailed
Safety rules
Electrical lock-out
Hardware commissioning coordination
  ADI
Experiment access
Access system (only general overview)

## Slide 3: Access restrictions of the LHC machine
From Shutdown coordination
to Hardware commissioning coordination

## Slide 4: The LHC machine
16 tunnel sectors
6 service areas (point 1, 2, 4, 5, 6, 8)
4 Experiments
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS

## Slide 5: Typical schedule evolution
Shutdown (installations, consolidations, maintenances)
  General access
Hardware commissioning
  General/Restricted access (ADI)
  Restricted/CLOSED for Powering Tests
    Phase 1 concerns tunnel
    Phase 2 concerns tunnel + service areas
See Matteo’s slides
1st ELQA
PT

## Slide 6: Sector 12 and 23
For examples

## Slide 7: Sector 12 – from 1st ELQA
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS
For example

## Slide 8: Sector 12 – from PT phase 2
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS
Waiting for safety rules
For example

## Slide 9: Sector 23 – from 1st ELQA
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS
For example

## Slide 10: Sector 23 – from PT phase 1
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS
For example

## Slide 11: Sector 23 – from PT phase 2
UJ17
PM18
UJ23
UJ27
PZ33
UJ43
UX451
UJ47
UL55
PM56
UJ63
UP63
UJ67
PM76
UJ83
UJ87
UJ13
PM25
PM15
PM45
PZ45
PM65
PM85
ALICE
ATLAS
LHCb
CMS
For example
Waiting for safety rules

## Slide 12: Starts of restricted access
Sector 12 – week 22
Sector 23 – week 18
Sector 34 – week 27
Sector 45 – week 19
Sector 56 – week 19
Sector 67 – week 24
Sector 78 – week 30
Sector 81 – week 31

## Slide 13: General Schedule with Powering Tests
Schedule under discussion
New Draft in work

## Slide 14: General overview – February09
Start on week 24
End on week 38
  15 weeks
BUT :
  No details of the Powering Tests
  No details of the ELQA
  nQDS racks were available end of April
LHC workshop – Chamonix09

## Slide 15: General overview – March09
PT
PT
PT
PT
PT
PT
PT
PT
Start week 26
End week 39
14 weeks
Racks mid of June

## Slide 16: General overview – last week
PT
PT
PT
PT
PT
PT
PT
PT
Start week 28
End week 41 !!
14 weeks
Racks end of June

## Slide 17: Target = gain time !
How to gain time :
  Starting as soon as possible
  Performing all what can be performed instead of waiting to do all at the same time
  Finding more human resources
      Works in parallel
      2 or 3 shifts

## Slide 18: New detailed draft – in work
Start week 22
End of May
End week 39
18 weeks
Racks end-June
will need 3 shifts
(24h/24h 7d/7d)
+ week-end