## Slide 2: Logistics update
01 September 2016

## Slide 3
0702 Speakers Visits
On schedule
2 guided visits booked on 4 November for 12 people each
One group at 10:00-11:30, the other one at 15:00-16:30
The visit itinerary will be : SC + CCC

## Slide 4
0703+0705 Pre-event activities
Conference with 3 TEDxCERN speakers on hot topic questions
Moderator: Olivier Dessibourg (Le Temps)
Opened to the public, registration mandatory
Speakers:
  Marcus Gary: Artifical Intelligence
  Jun Wang: Genetic Sequencing
  Denis Lo: Liquid Biopsy
  Eleonore Pauwels: Genomic Technologies
Format:
  17:30 short talk by speakers (4 x 10’)
  18:10 panel debate + Q&A (50’)

## Slide 5
0704 Event Activities (Eva + Maria)
On schedule
Potentially 4 speakers confirmed:
  Laura Baudis: prototype of her detector
  Samira Hayat: drone (location tbc)
  Michael Grätzel : solar cells tbc
  Shanon Dosemagen: activity tbc
SA exhibition space has been booked
Photo booth combined with a "Share your idea" panel tbc
“Be a TEDx speaker for 1 min” being discussed, need follow-up
Table decoration: in progress with Cinzia and Daniel
Activities requirements to be provided on 1 October
Book store: upstairs

## Slide 6
0706 Catering
On schedule
Call for tender sent, 3 short-listed within budget
Tasting done this week with Novae, Ô en Bouche, Mets Plaisir
Possibility to split between multiple caterers
Budget: ca CHF 20k incl. Volunteers party, excl. some speakers lunches
Deadline: caterer(s) picked 5 September

## Slide 7
0707 Spaces
On schedule
All spaces blocked
Room D for storage 2>4+6>7 Novemberc

## Slide 8
0708 Access (Erwin)
On schedule
Meeting was organised on
23 June with Didier Constant
to finalise paths and blocked
areas
Plan is:
  Favourable weather: guests enter and exit via Gate A, cars parked at Globe
  Unfavourable weather: VIP & media enter and exit via Gate A; standard guests via Reception
  Final decision taken on Wed. 2 November

## Slide 9
0709 Signage, maps, info screens
On schedule
Info screens booked (3 guaranteed, asking for 5)
IdeaSquare container inventory next week
Graphic Design wants all requirements by 17 October

## Slide 10
0710 Check-in
On schedule
Eventora confirmed for ticketing system
Check-in with 15 smartphones More flexible solution in case check-in is at Reception
Looking for smartphone providers (Swisscom or CERN)

## Slide 11
0711 Safety / Emergency
On schedule
Production held a meeting with HSE early July.
Document shared with Neal 22 July
HSE asked for update

## Slide 12
0712 Transports
On schedule
2 vans rented for speakers with Sixt through CERN Mobility
Drivers must have V access authorization Nikos and Christos?

## Slide 13
0713 External Contractors
On schedule
DAI requested to Marika for Cloakroom
Who takes care of hairdresser and makeup ?

## Slide 14
0714 Cleaning
On schedule
Ticket opened with SMB Awaiting feedback
Extra rubbish bins ordered

## Slide 15
0715 Communications
On schedule
Wi-Fi: requested extra coverage 12 August (5 points for CHF 1000)
Cable (50 CHF / point): TBD
Reserved 10 TETRAs

## Slide 16
0716 Technical support during the event
On schedule
Need to contact CERN service to check need / conditions
  Cooling and ventilation
  Lifts
Cleaning team ordered