Hardware Commissioning Coordination Meeting, 23 April 2009

Agenda (http://indico.cern.ch/conferenceDisplay.py?confId=57047):

1) Powering test and shift planning -Julie Coupard, Antonio Vergara, Matteo Solfaroli

2) HC activities during SD: SCT and WM - Marco Zanetti

3) AOB

- Readiness of Cryo for cooldown of S23 and S45  - Serge Claudet

- DFB preparation for powering  - Antonio Perin

- ElQA work plan: teams, shifts, schedule - Nuria Catalan

Powering tests and shift planning

- Planning (Julie)

Latest schedule has been presented, with the beginning of the powering tests foreseen by the end of May in sector 23 (phase I). The phase with large stored energy in the circuits (phase II) will start only when the nQPS will be available. First installation and IST of the latter scheduled for W28. Symmetric QPS, necessary to complete the phase II, will be available only at the end of July (W32).

Comment (Hugues): only main circuits require nQPS in place, the circuits (e.g. the IPQs or the ITs) could be powered even to high current before.

- OP Shift planning (Antonio)

Powering operations divided into three periods depending on the workload:

- May-June: 1 shift/day 5 days per week, 1 EiC+1 operator

- July: 2 shifts (M/A) 5 days per week, 1 EiC+ 2 operators

- Since ~August: 3 (not full) shifts.

Comment (Rudiger): it is assumed that other teams will assist OP.

Comment (Knud): nQPS installation will be done in one shift.

Request to free OP from the duty of giving access during the whole PT period.

ACTION: Resources for giving access to be recruited from PH and EN (Mike)

Comment (Roger): possible manpower issues during first week of August due to parallel OP activities

- S23 readiness for powering preparation (Matteo)

A detailed plan for ElQA and cool-down during weeks 18 and 19 has been presented: - ElQA on IT will start on Monday 27, continuing with LSSs during week 18 and finishing with the arc on Tuesday 05 (no work over the weekend, 1 day per DFB).

- Cool down of the arc to 80 K (currently floating) will begin on Tuesday 28 in parallel will ElQA on LSSs.

-  Cool-down to 80 K of the LSSs will begin after the completion of ElQA@300 K at the end of week 18.

Access in general mode during (2nd) cool-down.

Comment (Katy): do we have to move the sector to restricted mode since Tuesday 28? This would raise issues related to access management as several activities (BLI installation and source calibration, survey, UPS modification) are still planned during the cool-down period. Mike stated that the beginning of access limitation was foreseen for week 20.

Final decision: for week 18 and 19, sector 23 will stay in general mode with access to the tunnel limited to a list of people. Panel will be placed at the beginning of the tunnel and the gerant du point will patrol the area twice per day.

P8 Warm Magnets tests and P6 SCT

- P8 WM tests during week 17 were successful; all magnets (TI8 too) passed the WIC and PC tests. 24 hours heat run for septa and LHC magnets (Q6 corrector and LHCb compensators) led to positive results (magnets temperature < 50 C, polarity check OK)

- Interference between TI8 magnets and LHCb compensator to be verified as well as operations with the LHC SVC. The latter will be available since end of June

- Preparation for the SCT on P6 ongoing, heat run scheduled for Tuesday 28.

Cryo readiness for S23 hardware commissioning

- Preparation for cool-down and software ready by end of week 17. Milestone for week 18: PIMs temperature at 140 K.

- Interplay with ElQA as presented by Matteo. Final cool-down from 80 to 4.5 K to start when the ElQA@80 K will be finished for the arc and when all magnets will be OK at 80 K (scheduled day is Wednesday 6 May).

- Overall the cool-down is foreseen to last 2.5 weeks plus 1.5 week for DFB commissioning at 1.9 K.

Remark (Serge): can we cool-down the MS and IT magnets (currently at room temperature) with He at 80 K, i.e. with T>150 K? ACTION: check this issue with Jean-Philippe and magnets people.

Protection of DFBs electrical live parts

- Antonio described the plastic protections to be placed in front of the current leads. They are already in place on both sides of P2.

- Policy for when the protection should be mounted and when dismounted is being defined.

Comment (Katy): integration team should be always aware of new installation and protection of ICL group.

- Protections above Cryo-link are also being putting in place. The metallic structure could hold the weight of couple of people but they are NOT designed as footbridges.

The will also have to be modified in order to allow the opening of the DN200 valve on the cryo-link.

ElQA work plan: manpower and shifts

- Currently only 2 teams available (e.g. to start the ElQA on sector 23).

- 6 teams available since beginning of May.

- 7th team becoming available since beginning of June, the 8th has to be provided from within CERN.

- Only 2 shifts per day are foreseen at regime: ideally 4 teams working in the morning and 4 in the afternoon. The current planning does not require having 3 shifts.

Comment (Rudiger): the possibility to work in a different shift schedule should be envisaged, if required due to planning g constraints.

Summary written by Marco Zanetti