## Slide 1: Powering test and shift planning

## Slide 2: General Planning with the Powering Tests
Overview of the new Draft

## Slide 3: Target = gain time !
How to gain time :
  Starting as soon as possible
  Performing all what can be performed
  Finding more human resources
      Works in parallel
      2 or 3 shifts

## Slide 4: Draft in work – 9th, April 09
Start week 22
End of May
Racks end-June

## Slide 5: New Schedule – to be defined in details
Start week 22
End of May
Racks end-June – wk.27
Q-sym August – wk.32

## Slide 6: New Schedule – to be defined in details
QPS IST (without Q-sym)
QPS IST (Q-sym)
Phase 1
Phase 2

## Slide 7: Summary – starting dates
wk.33
wk.20 11.05
wk.29 13.07
wk.21 18.05
wk.24 08.06
wk.30 20.07
wk.32 03.08
wk.34 17.08
wk.20 11.05
wk.17 20.04
wk.25 15.06
wk.22 25.05
wk.22 25.05
wk.24 08.06
wk.27 29.06
wk.32 03.08
wk.32 03.08
wk.34
wk.36 31.08
wk.36 31.08
wk.29 13.07
wk.34 17.08
wk.30 20.07
wk.31 27.07
wk.35 24.08
wk.34 17.08
wk.39 21.09
ELQA @ warm
ELQA @ cold
PT Phase 1
PT Phase 2

## Slide 8: Shift planning

## Slide 9: Powering Test Shifts: a proposal
1 shift (9H-17H): 1 EIC + 1 Operator (+ 1 non-OP person for giving accesses)
2 shifts (M – A): 1 EIC + 2 Operators (same as last year)
3 shifts (M – A – N):
- Morning: 1 EIC (EIC or experienced operator)
- Afternoon: 1 EIC + 2 Operators
- Night: 1 EIC + 1 Operator