## Sheet1
2016-11-24 07:40
IDX | ACTION Description | Follow-up by | Status | Open | Deadline | Closed | Comments
1 | EN-EL inventory for LIU-PS installations for LS2 | J. Devine, P. Lelong | OPEN | 2016-06-30 | 2016-11-30
2 | ECR and SRR for the piping modification for the new cooling stations | S. Deleval | OPEN | 2016-07-12 | 2016-11-30
3 | Follow-up of the ECR of the EYETS still not completed (MU41, 80 MHz, BLMs) | LIU-PS meeting | OPEN | 2016-08-09 | 2016-08-30
4 | Input for the vacuum chamer design of the injection bumpers | D. Bodart | OPEN | 2016-09-27 | 2016-12-15
5 | SEM Grids functional specification | A. Guerrero | OPEN | 2016-10-25 | 2016-11-15
6 | Functional specifications for the low energy correctors, quadrupoles and injection bumpers | G. Sterbini and PS-OP | OPEN | 2016-11-24 | 2016-11-29
| SEM Grids mechanics installation in EYETS16/17 | A. Guerrero | CLOSED | 2016-10-25 | 2016-11-15 | 2016-11-15
| Sent to the integration team a refined BGI magnet model | D. Bodart | CLOSED | 2016-09-27 | 2016-10-11 | 2016-10-11
| To complete the ECR of the BGI magnet | D. Bodart | MERGED | 2016-09-12 | 2016-09-27 | 2016-09-27
| To complete the ECR of the MU41 quadrupole | D. Bodart | CLOSED | 2016-09-12 | 2016-09-27 | 2016-09-27
| Clarify the need and the preferred implementation for the TGM external condition | R. Steerenberg | CLOSED | 2016-01-12 | 2016-08-23 | 2016-08-23
| ECR of the BGI magnet | D. Bodart | CLOSED | 2016-03-01 | 2016-08-30 | 2016-08-09
| Requirements for the V BGI magent (aperture and B field) | A. Guerrero | CLOSED | 2016-06-30 | 2016-07-12 | 2016-07-12
| Report on the reference measurement of the MU42 | T. Dobers | CLOSED | 2016-05-17 | 2016-07-12 | 2016-07-12
| Contact the different teams for complete injection power converter specs | J-M. Cravero | CLOSED | 2016-05-17 | 2016-07-12 | 2016-07-12
| SRR for the vertical BGI (SS84) | A. Guerrero | CLOSED | 2016-06-30 | 2016-07-12 | 2016-07-12
| Verify if the SRR for extra cooling piping is needed | S. Mataguez | CLOSED | 2016-06-30 | 2016-07-12 | 2016-08-23
| Clarify the position of the vertical BGI | H. Damerau | CLOSED | 2016-04-12 | 2016-04-26 | 2016-04-26
| Distribute the EN-EL cables inventory to the WP holders | K. Hanke | CLOSED | 2016-03-14 | 2016-03-29 | 2016-03-29
| Quantify and communicate the magnet WU budget for TT2 LIU-PS related activities | D. Bodart | CLOSED | 2016-01-12 | 2016-02-16 | 2016-02-16
| Quantify and communicate the AC/DC WUs budget for TT2 LIU-PS related activities | J. Devine | CLOSED | 2016-01-12 | 2016-02-16 | 2016-02-16
| Clarify the DC cable extra budget (177 kCHF) for the PSR | J. Devine | CLOSED | 2016-02-02 | 2016-02-16 | 2016-02-16
| Clarify the RF heat load requirement | K. Hanke and C. Rossi | CLOSED | 2016-01-12 | 2016-02-02 | 2016-02-02
| Quantify and communicate the transport WU budget for TT2 LIU-PS related activities | C. Bertone | CLOSED | 2016-01-12 | 2016-02-02 | 2016-02-02
| Clarify the responsibility of the present TT2 interlock system dismantling | S. Pittet and R. Mompo | CLOSED | 2016-01-12 | 2016-02-02 | 2016-02-02
| EN-CV inventory for LIU-PS installations | S. Deleval | CLOSED | 2016-01-12 | 2016-05-01 | 2016-04-12
| Request a reference measurement for the present MU42 vacuum chamber | H. Damerau | CLOSED | 2016-04-26 | 2016-05-17 | 2016-05-17
| Organize a meetign for the BGI magnet status | K. Hanke | DELETED | 2016-04-26 | 2016-05-17 | 2016-05-17
| Provide mechanical drawings for BGI magnet integration to J.-M. Lacroix and Y. Muttoni | D. Bodart | CLOSED | 2016-03-01 | 2016-05-02 | 2016-05-31
| Clarify BLM rack position | K. Hanke, H. Damerau | CLOSED | 2016-05-17 | 2016-05-31 | 2016-05-31
| Contact M. Puccio for the protection of the low energy quadrupoles | K. Hanke | CLOSED | 2016-05-17 | 2016-05-31 | 2016-05-31
| Complete with the plan number the EN-EL cable request inventory | H. Damerau | CLOSED | 2016-04-26 | 2016-05-17 | 2016-05-31
| Bumper integration to report/discuss in the integration meeting | K. Hanke | CLOSED | 2016-05-17 | 2016-06-30 | 2016-06-14
| Define BLM crate layouts | C. Zamantzas | CLOSED | 2016-05-31 | 2016-06-30 | 2016-06-14
| Verify the civil work (mini-shafts) for the BLM cables passage | S. Mataguez | CLOSED | 2016-05-31 | 2016-06-30 | 2016-06-14
| EN-EL inventory for LIU-PS installations | J. Devine, P. Lelong | CLOSED | 2016-03-01 | 2016-06-30 | 2016-06-30
| Provide an estimate for the cost of the PS cooling station upgrade considering the direct connection to TT2 | S. Deleval | CLOSED | 2016-03-29 | 2016-06-30 | 2016-06-30