## Slide 1: ELENA Project E. Harrouch
Installation follow-up & Planning update

## Slide 2: Follow-up
Btrain installation :
  Completion of the Btrain system to be performed

## Slide 3: Follow up
Other equipment installation
  Tune measurement : Installed and aligned
  Scrapers : Installed and tested.
  Long PU : Installed
  BTV : Installed and tested
  BPMs : Installed
  Injection Kicker : Installed
  SEMs : First SEM : Installed on LNS. 3 / 4 SEM at CERN.

## Slide 4: ELENA Magnets status w39
12 MCCAY H/V correctors status:
  MCCAY03: Installed in position LNR.MCCAY.0130.;
  MCCAY04: Installed in position ;
  MCCAY02: Certification is not OK, Investigating ongoing by contractor ;
  MCCAY05: Certification is OK, Magnetic measurements are ongoing, Installation should be possible on 04/10/2016;
  MCCAY06: Certification is ongoing, Installation foreseen on 10/10/2016;
  MCCAY07: Certification is ongoing, Installation foreseen on 10/10/2016;
  MCCAY08 and MCCAY09, Shipment is ongoing. Delivery foreseen on 03/10/2016, Installation foreseen on 14/10/2016;
  MCCAY10 and MCCAY11, delivery foreseen on 14/10/2016, Installation foreseen on 24 /10/2016;
  MCCAY12 and MCCAY13, delivery foreseen on 20/10/2016, Installation foreseen on 01 /11/2016.

## Slide 5: Alignment
Chart: 
Statut de l’alignement : 100%
  Magnets :
    All the magnets are aligned
    Correctors magnets are not aligned, the survey only measures their position after installation : Difference of 5mm in the radial direction (Toward the inside of the machine)
  All the other beamlines components are aligned
Last step on-going : « Lissage » of the machine
Alignment required to close vacuum
Alignment progress

## Slide 6: Vacuum advancement
Vacuum sector | Desc. | Bake-out | Pressure reached
LNI-LNE | Inject, from AD + Eject. To exp. | Starting date to be defined | -
LNS20 | Source | Start expected by the end of the week | -
LNR10 | Eject. to exp. | Done | 1x10-12mbars
LNR20 | Inject. To ELENA | On-going | -
LNR30 | Eject. to GBar | Done | 2x10-12mbars
LNR40 | E-Cooler Sect | Done | 1x10-10mbars
LNR50 | Scrapers + RF | Done | 5x10-12mbars

## Slide 7: Bake-out planning
LNR 10,30,40,50 bake-out completed
LNR20 Bake-out on-going
LNS20 Bake-out start expected by the end of the week
LNI-LNE bake-out cannot be done in parallel of LNS20/LNR20 bake-out (Not enough power socket and space available)
Bake-out planning if we do not wait for the SEM

## Slide 8: Bake-out planning
3 weeks from now before the SEM are sent for vacuum tests
2 weeks of vacuum test
Bake-out completed by the 1/11 with this scenario
Bake-out planning if we wait for the SEM

## Slide 9: Summary of next week
Bake-out LNR20 (TE-VSC)
Bake-out LNS (TE-VSC)
“Lissage” of the machine (EN-ACE)
  Installation of one corrector magnets (TE-MSC)

## Slide 10: Hardware tests
Any tests performed on the machine should follow the same procedure :
  Notify Francois Butin and Jose Gascon by email with a description of the tests that you foresee.
  Francois will then trigger a Visite d’Inspection Commune (VIC) if required
Please notify to me all the tests/work that will be performed after the end of the bake-out so they will be integrated to the planning.
REMINDER

## Slide 11: Spare slides

## Slide 12: Lock-outs
Racks sous la responsabilité de TE-EPC :
Liste des Racks Convertisseurs se trouvant sur la plateforme :
  RYE01 à RYE03 Powering Ring (Responsable équipement : Kuczerowski, Nicolas)
  RYE08 Ion Switch (Responsable équipement : Machado Christophe)
  RYE10 à RYE13 Transfert Line HV (Responsable équipement : Machado Christophe)
  RYE18 à RYE21 Electron Cooler Low Converters (Responsable équipement : Yves Thurel, Ludovic Charnay)
Liste des Racks Convertisseurs se trouvant en salle de puissance :
  RA-K302 à RA-K307 ELENA Electron Cooler (Responsable équipement : Ludovic Charnay)
  RB300 et RB301 Convertisseurs APOLO + Spare (Responsable équipement : Christophe Mutin)
LNI bendings: Locked-out (C.Carli) + ground straps on magnets
La demande de consignation peut se faire via le service first line EPC 163668 ainsi qu’à Michal DUDEK ou un responsable d’équipement.
REMINDER

## Slide 13
On the 07/09
Please put your cables in the green configuration

## Slide 14
On the 21/09
Please put your cables in the green configuration