## Slide 1
East Hall Renovation
B.157 project meeting
S.Mcilwraith – C.Gasnier
Civil Engineering works
S.Mcilwraith – C.Gasnier (SMB-SE)
21/10/2016

## Slide 2
Project Background
IPP validated in 2016 in order to improve the safety and the thermal comfort of the building :
  Façades contain asbestos and provide a very poor insulation
   Refurbishment with new cladding and glazing
  Ceiling contains asbestos and provides a very poor insulation
   Removal of the old panels (asbestos) and installation of new insulated ceiling panels
B.157 project meeting
S.Mcilwraith – C.Gasnier

## Slide 3
Overview
  Ceiling :
    Insulation panels  4600 m2
  Facades :
    Glazing  1500 m2
    Cladding  1200 m2
  Option
    Catwalk 450m2
  Each item contains asbestos (either in panels or joints)
B.157 project meeting
S.Mcilwraith – C.Gasnier

## Slide 4
1. Upper-level interior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
8 months
6 months
6 months
~12 months
This planning can be optimized by dividing the building into zones.
Different tasks can be partially superposed

## Slide 5
1. Upper-level interior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
Suspended scaffolding
(~5000 m2)
Ceiling panels to replace
Upper windows to replace

## Slide 6
2. Exterior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
2 months / facade
3 months / facade
 Approx. 5 months of work per façade in total.

## Slide 7
2. Exterior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
Fibre-cement cladding to be replaced (1200 m2)
Glazing to replace(1500 m2)
Note: Possibility to reduce mid-level glazing to be investigated

## Slide 8
2. Exterior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
Constraint on façade works :
On the west side of the building, the PS ring makes the access to the facades difficult.
 Access on the backfill of the PS may be necessary however this option must be investigated more deeply

## Slide 9
3. Option: Mid-level interior of building
B.157 project meeting
S.Mcilwraith – C.Gasnier
Catwalks containing asbestos to be replaced
(450 m2)
Estimated time for removal of asbestos-containing vinyl tiles: unknown
  Proposed strategy: Authorise a test for a length of 5 – 10m to ascertain the required total work (possibility to choose zone most in need of repair)
Estimated time for installation of metal floors ≈ 6 weeks

## Slide 10
Procurement strategy
Design and preparatory works:
  Price enquiry for architect, mandate to include:
    Thermal studies
    Working conditions with respect to natural light
    Building permit
    Preparation of tender documents
Construction:
  Price enquiry for suspended scaffoldings
  IT for asbestos removal and reconstruction of ceilings and facades
     MS already established
  Option : Catwalk asbestos removal and reconstruction (blanket contract or included in IT)
B.157 project meeting
S.Mcilwraith – C.Gasnier

## Slide 11
Next steps
Scope to be frozen (SMB-SE & project team)
Purchasing strategy to be validated (SMB-SE & project team)
Price enquiry documents for architect to be prepared (following validation of purchasing strategy)
Construction program to be established (SMB-SE, project team and other infrastructure packages)
B.157 project meeting
S.Mcilwraith – C.Gasnier

## Slide 12
Technical points to be confirmed
Will the CE works be conducted under radiation controlled zone regulations ?
How advanced are the other WPs ? What conflicts / co-activities / task interfaces exist ?
B.157 project meeting
S.Mcilwraith – C.Gasnier

## Slide 13
Thank you for your attention.
Any questions ?
B.157 project meeting
S.Mcilwraith – C.Gasnier