## Slide 1: MOPOS status
Milestones and mid term plans
02/11/2016

## Slide 2: Milestones
LogAmp board tested
EYEYS 2016
GEFE FPGA batch qualified
May 2017
Sextant installed
YETS 2017
Full MOPOS upgrade
LS2

## Slide 3: To do…
Installation of an acquisition system (Thierry)
Development of a test GW for the GEFE (Manoel)
Development of a test GW for the VFC (Irene)
Development of a control SW (Irene/Manoel/Andrea)
Development of an analysis SW (Irene)
LogAmp board tested
EYETS 2016

## Slide 4: To do…
Acquisition of samples from a controlled batch (Manoel)
Test Definition (Manoel/Andrea)
Preparation of a test GW for the GEFE (Manoel/Jakub(?)/Luca&Sarah(?))
Preparation of a test GW for the VFC (Manoel/Irene)
Preparation of a control SW (?)
GEFE FPGA batch qualified
May 2017

## Slide 5: To do…
Procurement of the qualified batch of FPGA (Manoel)
Production of 40 GEFE (Manoel)
Production of 40 LogAmp and calibrators (Thierry/Laurant)
Production of ?? DOR boards (Marek/Jakub)
  Qualification and selection of the ADC (Jakub)
  Design of the board (Marek/Jakub)
Production of 36 Pizza Boxes (Thierry)
  Definition of the DOR board form factor (Marek)
Production of 10 VFC-HD (Andrea)
Installation in the tunnel (Everyone)
  Fibres (Joel)
  Cables (Joel)
GW development (Manoel/Irene/Jakub)
SW development (BE-BI-SW)
Sextant installed
YETS 2017

## Slide 6: Infrastructure status
Hybrids:
Cables:
Mini-rack:
Pizza-Box:
Fibres:

## Slide 7: Acquisition system status
Calibrators:
PS:
LogAmp:
DOR:
GEFE:
ADC board:
VFC-HD: