## Slide 1: (02/11/2016)
MOPOS Project
Manoel Barros Marin
Status Review & Plans
BE-BI-QP

## Slide 2
BE-BI-QP
Status Review & Plans
Outline:
Digital FE production status
Installation & radiation monitoring campaign
MOPOS Project

## Slide 3
BE-BI-QP
Status Review & Plans
Outline:
Digital FE production status
Installation & radiation monitoring campaign
MOPOS Project

## Slide 4
Digital FE (GEFE + BDF) production status
(1 of 3)
Introduction
  MOPOS Digital Front-End (DFE) composed by:
  General purpose rad-hard carrier: Gbt-based Expandable Front End (GEFE) (EDA-03168-V2)
  MOPOS specific mezzanine: Bpm Digital front-end Fmc (BDF) (EDA-03134-V1)
ADCs
FPGA
High-Speed Optical Link

## Slide 5
  Production Stage
  Foreseen by Q3 of 2017
  Custom rad-hard components already procured:
  - Transceiver ASIC (GBTx): 500 pieces
GEFE Production Status
  Pre-production prototype successfully developed and tested
  Pre-Production Stage
  - Reception test in laboratory
  - Radiation test in CERN facility (CHARM) (Target TID: ~750 Gy)
  - Optical Transceiver (VTRx SM): 500 pieces
  - DCDC converters (FEASTMP): 1000 pieces (2 per GEFE)
  COTS components already procured and successfully tested in radiation at PSI (except FPGA)
  Microsemi ProAsic3 FPGA:
  - Order to be placed by January 2017 (~350 pieces)
  ~350 pieces to be produced (216 BPM positions -> ~62% of spares)
  - Radiation test at CHARM by May 2017
Digital FE (GEFE + BDF) production status
(2 of 3)

## Slide 6
  Production Stage
  Foreseen by Q3 of 2017
  Custom rad-hard component already procured:
BDF Production Status
  First prototype successfully developed and tested
  Pre-Production Stage
  - Reception test in laboratory
  - ADC (AD41240): 1000 pieces (2 per GEFE)
  COTS components already procured and successfully tested in radiation at PSI (except FPGA)
  ~350 pieces to be produced (216 BPM positions -> ~62% of spares)
  - Radiation test at CHARM by May 2017
Digital FE (GEFE + BDF) production status
(3 of 3)
  Pre-production prototype foreseen by Q1 2017
  - No dedicated radiation test required (COTS components shared with GEFE except voltage regulator)
  - Replace COTS voltage regulator by rad-hard version.
  - Minor modifications
  Radiation test with final FW at CHARM by May 2017 (for final FW and FPGA qualification)

## Slide 7
BE-BI-QP
Status Review & Plans
Outline:
Digital FE production status
Installation & radiation monitoring campaign
MOPOS Project

## Slide 8
  Collaboration with Radiation Working Group (RadWG) and Monitoring & Calculations Working Group (MCWG)
  Significant difference between 2013 and 2015 reports from Radiation Protection
  Higher radiation levels in SPS that expedited
  - Advise about radiation effects mitigation techniques in electronics (e.g. TMR, encodings, etc.)
  MCWG
  RadWG
Installation & radiation monitoring campaign
  Radiation levels during operation cannot be quantified yet due to SPS performance improvements
  - RadMons installation (final positions decided before December 2016)
  - One per BPM position (216) at the rack level
  - Several BPM positions at the centre of the magnets (radiation levels may be lower there)
  - Installation during EYETS 2016/2107
  - Assistance in radiation tests
  - Assistance in RadMons data analysis and FLUKA simulations
  - Advise about radiation effects mitigation at system level (e.g. placement, shielding, etc.)
  Study ongoing for finding the most appropriate positions in terms of radiation dose

## Slide 9: Thank you
manoel.barros.marin@cern.ch
BE-BI-QP

## Slide 11: MOPOS request
BPM
RadMon
Rack
Request: estimation of radiation levels in racks positions (electronics for Beam Position Monitors - BPM)
X
BLM
97
93
33
X
RPL
X
BLM
X
RPL
Corinna Martinella EN-EA

## Slide 12: Shielding effect of the magnet
Simulations J. Saraiva
Corinna Martinella EN-EA
2600
2700
3300
3200
2800
2900
3000
3100
3400
Simulation for MBB.32090 and MBB.32030 at floor level:
Based on 2012 pattern of losses (each 40cm).
Shielding effect of the magnets: reduction of factor of 2 in both situations.
Different pattern of losses (increasing in the middle for MBB.32020).
MBB.32090 start
MBB.32090 end
MBB.32030 start
MBB.32030 end