## Slide 2: Introduction to the Linac4 Reliability Run: goals, schedule, organization
Wednesday 30 November 2016
Maurizio Vretenar

## Slide 3: Motivation
Reliability is one of the main challenges of Linac4
Goal of Linac4 is availability > 95%
(expected lower availability than Linac2 because >3 times higher energy and number of components)
Initial phase (first 1 or 2 years): expected availability < 95%
(note: this is my personal feeling…).
Example:
Linac2 fault rate after the installation of the new RFQ2 in 1993.
Reliability Run:
Debugging off-line for the initial teething problems
Objective for the Reliability Run:
reaching 90 – 95 % availability at the end of the RR.

## Slide 4: Responsibilities
4 main actors:
The operation team (BE/OP);
The supervision and setting-up team (BE/ABP);
The control and bookkeeping team (TE/MPE);
The equipment teams for good functioning and repairs (BE/RF, BE/ABP source, BE/BI, TE/EPC, TE/VSC, etc.).
Goal of this mini-workshop is to have the main actors around the table and define a plan of action to be further duscussed and then presented at Chamonix 2017 for final approval by all Groups.
Note: invited here only the equipment teams that I expect will be more involved in the Reliability Run – from the Linac2 experience!

## Slide 5: Long-term goals
The Reliability Run is intended as a step in the transition to the final operational organisation of Linac4 (being discussed between ABP and OP).
→ Towards the end of the RR, the new structure should be already in place!

## Slide 6: Organisation
Yes, but:
What will be the beam intensity and pulse length (need to compromise on activation of the dump).
What will be the operation schedule (technical stops, shutdown, etc.).
Who will check which beam parameters and what will be the threshold to declare a fault?
What will happen when a fault is declared?
Who will come to Linac4 and when if the machine is «on fault»?
Who will do the «post-mortem» of the faults, how the information will be structured and communicated, and who will decide/implement actions?
Expect an answer from Alessandra.
I will make a schedule proposal.
The operator; regular measurements to be organised.
4,5 I will present a sequence of events, for discussion.
6. TE/MPE, but the resulting actions need to be defined by the project.
Beam 24/7 on the Linac4 main dump

## Slide 7: Linac4 Masterplan
Present Masterplan
RR starts in June after completion of beam line and beam setting-up and DB measurements in the second half of May. Good timing with EYETS.
Continues until the end of 2017 run (18.12).
Could restart in 2018 if needed – for 2 months or more, before or after the end of the yearly shut-down, depending on the interventions foreseen on the machine and on the results of the initial RR period. The decision has be taken in Autumn 2017.

## Slide 8: 2017 RR schedule
Proposal:
Synchronise with the Injector Schedule – Technical Stops at the same time but longer (compromise availability of services – radiation - availability of personnel).
Allow for more Technical Stops if and when needed – to be decided during the Run.
Need to keep a flexible approach to the Run!

## Slide 9: 2017 RR schedule - proposal
Linac4 Run 1
Linac4 Run 1
Linac4 Run 2
Linac4 Run 2
Linac4 Run 3
Proposal:
Run 1: 7 weeks, June-July
Run 2: 13 weeks (should be split in 2?), August-October
Run 3: 6 weeks, November-December
Flexibility: the duration of the TS can be modulated and other TS can be added, depending on needs and plans

## Slide 10: Sequence
CCC operator detects «fault»
CCC operator analysis and action (from CCC only?)
CCC operator solves problem
CCC operator calls Linac Supervisor
CCC operator calls equip. specialist
LS solves problem
LS calls equip. specialist
Problem solved
eq. specialist solves problem
Operator Training?
Who will be the Linac Supervisors? Training?
How will be the support from equipment groups? Existing piquets, specialist support? Call-out lists?
Entry in the logbook
Who will analyse the logbook?

## Slide 11: Interventions
We understand that the same people is going to be in charge of interventions on the LHC and its injectors and on Linac4.
A new machine can be very demanding on the operation teams and we don’t want to increase stress with the risk of impacting LHC operation.
The proposal is to avoid interventions during nights: in case of a Linac4 fault detected after 17:30, the operator will try to solve the problem and if not successful the counting clock will be stopped and the specialist (linac or equipment) will be called only at 8:30 the following day – apart some exceptions (e.g. regular piquets).
But interventions should still be done during weekends, allowing for a more relaxed reaction time (time between call and time on site).
This intervention policy should be revised (both directions are possible!) following the initial experience.

## Slide 12: Conclusions
The Reliability Run is a great opportunity that we cannot miss, but to be effective it must be well organised.
All the time that we spend on Linac4 in this reliability phase will be time saved during the initial operation time!
During Reliability Run
After Reliability Run
Fixing Linac4: