## Slide 1
LHCb & EYETS 2016-2017

## Slide 2
LHC planning

## Slide 3
Detector Activities
VELO: Fix C02 pump
RICH1+2: HPD box RICH1 A-side out (FE electronics & HPD). HPD exchange (RICH2).
TT: Repair broken bonds (3 modules removed and shipped to Zurich). Replace dead VCSEL.
Dipole: Tightening current feed connectors, MSS PLC upgrade.
IT: -
OT: -
ECAL/HCAL: Change PMTs, CS 137 Scan, passive dosimeters exchange
PS/SPD: fix SPD VFE LV distribution, PRS VFE replacement, passive dosimeters exchange
M1: A Side open - fix chamber M20A1 (FEB) + other FE issues
M2-M5: Fix FE electronic issue on M2-front and M5-back, debugging of some electronic Boards (Towers). HV training…
Herschel L0/Scintillators replacement

## Slide 4
Planning

## Slide 5
Planning

## Slide 6
Planning

## Slide 7
Planning

## Slide 8
Day 1 (Dec 5)
Material for
TT
CO2 cooling/control box/cable
Preparing transfer lines support
New (rented) nacelle for CALO
PR787 crane electronic (RICH1)
GIS Bakeout
SMOG gas analysis
MUON HV training

## Slide 9
M1

## Slide 10
CO2 transfer lines

## Slide 11
Improved Muon Shielding
85 mm
74 mm

## Slide 12: Back side of HCAL

## Slide 13
M2-5 HV training

## Slide 14
CALOs

## Slide 15
RICH2 HPD

## Slide 16
RICH1

## Slide 17
Opening TT

## Slide 18
Dipole

## Slide 19
Cranes revamp.

## Slide 20: EYETS: Main tasks and constraints
Replacement AS713 (PZ85 lift) by EN-HE
    Schedule: 06/02/17 -14/04/17
    Access via PM85 shaft
    Access condition EDMS1682496
Revamping PR720&PR721 (UX85 80t overhead cranes) by EN-HE
    Schedule: Jan 30 – 14/04/17
    Limited access to detector
Very limited Time window for detector work :
From Dec 5 2016 to Jan 22 2017

## Slide 21
Access to UXA during Cranes revamping (provisional design)
(G. Roche)

## Slide 22
Access to UXA during Cranes revamping (provisional design)
(G. Roche)

## Slide 23
Important dates
EYETS from 5th of December 2016 @6am until April 30th
LHC back to OP on 14th April (powering tests)
(No access to CERN, incl. surfaces, offices …)
Experiments closed on 30th April
NO ACCESS during 
  AUG test P8: Feb 27th (incl. surface)
  Auto Transfer test Feb. 4-5th 2017
  DSO test April 7-8th (!Warning Patrol w14)

## Slide 24
CV / P8 yearly maintenance
400 kW
Weeks 3-4-5
Weeks 3-4-5 From Jan 16th to Feb 3rd 2017
  Stop of SF, SU, UW facilities
  Mechanical cleaning of towers
  Mechanical and electrical maintenance
Back-up cooling power: limited to 400kW