## Slide 1: LHC BE-BI activities in EYETS 2016/17

## Slide 2: LHC BE-BI activities in EYETS 2016/17

## Slide 3
Details BLM (S. Grishin)
System | Location | Subject | Task
BLMLHC | IP7 | Crystal Collimators | 2 new diamond BLMs under discussion and 2 new BLM
BLMD | LHC /TI | Diamond | Maintenances
BLMLHC | 6R1 | AFP | 2 new BLM ; Test of new monitors with irradiator; BI will pull cables;
BLMLHC | R8 | MKI8D rotation - Q5 | dismount-remount of BLM; (Under discussion)
BLMLHC | L2 | MKI2D rotation - Q5 | dismount-remount of BLM (Confirmed; ABT F.Castronuovo)
BLMLHC | L5 | XRP at 04L5 has been removed | Remove BLMs from already removed XRP
BLMLHC | 6L1 | ALFA | Mobile monitors dismounting
BLMLHC | 6L1 | ALFA | Installation of new ALFA station: BLMs to be removed and reinstalled
BLMLHC | 31L2 | Exchange magnet A31L2 (?) | dismount-remount of BLM, decision 2nd November
BLMLHC | S81 | Tomography test | dismount-remount of BLMBI
BLMLHC | LHC | Maintenances of BLM | Access to whole LHC, especially end of EYETS
BLMLHC | IP4 | RF zone | dismount-remount of 2 BLM and/or cables?
BLMLHC | IP1 | D1 magnets | 2 BLMs dismount -correct remount/fixation and permanent cabling
BLMLHC | IP5 | D1 magnets | new BLMs installation and cabling; Under preparation. S. Redaelli
CryoBLM | 09L5 | Change of HV and signal boxes | Change of HV and signal boxes, New cables from 09L5 to BY02 in USC55
CryoBLM | 09R7 | Change of HV and signal boxes | Change of HV and signal boxes
oBLM | L8 | oBLM | Installation of fibres in cells 08-09L8; EN cables;

## Slide 4
Details BPM (Ch. Boccard)
Impact | Location | Subject | Task
85564 | 5R | Wire collimator TCTPH.4R5.B2 | cablage des BPM et du fil sur le TCTPH.4R5.B2 + tests
85558 | 5L | Wire collimator TCL.4L5.B2 | cablage des BPM et du fil sur le TCL.4L5.B2 + tests
85566 | 7L | Installation of BPM collimator TCPP.C6L7.B1 | cablage des BPM sur le TCPP.C6L7.B1 + tests
85565 | 7R | Installation of BPM collimator TCSM.D4R7.B2 | cablage des BPM sur le TCSM.D4R7.B2 + tests
85567 | 1L | Cablage du BPMSA for AFP 6L1 | cablage du BPMSA pour AFP en 6L1 + tests

## Slide 5
DOROS (M. Gasior)
DOROS activities will concern:
- Adding new DOROS electronics for the new collimators with BPMs in P7 (TCSPM and TCPP);
- Adding new DOROS electronics for the BBLR collimator in P5 (TCTW);
- Potentially upgrading DOROS installations in P1, P2, P5, P6 and P8.
The work will be just installation of electronic modules and connecting them to the beam signals, Ethernet and timing fibres.
For the new installations the estimate is two days per point and for the upgrades also two days per point.
Most of the concerned locations are UAs.