## Slide 1: Crab Cavity engineering and production overview
Ofelia Capatina (CERN, EN-MME) on behalf of the WP4 members
International Review of the Crab Cavities Performance, 3 April 2017

## Slide 2: Overview
LHC Point 1 (vertical)
2 cavities / IP side/ beam
to be installed during LS3
LHC Point 5 (horizontal)
2 cavities / IP side/ beam
to be installed during LS3
SPS Test Prototype Module before LS2
SM18 Area
Cavity cold testing, clean room facilities & cryomodule qualification

## Slide 3: General plans
2 cryomodules for SPS tests
  1 cryomodule with 2 identical cavities (type «vertical» - DQW)
    Design as much as possible coherent with LHC
    To be tested in SPS in 2018
  1 cryomodule with 2 identical cavities (type «horizontal» - RFD)
    Design to be done as LHC prototype
    To be tested in SPS after LS2, in 2021
2 cavities pre-series for LHC (one of each type)
8 cryomodules (4 of each type) for installation in LHC during LS3 + 2 spares (1 of each type)

## Slide 4
Two types of cavities required (vertical, horizontal)
Two types of cavities under development
    Baseline : adopt both cavity types and exploit their natural RF topology
          Note: Both cavities could be used in the other plane
    Enforced common intra-cryomodule interfaces and platform
Cavity types
Double Quarter Wave (DQW) cavity – Vertical – to be used in Point 1 (ATLAS)
RF Dipole cavity – Horizontal – to be used in Point 5 (CMS)

## Slide 5
Dressed DQW cavity
Bare DQW cavity
DQW Cavity
See talk T. Capelli
See talk S. Verdu

## Slide 6
Dressed RFD cavity
Bare RFD cavity
RFD Cavity
See talk S. De Silva

## Slide 7
Cryomodules
SPS DQW cryomodule + service module
RFD
See talk K. Brodzinsky
See talks T. Capelli M. Sosin

## Slide 8: DQW Cryomodule for SPS

## Slide 9: DQW cavity manufacturing sequence

## Slide 10: Cavities and CM General schedule

## Slide 11: Cavities and CM General schedule
SPS
DQW
RFD
Preseries + series
Design
Manufacturing
Processing & cold tests
Assembly
SPS Tests

## Slide 12: Schedule SPS
UK+CERN
CERN
CERN
DQW
RFD
UK+CERN
CERN
CERN
UK
CERN

## Slide 13: Schedule SPS
UK+CERN
CERN
CERN
DQW
RFD
UK+CERN
CERN
CERN
UK
CERN
DQW:
1 cryomodule with 2 identical cavities
  Design as much as possible coherent with LHC
  Design collaboration CERN, USLARP, UK
  Manufacturing
    Cavities – CERN
    Cryomodule – CERN and UK
  Cryomodule assembly & cold test CERN
  To be tested in SPS in 2018
  RFD:
  1 cryomodule with 2 identical cavities
    Design to be done as LHC prototype
    Design collaboration CERN, USLARP, UK
    Manufacturing
      Cavities – CERN
      Cryomodule – UK and CERN
    Cryomodule assembly – UK
    Cold test – CERN
    To be tested in SPS after LS2, in 2021
See talk T. Jones

## Slide 14: DQW for SPS Status - Cavities
Both cavities manufactured
See talk M. Garlasche

## Slide 15: DQW for SPS Status - Cavities
DQW cavity manufacturing sequence
All manufacturing steps documented
See talk I. Bejar

## Slide 16: DQW for SPS Status - Cavities
See talk S. Verdu
Cavity tuning

## Slide 17: DQW for SPS Status – Cold tests
See talks A. Castilla & A. Macpherson
Cavity cold test

## Slide 18: DQW for SPS Status – HOMS & Pick-up
HOMS
Pick-up
See talks
M. Garlasche
E. Montesinos

## Slide 19: DQW for SPS Status – Helium vessel
Helium vessel
See talk P. Freijedo

## Slide 20: DQW for SPS Status – Helium vessel & cold magnetic shield assembly
Helium vessel
Cold magnetic shield
See talks
P. Freijedo
N. Templeton

## Slide 21
DQW for SPS Status – Tuning system
Helium vessel built and successfully tested
Tuning system built and successfully tested at cold
All complex components individually tested for validation
See talk K. Artoos

## Slide 22
DQW for SPS Status – CM RF internal lines
RF internal line for HOM extraction manufactured for extensive tests
All complex components individually tested for validation
Successful copper on stainless steel sputtering for FPC outer conductor by TE-VSC
See talks
T. Capelli
E. Montesinos

## Slide 23: DQW for SPS Status – Vacuum vessel
Vacuum vessel

## Slide 24: DQW for SPS Status – Magnetic & thermal shields
See talk N. Templeton
Thermal shield
Warm magnetic shield

## Slide 25
Assembly in
SM18 @ CERN
Vertical loading of equipment in vessel outside clean room
String assembly in clean room
See talks
E. Montesinos
M. Therasse
T. Capelli
DQW for SPS Status – CM assembly

## Slide 26: DQW for SPS Status – CM assembly tooling
Gantry for CM assembly

## Slide 27: DQW for SPS Status – CM assembly sequence

## Slide 28: SPS test zone
See talk G. Vandoni
V. Baglin
S. Claudet

## Slide 29: SPS test zone
See talk G. Vandoni
V. Baglin
S. Claudet

## Slide 30: SPS test zone
See talk G. Vandoni

## Slide 31: LHC
LHC layout: 4 “SPS like” cryomodules x 2 cavities each / IP side (high modularity)
Lateral view
Top view
See talk P. Fessia

## Slide 32: LHC
See talk P. Fessia

## Slide 33: Cavities and CM General schedule
SPS
DQW
RFD
Preseries + series
Design
Manufacturing
Processing & cold tests
Assembly
SPS Tests

## Slide 34: Schedule preseries and series

## Slide 35: Schedule preseries and series
March 2025 start tunnel installation last cryomodule
2x Preseries cavities to be manufactured in Industry (by the same companies that will produce series cavities)
Preseries DQW contract to be started in 2018 by CERN
Series production of 10 fully dressed DQW cavities followed up by CERN
Preseries RFD contract by US
Series production of 10 fully dressed RFD cavities followed up by US
  including processing + cold test of bare and dressed cavities
(8x + 2x spare) Cryomodule components manufacturing by CERN
Cryomodule assembly + cold tests at CERN (UK assembly of LHC prototype for RFD)
Only one existing infrastructure considered for series production strategy (processing, clean room, assembly benches, cold tests)
See talk T. Jones
See talk C. Zanoni
See talk L. Ristori

## Slide 36: Schedule series

## Slide 37: Schedule series
US contribution
RFD spare
DQW spare
Infrastructure needed at CERN (existing):
One BCP stand
One thermal treatment furnace
Two vertical tests stands (one for bare and one for dressed cavities)
One clean room string assembly zone (SM18)
One cryomodule assembly zone (SM18)
One cryomodule cold test stand in bunker (SM18)

## Slide 38: Summary
Cavities and cryo-module on track for DQW SPS tests before LS2; Very tight schedule
Same planned for RFD to be tested in SPS after LS2
  Cavities for SPS will be manufactured by CERN; Cavities manufactured by US LARP will feed useful information back into CERN’s process
  Cryo-module will be designed as LHC prototype
  Cryo-module assembly will be done in UK
Know-how will be transferred to industry for pre-series and series cavities production
  DQW dressed cavities manufacturing under CERN responsibility
  RFD dressed cavities manufacturing under US AUP responsibility
Plan for cryo-modules series production based on existing infrastructure at CERN;
  Know-how in UK developed during prototyping would be very helpful

## Slide 39: Thank you!
Teamwork and commitment