## Slide 1: Crab cavities, Cryogenics consideration for the SPS and HL-LHC
Serge Claudet, on behalf of Cryo teams dedicated to this aspects
Int’l Review Crab Cavities – CERN – 3rd & 4th April 2017

## Slide 2: Outline
Introduction,
status and perspectives for SPS (+concerns)
Introduction,
status and perspectives for HL-LHC (+concerns)
Concluding remarks

## Slide 3: BA6 general cryogenic layout
90m transfer line
Cryogenic He transfer line
Warm He pipework
Cold Box
Cryogenic LN2 transfer line
VB1
150L LHe
LN2 phase separator
LN2 storage
CCM
100L LHe
SB
VB2
150L LHe
He Heater
He Pump
Compressor station
BA5
BA1
Legend:
VB1 – valve box 1
VB2 – valve box 2
SB – service box
CCM – crab cavity module
GHe storage
A completely new cryogenic infrastructure to be installed and operational in 2 years, with very limited access to install and commission the equipment
Past EYETS: All long items
(80m cryoline, piping, cables)
Future YETS: All local items
(various cryogenic boxes)

## Slide 4: Helium main systems – status
Production plant (QSC+QUR) – Contract F702 status: Process revised with +15% w.r.t Tech. Spec. for SPS-BA6 needs, Design Review foreseen in May’17, Fabrication Q3/Q4’17, delivery mid Jan’18
Distribution system (VB1+transfer line+VB2) – IT4189 status: 80m line installed, kick-off for valves boxes tomorrow, design Q2’17, production summer’17 for delivery expected Oct’17 for meca-instrum test in workshop, installation end Jan’18
Proximity equipment (SB and flex transfer lines – DO-30000, HeP, EH) status: SB+flex designed, delivery in summer 2017, HeP in place EH identified (local connections required for both)
Storage tanks GHe + LN2 (Recovered + to be Rented) status: Integration and site acceptance in final phase, delivery before Q4’17
GHe storage tanks
Cold Box
Warm compressor station
Cryo-distribution

## Slide 5: Hi-Lumi LHC: New Cryoline @ SPS – BA6
80 m cryo distribution line installed during Feb-Mar 2017
From Cold-Box & Valve Box 1
To Valve Box 2 & RF Cryostat
In addition: warm piping in shaft, cabling anticipated with EN-EL, He pumps

## Slide 6: Baseline for controls architecture
Definition anticipated Q2’16 for obvious schedule control credibility (cable and racks already installed during EYETS early 2017)

## Slide 7: Global SPS cryo planning – status
Transf. line
VB1+VB2
Resp: K. Brodzinski
Order in place for Service Box, delivery summer’17
Resp: H. Derking + S. Claudet
Ph1 done, Ph2 being launched
Resp: L. Delprat + S. Claudet
Contract F702, delivery Mid Jan’17
Resp: J. Metselaar + O. Pirotte
Warm piping foreseen EYETS, LN2 infrastructure for 2017
Cryo for Crab Cav. At SPS
Infrastructure
Refrigeration
Distribution
Proximity
Schedule updated Autumn 2015, being followed, target to be ready for 21st Feb’18

## Slide 8: Work and perspectives for next 12 months
Storage tanks, Interconnecting piping, LN2 lines and box:
  Work to be done as much as possible (surface) during 2017
Mobile liquefyer:
  On tracks, confident as based on “industrial standard product”
Valve boxes:
  To be delivered at surface Oct’17 for checks, cabling and preparation
Instrumentation and controls:
  Being ordered “CERN supplied items” to match our standards (technical & Quality)
Installation, cabling, safety/legal and basic tests (Pressure, elec, interlocks)
  WILL HAVE TO BE DONE ON SITE, even if minimised
Training and procedures:
  At least preliminary versions to start with

## Slide 9: CONCERNS for SPS-BA6
Concepts and major procurements: Done
Design of major sub-systems: Done or being done
Fabrication: Started or being started
Deliveries: expected just in time
Installation phase: to be looked at in details
Commissioning: necessary, at least the minimum required
in LHC, no access during cool-down or warm-up between 300K and 80K
Compulsory consolidations foreseen in 2019/2020 during LS2 !
There is not much margin for crab cavities to be tested with beam in SPS in 2018, but nobody would like to be the one preventing this to happen !!!
The Cryo team is just focussed on delivering the required functionalities by 21st Feb’18
We believe all teams have a similar approach, so Jan-Feb 2018 will be extremely dense-populated with strong (competing!) commitments…
Realistic considerations will have to be added to “success oriented”
(Safety of personnel with co-activities, protection of hardware, schedule)

## Slide 10: Outline
Introduction,
status and perspectives for SPS (+concerns)
Introduction,
status and perspectives for HL-LHC (+concerns)
Concluding remarks

## Slide 11: P1/P5 Cryogenic architecture
QSCG
QSVB
QSDQ
QSRG
QSDN
QSAG
QURCG
QPLG
QXL
DFHM
DFHX
QSP
GHe storage tanks
Dryer
Liquid Nitrogen tanks
Surface cold box
Vertical transfer line
Quench tank
Surface piping
Warm compressor station
DSHX
DSHM
DSL
Q1
Q2b
Q3
CP
D1
D2
CC
CC
Q4
Q5
Q6
HRL
QRP
QPP
SHE
SHM
SD
US
SLN
SLN
Q2a
Surface
Shaft
Underground
LHC tunnel
After internal Cost to Performance review (Performance - Cost - Risk)
18 kW equivalent at 4.5 K, including 3 kW at 1.8 K
Cold compressors box
QUIG
Interconnection box
UR
UL
DFBL
Not standard components (pressure, commissioning)
(existing)

## Slide 12: HiLumi Cryogenic masterplan
Just-in-time for SPS-BA6, last studies for LHC-P4 before decision,
Some more time for us for LHC P1/P5, but interfaces required by others
Today
Significant time ahead of us for efficient studies and coordination of interfaces

## Slide 13: Work and perspectives for next years
Cooling capacity:
  So far estimates, about 10% of total requirements per point
  Project baseline to consider full CC scheme for cryoplant design
Design pressure:
  A delicate aspect: a low pressure item (2-3 B_abs) in the middle of magnets (15-20 B_abs).
  Experience with LHC (RF, Electrical feedboxes DFB’s)
  BUT this time consideration to have over-pressure safety devices in cryo-distribution line (not at all a standard, risk for CC lifetime?)
Operating Pressure:
  Absolute value (30mbar) and acceptable fluctuations (+/- 1mbar) to be evaluated
  Feasible to control a fixed value (pressure control valve) for fixed heat loads
Physical interfaces (jumpers from Cryoline QXL):
  So far “double jumper” to be considered as baseline, not an issue
  Could be wise to installed for all CC in one go, with caps/capilleries for easy connection when desired

## Slide 14: Concluding Remarks
For SPS-BA6:
  We are fully motivated and committed (21st Feb’18)
  So far just in time, but significant concerns for the co-activities Jan-Feb 2018
  We would consider wise to evaluate how to make the best use of 2018 for the crab cavities project (SPS if possible, back at surface if not possible, other?)
For HiLumi P1/P5:
  We have a bit of time ahead of us, not to be wasted!
  We believe so far that we should consider full CC scheme from scratch (not much to gain to be to strict, higher risks to have a small 2nd phase later)
  Decisions to be taken by the end of 2020 (based on what we will have at that time)